## 19-20 Summary sheet
Budget line | £k | NTS % | GDN % | IGT% | Shipper % | NTS £k | GDN£k | IGT £k | Shipper £k
Change projects Year 1 | 2500 | 1.6% | 16% | 0.3% | 82.08% | 40 | 400 | 7.5 | 2052

## 19-20 BP change details (hidden)
Title | Description | Amount | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 165000
Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 38500
Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 330000
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 55000
Actual read following estimated transfer read calculating AQ of 1 | Interim solution for XRN4713 | 55000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 55000
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 110000
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | 0% | 100% | 0% |  | 0 | 57000 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | 7.119% | 51.04% | 1.462% | 40.38% | 11746.7058 | 84211.587 | 2412.4667 | 66629.2405
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | 0% | 100% | 0% | 0% | 0 | 58000 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 165000
Allowance for unforseen |  | 394000 | 7.119% | 51.04% | 1.462% | 40.38% | 28049.7096 | 201087.0622 | 5760.678 | 159102.5501
Total Change Budget 19-20 | [6 empty] | 39796.4155 | 400298.6491 | 8173.1447 | 2051731.7907

## Sheet2 (hidden)
Spend To date
June 19 Release ( XRN4679) | 51165.89
DDP | 50000
MOD700 | 40448

## Sheet1 (hidden)
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 |  | DN
XRN4991: MOD700 |  |  |  | 80896 | 50% | 50% |  |  | 40448 | 40448 | Excluding June 20 | 141613.89
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 2020-06-01 | 247893
DN

## 19-20 - Spend to date (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [8 empty] | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 19/20 Pipeline | 0 | 171053.49 | 10299.9 | 731583.61 | [8 empty] | 2500 | 960.833 |  | 1539.167 | 960.833
19/20 Budget | 40000 | 400000 | 7500 | 2052000
Variance | -40000 | -228946.51 | 2799.9 | -1320416.39
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 85913 | 100% |  |  |  | 85913 | 0 | 0 | 0
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 |  |  |  |  | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 271954 | 100% |  |  |  | 271954 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-06-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-06-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 |  |  |  |  | 0 | 0 | 0 | 0
XRN4677: Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | Cancelled | [5 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 | 0 | 0
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | ? | [5 empty] | 0 | 0 | 0 | 0
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | Cancelled | [5 empty] | 0 | 0 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 76367 | 100% |  |  |  | 76367 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 40000 | 100% |  |  |  | 40000 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 5434 | 100% |  |  |  | 5434 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 9139 | 50% | 50% |  |  | 4569.5 | 4569.5 | 0 | 0
XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Descoped from June 20 | [7 empty] | 0 | 0 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 5928 | 100% |  |  |  | 5928 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 8151 |  |  |  | 100% | 0 | 0 | 0 | 8151
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 8892 | 100% |  |  |  | 8892 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for June 20 |  | 2020-06-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 10868 |  | 90% |  | 10% | 0 | 9781.2 | 0 | 1086.8
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 5434 | 100% |  |  |  | 5434 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 75845 | 100% |  |  |  | 75845 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 16000 | 100% |  |  |  | 16000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0
[9 empty] | 731583.61 | 171053.49 | 0 | 10299.9

## 19-20 Final Cost view (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [9 empty] | Budget £k | Actual |  | Budget | Actual
Change Budget 19/20 Actual cost | 0 | 344531.89 | 72698.6 | 983609.8168 | [9 empty] | 2500 | 1400.8403 |  | 1099.1597 | 1400.8403
19/20 Budget | 40000 | 400000 | 7500 | 2052000 | [10 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | -40000 | -55468.11 | 65198.6 | -1068390.1832 | [9 empty] | 20/21 June 20 Release |  | 171819.3128 | 43255.2521 | 113689.8466 | 328764.4115
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £ |  | 20/21 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 75174 | 100% |  |  |  | 75174 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 | 100% |  |  |  | 24896 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 268274 | 100% |  |  |  | 268274 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-11-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7 |  |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-11-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4 |  |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 | 100% |  |  |  | 23000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | 2019-11-01 | 59097 | 33% | 67% |  |  | 19502.01 | 39594.99 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 59097 | 100% |  |  |  | 59097 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 25510 | 100% |  |  |  | 25510 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 59984 | 100% |  |  |  | 59984 | 0 | 0 | 0 |  | 32131 | 100% |  |  |  | 32131 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 97579 | 50% | 50% |  |  | 48789.5 | 48789.5 | 0 | 0 |  | 51831.2915 | 50% | 50% |  |  | 25915.6457 | 25915.6457 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 48679.6684 | 100% |  |  |  | 48679.6684 | 0 | 0 | 0 |  | 24894.0466 | 100% |  |  |  | 24894.0466 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 54902 |  |  |  | 100% | 0 | 0 | 0 | 54902 |  | 27043.7336 |  |  |  | 100% | 0 | 0 | 0 | 27043.7336
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 31990.1193 | 100% |  |  |  | 31990.1193 | 0 | 0 | 0 |  |  | 100% |  |  |  | 0 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for Nov 20 |  | 2020-11-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0 |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 167345 |  | 90% |  | 10% | 0 | 150610.5 | 0 | 16734.5 |  | 162115.1856 |  | 90% |  | 10% | 0 | 145903.667 | 0 | 16211.5186
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 57903.5192 | 100% |  |  |  | 57903.5192 | 0 | 0 | 0 |  | 30749.1543 | 100% |  |  |  | 30749.1543 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 72185 | 100% |  |  |  | 72185 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 15420 | 100% |  |  |  | 15420 | 0 | 0 | 0 | CCR | [5 empty] | 0 | 0 | 0 | 0
XRN4779 - Adding AQ to PARR Report |  |  |  | 31159 | 100% |  |  |  | 31159 | 0 | 0 | 0
XRN5064-Meter Asset enquiry API enhancement |  |  |  | 12000 | 100% |  |  |  | 12000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
[9 empty] | 983609.8168 | 344531.89 | 0 | 72698.6 | [6 empty] | 113689.8466 | 171819.3128 | 0 | 43255.2521

## 19-20 Year End Forecast (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [9 empty] | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 19/20 Pipeline | 0 | 355523.6799 | 71268.1128 | 1038827.5259 | [9 empty] | 2500 | 1465.6193 |  | 1034.3807 | 1465.6193
19/20 Budget | 40000 | 400000 | 7500 | 2052000 | [10 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | -40000 | -44476.3201 | 63768.1128 | -1013172.4741 | [9 empty] | 20/21 June 20 Release |  | 174041.5104 | 41701.2347 | 156977.8676 | 372720.6127
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £ |  | 20/21 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 85913 | 100% |  |  |  | 85913 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 | 100% |  |  |  | 24896 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 271954 | 100% |  |  |  | 271954 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-11-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7 | 2020-06-01 |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-11-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4 | 2020-06-01 |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 | 100% |  |  |  | 23000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4677: Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | Cancelled | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | ? | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | Cancelled | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 76367 | 100% |  |  |  | 76367 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 40000 | 100% |  |  |  | 40000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 59100.11 | 100% |  |  |  | 59100.11 | 0 | 0 | 0 |  | 32044 | 100% |  |  |  | 32044 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 95945.3193 | 50% | 50% |  |  | 47972.6596 | 47972.6596 | 0 | 0 |  | 84248 | 50% | 50% |  |  | 42124 | 42124 | 0 | 0
XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Approved for June 20 |  | 2020-06-01 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 47620.2555 | 100% |  |  |  | 47620.2555 | 0 | 0 | 0 |  | 24894.0466 | 100% |  |  |  | 24894.0466 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 53445.0983 |  |  |  | 100% | 0 | 0 | 0 | 53445.0983 |  | 27043.7336 |  |  |  | 100% | 0 | 0 | 0 | 27043.7336
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 30401 | 100% |  |  |  | 30401 | 0 | 0 | 0 |  |  | 100% |  |  |  | 0 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for Nov 20 |  | 2020-11-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0 | 2020-06-01 | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 167609.1448 |  | 90% |  | 10% | 0 | 150848.2303 | 0 | 16760.9145 |  | 146575.0115 |  | 90% |  | 10% | 0 | 131917.5104 | 0 | 14657.5012
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 56932.3908 | 100% |  |  |  | 56932.3908 | 0 | 0 | 0 |  | 57915.821 | 100% |  |  |  | 57915.821 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 75845 | 100% |  |  |  | 75845 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 15420 | 100% |  |  |  | 15420 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4779 - Adding AQ to PARR Report |  |  |  | 36159 | 100% |  |  |  | 36159 | 0 | 0 | 0
XRN5064-Meter Asset enquiry API enhancement |  |  |  | 12000 | 100% |  |  |  | 12000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
[9 empty] | 1038827.5259 | 355523.6799 | 0 | 71268.1128 | [6 empty] | 156977.8676 | 174041.5104 | 0 | 41701.2347

## 20-21 Year End Forecast
| NTS £ | GDN£ | IGT £ | Shipper £ | [9 empty] | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 20/21 Pipeline | 4000 | 364319.3128 | 94005.2521 | 953439.7475 | [9 empty] | 3000 | 1415.7643 |  | 1584.2357 | 1415.7643
20/21 Budget | 48000 | 600000 | 9000 | 2343000 | [9 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | -44000 | -235680.6872 | 85005.2521 | -1389560.2525 | [8 empty] | 21/22 Forecast | 0 | 0 | 0 | 0 | 0
Title | Description | ROM/HLSO/BER/CCR | 19/20 spend | Amount | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £ | 21/22 | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £
XRN4941 Auto updates to meter read frequency (MOD0692) |  | 19/20 BER, 20/21 HLSO | 31990.1193 | 44000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 44000 | [5 empty] | 0 | 0 | 0 | 0
XRN4932 - Improvements to the quality of the conversation factor values held on the supply point register (MOD0681S) | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER | 57903.5192 | 30749.1543 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 30749.1543 | [5 empty] | 0 | 0 | 0 | 0
XRN4930 - Requirements to inform Shipper of Meter Link Code Change | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER | 48679.6684 | 24894.0466 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 24894.0466 | [5 empty] | 0 | 0 | 0 | 0
XRN4888 - Removing duplicate address update validation for IGT Supply Meter Points via CMS | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER | 54901.791 | 27043.7336 | 0% | 0% | 100% | 0% | 0 | 0 | 27043.7336 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to treatment and reporting of CYCL reads | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER | 59984.478 | 32130.9009 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 32130.9009 | [5 empty] | 0 | 0 | 0 | 0
XRN4850 - Notification of customer contact details to Transporters | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER | 167344.5788 | 162115.1856 | 0% | 90% | 10% | 0% | 0 | 145903.667 | 16211.5186 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) improvements | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER | 97578.5807 | 51831.2915 | 0% | 50% | 0% | 50% | 0 | 25915.6457 | 0 | 25915.6457 | [5 empty] | 0 | 0 | 0 | 0
XRN4871B Modification 0665 - Changes to ratchet regime | Part B only - functional changes to auto calculate associated ratchet charges | HLSO | 9880 | 52500 | 0% | 100% | 0% |  | 0 | 52500 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | Agreed in Feb 20 CHMC to close change |  | 5187 | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | Agreed in Feb 20 CHMC to close change |  | 5434 | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes |  |  | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes |  |  | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5053 - Single sided nominations improvements | Gemini Funded change |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5054 - Negative implied flow rates | Gemini Funded change |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4801 - Additional information to made veiwable on DES | November 20 release | HLSO |  | 55000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 55000 | [5 empty] | 0 | 0 | 0 | 0
XRN4931 - Submission of space in mandatory data on multiple SPA files | November 20 release | HLSO |  | 25000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 25000 | [5 empty] | 0 | 0 | 0 | 0
XRN4992 - MOD0687 creation of new charge to recover Last Resort Supply Payments | November 20 release Option 1 90,000 GBP(enduring) subject to ofgem approval Option 4 30,000 GBP(interim) subject to ofgem approval | HLSO |  | 120000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 120000 | [5 empty] | 0 | 0 | 0 | 0
XRN5036 Updates to must read process | November 20 Release Option 1 costs 30k (progressing with this option) Option 2 costs 48k | HLSO |  | 30000 | 0% | 100% | 0% | 0% | 0 | 30000 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5048 - Make an indicator available where a Supply Meter Point forms part of a Network Trial | Closed with no further action |  |  |  | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5038 - MOD0691 CDSP to convert class 3 or 4 meter points to Class 1 when G1.6.15 criteria is met | ROM costs |  |  | 70000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 70000 | [5 empty] | 0 | 0 | 0 | 0
XRN4899 - PSR - Change of Supplier event | November 20 release | HLSO |  | 22750 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 22750 | [5 empty] | 0 | 0 | 0 | 0
XRN4897 - Resolution of deleted Contact Details (contained within the S66 records) at a change of Shipper event | November 20 release | HLSO |  | 22750 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 22750 | [5 empty] | 0 | 0 | 0 | 0
XRN5070 - amendments to isolation flag | Awaiting HLSO |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
Market Trial for 2 Major releases |  |  |  | 250000 | 1.6% | 20% | 0.3% | 78.1% | 4000 | 50000 | 750 | 195250 | [5 empty] | 0 | 0 | 0 | 0
PAFA/PAC reporting changes |  |  |  | 75000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 75000 | [5 empty] | 0 | 0 | 0 | 0
XRN 5072 - Class 4 with AMR/DRE installed-RGMA flow received with no RTC count |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5080- Failure to supply gas (FSG/GSOP1)-System changes |  |  |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5091 - Defferral of creation of class change reads at tranfer of ownership |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5092 - iConversion phase2 | to be funded from Gemini |  |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5093 - Update of AUGE table to reflect new EUC band |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. |  |  | 60000 |  |  |  | 100% | 0 | 0 | 0 | 60000 | [5 empty] | 0 | 0 | 0 | 0
XRN5014 - Facilitating hydeploy live trials | November 20 release | HLSO |  | 60000 |  | 100% |  |  | 0 | 60000 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4780B - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4780C - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | November 20 release - 130,000 | HLSO |  | 130000 |  |  |  | 100% | 0 | 0 | 0 | 130000 | [5 empty] | 0 | 0 | 0 | 0
IGT DDP access |  |  |  | 50000 |  |  | 100% |  | 0 | 0 | 50000 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5116 Domestic Report - Must Read Prenotification |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5120 MAP to UKL Monthly Comparison Service |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
XRN5121 Supplier Portfolio Service |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
XRN5122 Gemini System Enhancements - Delivery |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5142 New Allowable Values for DCC Service Flag in DXI File From DCC |  |  |  | 0 |  | 90% | 10% |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5143 Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP |  |  |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5146 Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) |  |  |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | CSS Funded |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5147 Optimising the Must Read process for IGT Customers |  |  |  | 0 |  |  | 100% |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5164 CSEP Data Assurance – Performance Monitoring Capability |  |  |  | 0 |  | 90% | 10% |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5167 Report Product Class 4 Read Performance (MOD 672) |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5168 – MOD0721 – Shipper submitted AQ Corrections during COVID-19 |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5169 – MOD0722 – Allow Users to submit Estimated Meter Readings during COVID-19 |  |  |  | 0 |  | 67% |  | 33% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5170 – MOD0723 – User of the Isolation Flag to identify site with abnormal load reduction during COVID-19 period |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5171 – MOD0724 – Amendment to Ratchet charges during COVID-19 period |  |  |  | 0 |  | 67% |  | 33% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN5172 MOD0725 – Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 |  |  |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
XRN4923-AQ calculation for RGMA (ONUPD) customer reads |  | HLSO |  | 20000 |  |  |  | 100% | 0 | 0 | 0 | 20000 | [5 empty] | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
New CP to combine XRNs 4691-4694 | Expected to be delivered via DDP |  |  | 0 |  | 90% | 10% |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
[18 empty] | 0 | 0 | 0 | 0
Total Change Budget 20-21 |  |  |  | 3000000 |  |  |  |  | 4000 | 364319.3128 | 94005.2521 | 953439.7475 | [5 empty] | 0 | 0 | 0 | 0
[9 empty] | 48000 | 600000 | 9000 | 2343000