## Slide 1: XRN4996 - June 20 Release - Status Update
27th May 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Issues with User Acceptance Testing (UAT) and Regression Testing (RT) have been experienced by Xoserve which is has had a cumulative impact on plan. RAG status remains Amber, however we remain on track to Go Live on 27th June Delivery: UAT assurance in progress for final change XRN4865 RT re-plan completed. RT in progress for final 2 changes XRN4850 and XRN4888 Performance Testing: In progress for remaining 2 changes, XRN4888 and XRN4850 Penetration Testing: In progress forXRN4850, no Critical or High risk findings have been identified Market Trials: MT commenced with 4 participants on 1st June following confirmation of Go decision on 29th May. iDR: Preparation has commenced with a planned execution on 12th/13th June Implementation: Implementation date of Saturday 27th June confirmed. Implementation approach shared. |  |  | 
Risks and Issues | Risk – There is a risk that the progress of June 20 project phases will be impacted because of the impacts on resources (i.e. illness/remote working) of the spread of COVID-19 leading to a delay to the implementation of the release. |  |  | 
Cost | Project Delivery costs are in line with approved BER |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases, COVID19 priorities etc.) is ongoing |  |  | 

## Slide 2: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion
- 19/09/19
Design completion
- 13/12/19
Build & Unit Test completion
- 31/01/20
System Testing completion
- 03/04/20
UAT completion
- 05/06/20
Regression Test completion
- 12/06/20
Market Trials completion
- 19/06/20
Implementation
- 27/06/20
PIS Completion
- 25/09/20 (provisional)

## Slide 3: June 20 Release Summary
June 20 Release consists of 7 changes, Implementation is planned for June 2020:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 – Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
  MAP ID data load into UK Link is being planned for implementation during the PIS period
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs. Descoped at ChMC on 08/01/20
** Descoped at eChMC on 22/11/19
*** Added to scope (revised scope from original)