## Slide 1: XRN4914 MOD 0651- Retrospective Data Update Provision – Proof of Concept Progress update
10th June 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delivery: Step 2 deep dive analysis is in progress however it has not progressed to plan due to additional resource constraints (sickness) in Customer Change team impacting ability to focus on Retro activity. The project team are still working towards publishing Industry Packs and Retro recommendations in late June however this is dependent on resources being in place to support the POC. Internal discussions have taken place to ensure wherever possible resources are allocated to POC activity The intention is to publish Step 2 outputs ahead of next ChMC in July then present the findings and recommendations at the meeting Customer Engagement and Communications: Ongoing communication with POC participating members on progress of Step 2 deep dive Intention is to present findings in July ChMC |  |  | 
Risks and Issues | There is a risk that resources in place to support Retro POC deep dive analysis are pulled from Retro to support priority or urgent MOD work Mitigation: Project team are working with resources to ensure they are ringfenced to support POC where possible to meet planned timescales |  |  | 
Cost | Approval received from DN’s for BER of £270k for proof of concept. Costs within approved budget. |  |  | 
Resources | Xoserve Customer Change team leading execution of POC Step 2 with input from SMEs where required |  |  | 
XRN4914 MOD 0651 - Retrospective Data Update Provision - ChMC Update 10th June

## Slide 2: XRN4914 – Retro proof of concept – Timeline
2019 / 2020
Customer Engagement
Key:
Completed
Slipped / High risk
Medium risk
On-target
Support
Analysis
Customer / Advocates encouraging participation
Checkpoint 1 29th Nov
Design (Step 1)
Test files can be accepted
Initial Customer engagement
kick-off 4th Nov
Planning
Develop (Step 2)
Testing (Step 2)
Kick-off prep
Actual data
files in
Step 1 Compare / Outcome / Aggregate
Initial Customer engagement of File receipt and triage
Actual data files can be accepted
Test data
files in
8th Dec data sliced
Output from Step 1 (Volunteer Shippers > ChMC > PAFA > Website)
Recommendations
Develop (Step 1)
Testing (Step 1)
Checkpoint 2 4th Feb
Design (Step 2)
Dates need to be confirmed post Step 2
results as volumes will inform task size
File Triage
Core Retro Shipper Pack
XRN4914 MOD 0651 - Retrospective Data Update Provision – 13th May 2020
Checkpoint 3 May 1st
Bi - Weekly project update via external communication methods
Technical Support (Innova & Data Strategy) – Excluding Environment maintenance which continues
Industry Pack
RGMA & MAM
Raw Data
Notes: Tony