## Slide 1: Amendment Invoice Update
17th June 2020

## Slide 2: Summary
120 unique MPRNs with ASP mismatch.
ASP file merge activities included all 120 of the MPRNS that were originally missed.
Automation of Exception resolution underway and resolution steps for a number of exception codes have been implemented.
Defect resolution and deployment has been affected by re-prioritisation and focus on AQ issues and test environment availability issues causing bottle necks through-out the process. RTG forecast to be by 31st July 2020.

## Slide 3: Summary Resolution Plan
Apr
May
Jun
Jul
Aug
Sept
Mobilise
Oct
Nov onwards
ASP / AML Mismatches
Exclusions
Defects
MI / Reporting
Backlog Clearance
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
RCA activities
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
Backlog Clearance
Operating within SLA
Deploy MI solution
Operating within SLA
Exceptions (LSPs)
Exceptions (SSPs)

## Slide 4: Supporting Information Mismatches
SLA
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
GREEN
RAG Justification
120 MPRNs out of the 249,620 LSPs (0.05%) that were billed incurred an ASP mismatch.
120 unique MPRNs with ASP mismatch. File merge activities ensured mismatch data was included in ASP file issue on the invoice issue date.
All AML files were delivered ahead of the SLA date with the exception of 1 customer with limited IX kit.
 |  |  | ASP Mismatches |  | AML Mismatches |  | 
Billing Month | Billed Contracts | LSP Invoiced | Unique LSP MPRNs causing ASP mismatch | % of invoiced LSPs causing ASP mismatches | SSP Invoiced | Unique SSP MPRNs causing AML mismatch | % of invoiced SSP causing AML mismatches
Apr-19 | 8,896,444 | 184,562 | 264 | 0.14% | 8,711,882 | 5,594 | 0.06%
May-19 | 9,648,261 | 168,267 | 118 | 0.07% | 9,479,994 | 7,493 | 0.08%
Jun-19 | 9,653,613 | 178,064 | 65 | 0.04% | 9,475,549 | 1,882,702 | 19.87%
Jul-19 | 9,895,118 | 180,536 | 92 | 0.05% | 9,714,582 | 250 | 0.00%
Aug-19 | 9,977,884 | 230,802 | 254 | 0.11% | 9,747,082 | 208 | 0.00%
Sep-19 | 11,133,817 | 310,321 | 284 | 0.09% | 10,823,496 | 2,701 | 0.02%
Oct-19 | 11,067,074 | 252,181 | 855 | 0.34% | 10,814,893 | 9,235 | 0.09%
Nov-19 | 10,746,544 | 235,402 | 110 | 0.05% | 10,511,142 | 585 | 0.01%
Dec-19 | 9,907,903 | 227,508 | 133 | 0.06% | 9,680,395 | 2,019 | 0.02%
Jan-20 | 11,143,336 | 190,009 | 189 | 0.10% | 10,953,327 | 1,521 | 0.01%
Feb-20 | 10,672,939 | 206,203 | 151 | 0.07% | 10,466,736 | 247 | 0.002%
Mar-20 | 11,210,849 | 257,092 | 172 | 0.07% | 10,953,757 | 1,113 | 0.010%
Apr-20 | 10,308,100 | 249,620 | 120 | 0.05% | 10,058,480 | 4,582 | 0.046%

## Slide 5: Exceptions
SLA
Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
AMBER
RAG Justification
A number of exceptions BAU (raised between 1st August and current date) continue to miss the 2 month SLA. Cataloguing of Exception resolution steps has now been completed and the documents in the process of being approved.
What is an exception?
Business or Technical processing errors generated within our system, that cause reconciliations at individual sites, to be held back off the Amendment Invoice until resolved.
130,441 distinct MPRNs currently have unresolved exceptions within our systems (as of 1st June 2020).
(Jan-20 208,037, Feb-20 = 219,491, Mar-20 = 320,023)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 6: Unworkable Exceptions
The majority of exceptions are resolved via a technical or business solution and have no impact to customers as they are resolved before they are needed in the next step of the process. However, there are three outstanding exceptions which we are unable to resolve. Details of these are below and an initial industry communication was issued on 27th April 2020.
Exception Type | SAP Message Text | Exception Count at 27/05/20 | Average Growth Per Month | Unique MPRN Count at 27/05/20 | Customer Impact | Target Deploy date | Backlog - Clearance date | Comments/Status
MN09 | NDM Recn- Prevailing Volume is zero | 165,623 | 9,300 | 97,138 | Reconciliation charges are not being invoiced to the Shipper for the period that is being held due to the exception and subsequent periods | TBC (Perm solution) | June (Tactical solutuon) | Solution agreed, target implemenation date July 20th. Plan for backlog TBC
BI49 | Variance value for isolation period has non-zero value | 10,251 | 230 | 10,251 | 1. If the site is consuming but the meter point remains as 'isolated' on UKLink, the energy consumed is not being billed and will therefore be picked up in UIG. 2. When the isolation status is updated, following acceptance of a read, any reconciliations for periods after the status update will not be processed | Mid Feb 2021 | TBC | Solution confimed, target implementation for July Permanent change delivery via CTO projects – Richard Hadfield.
BI29 | Change to group characteristics for installation | 197 | 10 | 197 | No Rec periods are being invoiced to the Shippers for the the period that is being held due to the exception and subsequent periods. | Linked to main Primes & Subs Change | July | Tactical solution established. Requires manual input of meter reads on a case by case basis.

## Slide 7: Exclusions
SLA
Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection.
Target Date to operate within SLA
July 2019
Current SLA RAG Status
AMBER
RAG Justification
Cataloguing of all scenario resolution steps to ensure accuracy now completed.
What is an exclusion?
Until permanent system fixes are deployed to address charge calculation errors, monthly profiling of new reconciliations received that relate to the scenario of the open defect is performed, with “bill blocks” applied to that MPRN to safeguard the accuracy of the amendment charge calculations by exclusion from the AMS.
1,158 distinct MPRNs for the April 2020 billing period currently have bill blocks placed upon them (as at 1st June 2020). Bill blocks are placed on MPRNs where there are known issues that will result in incorrect charges being calculated.
(Jan-20 = 2,894, Feb-20 = 11,208, Mar-20 = 4,567)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 8: Defects
SLA
Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
RED
RAG Justification
1 Defect did not meet the May SLA: - 61452 – This defect was previously delayed as clarification was required whether the defect was to be included in existing CR. Following further analysis, it was agreed to continue as a defect. UAT was delayed due to environment outage in April 20. Defect is currently with UAT and is being progressed however there is an issue with authorisation within the class change process which the technicians are working through.
14 open ASP/AML related defects as of 3rd June 2020
(14 defects open at last month’s update)
Defect ID | Defect Title | Date Detected | Target Fix Date | SLA Resolution Date
1513 | MR15 exception not created when the variance volume was negative but total volumes was positive and vice versa | 17/12/2019 | TBC | 06/03/2020
1520 | Incorrect Volume in SAP due to multiple check read processing on same day in incorrect sequence | 07/01/2020 | TBC | 06/03/2020
61159 | Class change from 4 to 1 not updating total check to check volume and energy against MRD | 24/01/2020 | 27/03/2020 | 03/04/2020
61452 | Rec is not happening for Prime and sub site when there is RGMA or class change or shipper transfer estimated read | 19/02/2020 | 08/05/2020 | 08/05/2020
61896 | High Value rec report is not displaying data properly and requires some code changes | 20/03/2020 | 27/04/2020 | 05/06/2020
61941 | Check to Check rec is not happening for a particular MPRN | 25/03/2020 | 30/04/2020 | 05/06/2020
62028 | Replacement read for inactive read should be rejected. | 01/04/2020 | 05/06/2020 | 05/06/2020
62060 | The cyclical read received with read on class change end date should be made inactive to avoid issues with rec | 03/04/2020 | 05/06/2020 | 05/06/2020
62134 | NDM Replacement read – The forward reconciliation is updating an incorrect volume against billable order (RR-02) | 08/04/2020 | 05/06/2020 | 05/06/2020
62178 | MR19 exception needs to be created in cases where profiles upload results in errors | 16/04/2020 | 10/07/2020 | 10/07/2020
62397 | Amendment billing issue; When a bill adjustment trigger is spanning across two contracts, it is not getting properly billed. | 15/05/2020 | 07/08/2020 | 07/08/2020
62432 | ASP Simulation Job Failure for the Bill Month 03.2020 | 20/05/2020 | 07/08/2020 | 07/08/2020
62434 | There are incorrect Records In the ASP Simulation File | 20/05/2020 | 07/08/2020 | 07/08/2020
62513 | (Introduced by Defect 1464) - When the Cyclic read is received in the Class 3 period before RGMA activity date(D-1), the Profile values are being loaded. | 29/05/2020 | 07/08/2020 | 07/08/2020

## Slide 9: MI / Reporting
SLA
All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
Reports shared with all customers and general and individual WebEx’s are ongoing.
MI reports continue to be shared with our customers 2 business days after Amendment invoice issue date.
Ongoing individual customer meetings to discuss what the MI means specifically to them.
If any customer would like an explanation of the MI reports they receive just let us know and we will arrange a session (contact Dan Donovan, Xoserve Invoicing Business Process Manager - dan.l.Donovan@xoserve.com).

## Slide 10: Summary Resolution One Pager
Mismatches | Exceptions | Exclusions | Defects | MI / Reporting
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age. | Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old. | Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection. | Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised. | All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA |  |  |  | 
September 2019 | August 2019 | July 2019 | August 2019 | August 2019
Current SLA RAG Status |  |  |  | 
GREEN | AMBER | AMBER | RED | GREEN
RAG Justification |  |  |  | 
120 MPRNs with ASP mismatch ASP file merge activities ensured the mismatch data for the affected MPRNs were included in the ASP online file. 1 customer with limited IX kit did not received their AML files ahead of SLA. All other files delivered in line with SLA | A number of exceptions BAU (raised between 1st August and current date) continue to miss the 2 month SLA. Automation of Exception resolution underway and resolution steps for a number of exception codes have been implemented. | 1,158 unique MPRNs excluded from March 2020 invoice cycle. | 1 Defect did not meet the May SLA: 61452 – This defect was previously delayed as clarification was required whether the defect was to be included in existing CR. Following further analysis, it was agreed to continue as a defect. UAT was delayed due to environment outage in April 20. Defect is currently with UAT and is being progressed however there is an issue with authorisation within the class change process which the technicians are working through. | Reports shared with all customers 2 business days after Amendment invoice issue date.