## Slide 1: CSSC Programme Dashboard
28th May 2020

## Slide 2
Executive Summary
Key Programme Update: All programme milestones falling into this reporting period have been met. We continue to track to an Amber staus. Data Migration – planned PIT activities have completed with our exit report and data summary report have been provided to the SI. Xoserve commenced DMT smoke testing to plan on the 11th May. The CSSP were unable to commence smoke testing to plan due to having no environment, this has since been resolved with Landmark joining later than the other ESP’s. We have encountered defects related to REL data relating to design discrepancies between programme documentation. Issues are being progressed with one severity 1 being raised against Landmark. SIT: Xoserve has entered SIT on the 29th April, early tests has highlighted issues with the CSSP in several areas of their solution not being complete. These issues have been documented and escalated to be addressed by DCC/CSSP/SI. Initially only 9/17 planned test could be completed due to issues at Landmark’s end. The SI are progressing with fixes being released on a phased basis. Environments: Xoserve have raised concerns in relation to the number of environments required by the Switching Programme for various test phases. We have asked for an exercise to rationalise environment usage by re-planning to allow reuse where possible. This is an effort to reduce the environment costs that will be incurred by both Xoserve and other Industry parties based on the current plan. Internal Testing – SIT phase 2 has successfully completed with all P1 and P2 defects closed. P3 and P4 defects are being analysed and resolved during the next phase. SIT phase 3 has commenced to plan. NFR testing is in progress alongside preparation for SIT phases 4 & 5 and UAT. DES/API Agile delivery continues to plan in order to feed into SIT phase 4. CCMT: Re-planning is in progress with agreement from both Ofgem and the Market Trials Working Group that consequential testing will commence on the 1st December 2020. COVID-19: Xoserve continue its BCM activities, including remote working. Xoserve will be working through the lower level detail of the Programme re-plan activities with the SI during the next couple of weeks. The finalised plan is due to be approved at September’s delivery group.
Programme Health – RAG |  | 
Overall Programme Status | Previous | Current
Programme Plan – On Track | Previous | Current
Risk Profile | Previous | Current
Resources | Previous | Current
Return To Green Plan |  | 
Resources, Risk and Plan are showing Amber due to uncertainties with the lack of an Ofgem plan. RTG will take place when a plan materialises. Based on this, the programme continues to trend at an amber status |  | 
KEY Progress (Last Month) |  | 
External DMT entry achieved Good progress on external NFR testing readiness Secondary API baselined External SIT entry achieved Internal SIT Phase 2 completed Internal SIT Phase 3 commenced Programme Re-plan (including finances) started to align to Switching Programme near term plan |  | 
Programme Update

## Slide 3: Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Data Migration | Overall RAG is Amber: Schedule is Amber as Smoke testing start was delayed due to Landmark environment not being available with test execution rescheduled. Planning for DMT non functional is behind schedule due to the SI working on re-planning the upcoming DMT phases and environment requirements.
 |  | DES & APIs | On track for delivery to meet Internal test phases and consequential market trials.
 |  | Networks | Overall RAG Amber. This is unchanged pending submission of the Ofgem CR as captured at the Switching Programme Implementation Group on 14/4/20 detailed below - IG10-A03: Adaptor Services Recommendation 17 - It was confirmed that no party intends to use the IX network to connect to the CSS and that Ofgem, Xoserve and DCC were collaborating to identify the appropriate mechanism to descope IX delivery from the Switching Programme which will be implemented via a CR.
 |  | Testing | Overall RAG Green: Test phases in progress and tracking to plan. Severity 1 & 2 defects are being resolved within test phase with severity 3&4 being analysed and resolved within the next phase.
 |  | Market Trials | Overall RAG is Green.CCMT timelines have been shared with Ofgem and the CCMTWG community with positive responses. Work will continue on all CCMT preparation activities.
 |  | UK Link | Overall RAG Green. CR delivery and Test support is continuing to progress to plan
 |  | Service Management | Overall RAG green. Decision required around the option to integrate Incident Management and Service Request processes once IA has been completed. Workshops with DCC required for each core process where outstanding questions can be discussed and assumptions validated/rejected. Proposed workshop schedule issued to DCC however, awaiting confirmation that the dates are suitable.
 |  | Gemini | Overall RAG green. The schedule is amber until details of the Programme re-plan are available. Most of the Gemini defects that have been raised during UK Link SIT have now been resolved and closed. We have been working with the test stream and have made some good progress on the testing of the Gemini triggers. There are ongoing conversations around when Gemini UAT will take place, along with the transition to the Gemini ECP environments.
 |  | Business Change | Overall RAG Green. The business change assessment pack to support BC020 has been completed and sent to Ofgem and the SI on 09/04​. A re-plan will be conducted once the SI issue a revised CSS IP which incorporates the 6-month extension announced by Ofgem.
 |  | Environments & Release Mgt. | Overall RAG green. Review of all environment requests to take place using the updated test plan as reference which could impact scope.

## Slide 4: Key Programme Issues
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62484 |  | Data | The SI have confirmed that there are a number of discrepancies in data definitions between the PHID and the DM solution design document set. These have yet to be shared with parties for review. This may impact on DMT, and downstream functionality (including SIT) if parties have coded against differing elements of the design | Discussions ongoing with the SI to agree options with the aim of minimizing impacts to industry parties | 27/05 A meeting has been scheduled for 28/05 to determine how temporary data fixes can be applied so that DMT is not delayed. Further consideration is required to determine the enduring fix requirements and impact on the core functionality (and therefore any impact on SIT) | 0506/20
62485 |  | Data | The PHID defines REL logical status and language as optional data items, however the DM validation catalogue shows them as mandatory. Xoserve have coded these as mandatory, and they are part of a composite key and so raised a Sev1 defect in smoke testing on receipt of a data file which did not contain the data expected. There is disagreement between parties over the correct definition of the data items which needs to be resolved in order for DMT to proceed. | Discussions ongoing with the SI to agree options with the aim of minimizing impacts to industry parties | 27/05: Xoserve have reviewed their design and believe that these fields should always be populated - there are no instances where a value can not be determined. Without these values populated it becomes impossible to determine whether duplicate / erroneous data has been provided. To be discussed further with Landmark and SI | 05/06/20

## Slide 5: Key Programme Risks (1/3)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62444 |  | Programme | There is a risk that Xoserve's solution delivery is incompatible with the CSS being delivered by Landmark because of poor version control and ambiguity as to which is the live version of the CSS Interface Design Specification that the CSSP have built to, leading to avoidable defects arising in SIT and the subsequent rework required by one or both parties. | Discuss with SI to assess the level of discrepancies and ensure action plan is in place to manage this for future phases/deliverables | This RAID item will be kept open for monitoring during SIT | 30/06/20
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This RAID item will be kept open for monitoring during SIT | 30/06/20
54378 |  | Programme | There is a risk that the logical model contained in Abacus may not fully reflect the CSS processes and interactions with existing service providers because of limited engagement of all Programme stakeholders during the industry wide design phase. Leading to rework of the consequential design activities that have already been completed. | Engage with SI to ensure that Abacus update to fully reflect CSS processes | This RAID item will be kept open for monitoring during SIT. | 30/06/20

## Slide 6: Key Programme Risks (2/3)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This RAID item will be kept open for monitoring until the end of SIT phase 1. | 30/06/20
62377 |  | Data Migration | There is a risk that Xoserve may not be ready for DM non functional testing on time because of lack of clarity of Overall programme plans for environments, testing and data leading to insufficient time allowed for preparation | Xoserve to engage with the SI on this risk | DM non functional testing to be re-planned by Ofgem / SI. Awaiting revised plans | 29/05/20
62376 |  | Data Migration | There is a risk that data provision for UEPT may be delayed because UEPT testing start date has been communicated, but the dates for the production data cut and provision of data to CSP have not, and so Xoserve are unable to plan this activity leading to potential delay in delivery of data if insufficient lead time allowed on programme plan | Xoserve to engage with the SI on this risk | Awaiting revised plans | 30/06/20

## Slide 7: Key Programme Risks (3/3)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
61894 |  | Service Management | There is a risk that the CSS proposed SLAs do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | Discussions are ongoing with DCC as part of the monthly Stakeholder sessions as well as detailed sessions (dates to be agreed with DCC). Current assumption is that Xoserve's existing SLAs will continue to hold until notified otherwise by Ofgem (potentially via REC consultations) | 26/06/20
50199 |  | Programme | There is a risk that CSS Consequential may be unable to meet switching Programme timelines and end up delaying the overall Ofgem Switching Programme because of the fact that Xoserve consequential changes are complex and significant in scale, leading to potential delays to the Industry plan & reputation impact to Xoserve | Continued engagement with SI and other Switching Programme stakeholders to ensure that all inbound dependencies are met within expected timelines. | This continues to be actively monitored and managed - no changes to the status has been identified that could alter the probability or impact. Xoserve's activities continue to be on track to deliver to plan | 30/09/20
62326 |  | Service Management | There is a risk that Service Design and Service Management processes are being tested before the E2E testing of CSS is complete (or even started) because Operational Testing is not being re-planned alongside the re-plan of the UEPT and E2E test phases leading to the possibility of additional test cycles being required at later stages of the programme to cover potential gaps that will be uncovered via market participant testing and as a result additional costs to be borne by Xoserve (and other existing service providers) | Raise with DCC & SI to understand mitigation strategy | DCC have taken away an action to look at the risk. Awaiting update from DCC. | 01/06/20
55572 |  | Network | There is a risk that Market Participants may not have sufficient time to procure and provision IX , if they choose the IX option for comms network connectivity, because of lead times for hardware, software and installation into data centres. Leading to lack of readiness on the part of Market Participants for UEPT in April 2020. Xoserve request that SI / DCC engage with Market participants as early as possible. | Raise with SI / DCC, to request early engagement with Market Participants and review additional MAD milestones as they become available. | Description and probability updated to reflect the re-planning if UEPT. No update received on the mechanism to provide IP addresses to Xoserve or whether any MPs have signed up to use IX to connect to CSS. | 30/06/20

## Slide 8
High Level Plan