## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0664 | With Workgroup | UNC - UIG | Adopted by SSE | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | No implementation specified | Rule & System change | NA | UK Link | Impacts on UK Link to bulk transfer sites from Classes 2 and 3 to Class 4. Invoicing and charging arrangements to be put in place for the CDSP reclassifying sites. Reports required to compare Shipper performance. | NA | Retail & Network | David Addison | Modification looks to create an obligation for Shippers to move Supply Points with low Valid Daily Meter Reading submission performance from Classes 2 and 3 into Class 4 following a consecutive period of poor performance. The CDSP will automatically move any Supply Points note moved by the Shipper in such a scenario (after an allowed period of time). Impacts to UK Link expected. A ROM response has been provided giving an indication of costs and effort. Panel agreed to send 0664 back to WG to address the issues raised during consultation. This includes the issue highlighted with treatment of Shippers which ship to multiple Suppliers. Development at WG is likely to result in a change in the CDSP solution. XRN4990 is still within the early stages of development and is not currently in scope for a release.
Mod 0670R | With Workgroup | UNC - NTSCMF | NTS | Review of the charging methodology to avoid the inefficient bypass of the NTS | Any Modifications as a result of 0670R will be impact assessed and system implications considered. If modification is raised, it is likely to have cross-platform impacts (Gemini and SAP ISU). | [5 empty] | Transmission and Shared Services | Steve Pownall | Review Group requested to conduct an assessment of the charging methodology that is a feature of the overall Gas Transportation Charging framework to avoid the inefficient bypass of the NTS (currently the NTS Optional Commodity charge). The review assesses the objectives, identify requirements, analyse potential options and propose an enduring proportionate solution. Currently 3 ideas for a charging methodology to avoid the inefficient bypass of the NTS. If a modification is raised from the review group, it is likely to have central impacts as any new NTS short haul product will be based on NTS capacity rather than commodity. Modification 0718 has been raised to address the Inefficient Bypass of the NTS with 3 alternates (A / B / C). Modification 0718 A / B /C have been withdrawn as they were based on code which isn't live yet.
Mod 0672 | Approved by Panel Proposes removal from Bubbling Under | UNC - UIG | Scottish Power | Target, Measure and Reporting Product Class 4 Read Performance | No implementation specified | Reporting | NA | UK Link | New reports required to measure performance | NA | Gemini | David Addison | Modification has changed significantly and removed the incentive element. Focus is now on measuring performance. seeks to reduce Unidentified Gas (UIG) volume by providing a target for read submission performance for Product Class 4 sites against overall portfolio. This modification proposes to target and measure performance against an agreed percentage for Energy reconciled after a defined period and provide PAC with a report which will enable them to target shippers whose performance is below the target threshold. The central system impacts are now around creating new reports to measure performance. ROM response provided which details a 4 to 8 week implementation timescale with a upper range cost of £30,000. A Change Proposal has been raised to deliver the reports set out within the Modification (XRN5167). The reports are due to be delivered via DDP and outside of a Major Release. Proposed to be removed from Bubbling Under.
Mod 0674 IGT138 | With Workgroup | UNC - UIG | Scottish Power on behalf of PAC | Performance Assurance Techniques and Controls | No implementation specified | Reporting and Invoicing | NA | NA | New reports are required and the incentive regime will need to be developed with considerations around the invoicing element. | TBC | Gemini | Emma Smith | Modification seeks to provide an effective framework for the governance of industry performance that gives industry participants mutual assurance in the accuracy of settlement volume allocation. Developing through the WG. System impacts currently unknown. Reporting is definitely expected but the way sanctions and incentives are to be applied must be developed and system impacts assessed. Modification still developing.
Mod 0676R | With Workgroup | UNC - WG | Gazprom Energy | Review of Gas Transporter Joint Office Arrangements | Any modifications as a result of 0676R will be impact assessed and any implications considered. | [5 empty] | NA | TBC | To request a review of the Uniform Network Code (UNC) General, Modification Rules and Joint Gas Transporter Governance arrangements for the Joint Office of Gas Transporters. Output for the Review Group is to assess whether the current arrangements are fit for purpose and recommend modifications where appropriate.
Mod 0678 (A-J) Urgent | 0678A Approved for Implementation All others rejected Proposed to be removed from Bubbling Under | UNC - WG | Various proposers | Amendments to Gas Transmission Charging Regime | Oct-20 | Rule and System Change | No | UK Link and Gemini | Impact picked up through the Gemini project team | Oct-20 | Gemini | Steve Pownall | Modification proposal is to amend the Gas Transmission Charging regime in order to better meet the relevant charging objectives and customer/stakeholder provided objectives for Gas Transmission Transportation charges and to deliver compliance with relevant EU codes (notably the EU Tariff Code). There are currently 11 alternates. Modifications look to address the issues highlighted in the Ofgem rejection letter for 0621 and the alternatives. Impacts to be picked up as part of the project team. Panel did not recommend that 0678 or any of the alternates should be implemented. Panel also indicated no clear majority view on the preference around which modification better facilitates the Relevant Objectives. Ofgem approved implementation of 0678A and rejected all others. The central changes will be picked up through the Gemini project team.
Mod 0686 (Urgent) | Awaiting Ofgem decision | UNC - Transmission | Vermilion Energy Ireland Limited | Removal of the NTS Optional Commodity Rate with adequate notice | Oct-20 | Rule and System Change | No | UK Link and Gemini | Impact assessment required | TBC | Transmission and Shared Services | Steve Pownall | Removal of the NTS Optional Commodity Rate1 with adequate notice. “Adequate notice” here means a notice period that is consistent with both the TAR NC and the UNC requirements. As long a notice period as possible is desirable for Users who may be subject to contractual constraints. It is not considered as an alternative to 0678 because the proposer has stated that it will be possible to implement this proposal for effect on the OCR tariff from October 2019 and any one of the 0678 (or alternatives for effect on other tariffs at the same time or any subsequent date. Panel did not recommend the implementation of modification 0686. Ofgem have decided to implement 0678A. This may impact the decision on 0686.
Mod 0687 | Awaiting Ofgem decision | UNC - DWG | Total Gas & Power (on behalf of ICoSS) | Clarification of Supplier of Last Resort Cost Recovery Process | Nov-19 | System Change | No | UK Link | Changes to introduce a new charge type for domestic and non-domestic sites in a SoLR event | Nov-20 | Retail & Network | Ellie Rogers | Modification seeks to provide clarity on how any costs incurred by the Gas Distribution Networks (Transporters) as part of a Last Resort Supply Payment arising from a Supplier of Last Resort event are recovered from Shippers. It proposes the introduction of a new customer charge (the SoLR customer charge) into the Gas Transportation charging statements in order to provide detail on how these costs are allocated. A Change Proposal has been raised XRN4992 has been raised to deliver the system changes for 0687. Panel voted to implement the modification and it is currently with Ofgem for a decision. ChMC approved the enduring solution for XRN4992 to be delivered within November 2020 Release. May ChMC decided to remove XRN4992 from scope of November 2020 release in order to wait for the Ofgem decision.
Mod 0691 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | CDSP to convert Class 3 or 4 meter points to Class 1 when G1.6.15 criteria are met | TBC | Rule, System and Reporting Change | No | UK Link | System changes will be required to identify and move sites to Class 1 when they meet the qualifying criteria. New reports will be required to identify this. | TBC | Data & R&N | Ellie Rogers | This Modification proposes that where the requirement for a Class 2, 3 or 4 meter point to become Class 1 (number of calculations and number of months) has been met, and the Shipper has not taken steps to convert the site to Class 1 within a 20 SPSBD, that the CDSP would take steps to convert the meter point to Class 1. The Modification also proposes new Performance Assurance reports of sites where the CDSP has taken action, over the previous 12 months. A Change Proposal (XRN5038) has been raised to deliver the system changes for 0691. Release type required is currently unknown and depends on the solution option however due to the low volumes involved with this change, we will aim for delivery outside of a Major Release.
Mod 0692 IGT131 | Approved by Panel Appeal has been raised and awaiting Ofgem decision | UNC - DWG | Total Gas & Power (on behalf the UIG Taskforce) | Automatic updates to Meter Read Frequency | Jun-20 | Rule and System Change | No | UK Link | System changes required to update the MRF for sites with an AQ over 293,000kWh or with Smart or Advanced Metering equipment in operation | Nov-20 | Retail & Network | Ellie Rogers | To place an obligation on the CDSP to automatically update the Meter Read Frequency of a Class 3 or 4 Supply Meter Point to Monthly, if: a) The AQ increases to 293,000 kWh or above; or b) The Supply Point Register is updated to show that either Smart or Advanced metering equipment is in place. In addition to undertake a one-off exercise to update the Meter Read Frequency of all current registered Supply Meter Points to Monthly, where they meet at least one of the two criteria above. An appeal was raised regarding Panel\s decision to implement 0692. The associated XRN4941 was removed from November 2020 scope due to the outstanding appeal.
Mod 0693R | With Workgroup | UNC - UIG | Scottish Power (on behalf of the UIG Taskforce) | Treatment of kWh error arising from statutory volume-energy conversion | Any modifications as a result of 0693R will be impact assessed and system implications considered. | [5 empty] | TBC | James Rigby | The Request is to review the treatment of the error in kWh that arises from statutory volume to-energy conversion factors in order to mitigate the impact on gas settlement, reconciliation and Annual Quantities (AQs). WG are discussing the request. Any potential solutions from the review will need to be assessed for system impacts.
Mod 0696 | Awaiting Ofgem decision | UNC - DWG | Gazprom Energy | Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule Change | TBC | Potential system impacts | For the CDSP to correct any capacity charges identified by the Shipper, an offline process would be required. New internal screen expected to set the PMSOQ at the NExA SOQ value provided by the Transporter. | TBC | Retail & Network | Ellie Rogers | To the extent to which a Consumer has entered into a bi-lateral Network Exit Agreement (NExA) with the relevant Transporter then any new or additional capacity charging should only apply from the relevant date set out in the NExA. Modification looks to propose that any new or additional capacity requested under the UNC should only be chargeable from the date set out in the NExA. Modification issued back to WG by Ofgem to consider further questions. Following the addition of a new business rule, a small system change is anticipated to create a new screen to cap the PMSOQ at the NExA SOQ and a Change Proposal would be required to deliver this and to put in the offline process to conduct the capacity correction. A ROM Response for this system change has been provided. May Panel recommended the implementation on 0696. It is now with Ofgem for a decision. A Change Proposal is being raised for the associated system changes and processes.
Mod 0697 IGT135 | With Workgroup | UNC - DWG | Gazprom Energy | Alignment of the UNC TPD Section V5 and the Data Permissions Matrix | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document and process change only | TBC | N/A | Dave Addison /Ellie Rogers | This modification seeks to rationalise UNC TPD Section V5 and remove inconsistency with the Data Permissions Matrix. No system impacts resulting from this change, just documentational only. WG discussions are continuing.
Mod 0699 | Withdrawn Proposed removal from Bubbling Under | UNC - DWG | Scottish Power | Incentivise Read Submission Performance using additional Charges | TBC | Reporting and System Change | N/A | UK Link | New reports required to assess Shipper performance. Arrangements for incentivising performance and invoicing required | N/A | N/A | Dave Addison/ Ellie Rogers | To create a Shipper incentive mechanism, which encourages the submission of valid meter readings into settlement through achievement of UNC targets and obligations. A charge will be levied in each retrospective month, to Shippers where performance has not met a set of pre-determined UNC targets. Modification concept was changed. No longer looking to utilise UIG to incentivise performance. Central system impacts are still expected (minimum to add new Charge Types) but needs to be assessed fully once the modification has developed. Proposer has withdrawn the modification. It may be adopted by a new proposer. Until confirmed, central system impacts are unknown. No new sponsor has taken on this Modification. Proposed removal from Bubbling Under.
Mod 0701 | Awaiting Ofgem decision | UNC - DWG | NGN | Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule and System Change | N/A | UK Link | Changes to UK Link to enhance what is held against NExA sites and add rules for certain data items | TBC | TBC | Ellie Rogers | To improve visibility where a consumer has entered into a bilateral Network Exit Agreement (NExA) with the relevant Transporter, and to link capacity increased with the NExA so that the allowed capacity does not exceed the capacity as agreed in the NExA. System impacts expected to enhance what is currently held in UK Link against NExAs. New rules and logic also to be applied for NExA sites. ROM response has been provided which indicates the central system impacts. This is being reassessed in line with updated business rules. The modification will require delivery within a Major Release. May Panel recommended the implementation on 0701. It is now with Ofgem for a decision. A Change Proposal is being raised for the associated system changes and processes.
Mod 0702 IGT134 | Approved and awaiting implementation Proposed removal from Bubbling Under | UNC - DWG | Gazprom Energy | Introducing ‘Research Body’ as a new User type to the Data Permissions Matrix and UNC TPD Section V5 | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document change only to update the DPM | TBC | N/A | Ellie Rogers | This modification seeks to further realise the benefit of the Data Permissions Matrix reflecting the direction to greater data openness by adding ‘Research Body’ as a new user type to UNC TPD Section V5 and the Data Permissions Matrix. No system impacts expected, only documentational. Modification is out for Consultation. Due to be voted on at May Panel. The associated process has been agreed by the CoMC through the Research Body Framework. Approved by May Panel and currently awaiting implementation. Proposed removal from Bubbling Under.
Mod 0704 | Approved and awaiting implementation Proposed removal from Bubbling Under | UNC - DWG | SGN | Review of Transporter Theft Reporting | TBC | Reporting Change | N/A | No system impacts | No central system impacts as we are expecting to receive the information offline and manual create the report | TBC | N/A | Ellie Rogers | This modification amends the existing Transporter theft of gas reporting requirements following discussions at the 0677R Shipper and Supplier Theft of Gas reporting arrangements review group. No system impacts expected. The current theft reports are expected to be updated to align with the final Transporter reporting obligations agreed within this modification. IGT equivalent has been raised (IGT133). Currently there is a SAP BW report which is generated in order to produce the Transporter theft reports. It is expected that this report will no longer used and instead Transporters will manually send the data to the CDSP to collate manually. Modification approved by May Panel and due to be implemented in June. Proposed to be removed from Bubbling Under.
Mod 0705R | With Workgroup | UNC - WG | National Grid | NTS Capacity Access Review | Any modifications as a result of 0705R will be impact assessed and system implications considered. | [5 empty] | TBC | Steve Pownall | To review the principles and establish long-term strategy for the NTS capacity access regime. Ensuring the regime is appropriate for commercial behaviours experienced today, simplified and adaptable whilst being consistent with relevant obligations. To make recommendations for change and addressing short-term problems in accordance with the long-term ambition. 12 month Review Group has been set up. Central impacts currently unknown and dependent on the Review Group development which will be monitored.
Mod 0708 IGT137 | Approved and awaiting implementation Proposed removal from Bubbling Under | UNC | Northern Gas Networks | Re-ordering of the UNC in advance of Faster Switching | No implementation specified | Administrative Change | N/A | No system impacts | No system impacts as it is a recording of UNC legal text only | N/A | N/A | Dave Addison | This modification proposes to realign the UNC to match the re-ordering that is in the proposed Legal Text developed for the Switching Programme and discussed at the Workgroup for Request 0630R - Review of the consequential changes required in UNC as a result of the Ofgem Switching Programme. May Panel approved implementation. No central system impacts. Proposed removal from Bubbling Under.
Mod 0710 IGT119 | With Workgroup | UNC - DWG | WWU | CDSP provision of Class 1 Read service | 2020 outside of the winter period | Contractual Change | N/A | Minimal system impacts | Minimal system impacts expected as it is a change to the contract only | N/A | Retail & Network | Ellie Rogers / Dave Addison | This modification proposes that the CDSP provides the Class 1 Supply Meter Point read service. It will remove the Transporter obligation to provide a Daily Read service to Shippers for non-telemetered Class 1 Supply Meter Points. This does not affect arrangements for directly connected telemetered Supply Meter Points on DNOs or NTS networks. No system impacts expected as this is a contractual change. Proposer now expects implementation early next year rather than summer of 2020.
Mod 0711 | Awaiting Ofgem decision | UNC - DWG | Gazprom Energy | Update of AUG Table to reflect new EUC bands | Oct-21 | System and Contractual Change | N/A | UK Link and Gemini | System impacts to reflect the EUCs within the UIG Share factors | N/A | Retail & Network and Gemini | Ellie Rogers / Dave Addison | This modification updates the Allocation of Unidentified Gas (AUG) Table set out in UNC TPD Section E Annex E-1 to include the new End User Categories (EUC) brought in by DSC Change Proposal XRN4665 Creation of New End User Categories. Changes to the AUGE and CDSP contract plus system changes to reflect the EUCs within UIG Share factors are required. A ROM response has been provided and indicated the modification must be delivered within a Major Release. A DSC Change Proposal (XRN5093) has been raised to commence the change process. Implementation is required ahead of October 2021. Modification was majority approved by Panel is with Ofgem for a final decision.
Mod 0715S IGT139 | Approved and awaiting implementation Proposed removal from Bubbling Under | UNC - DWG | National Grid | Amendment of the Data Permission Matrix to add Electricity System Operator (ESO) as a new User type | No implementation specified | Permissions Change | N/A | No system impacts | No system impacts, change to UNC and DPM to add ESO as new user type | N/A | N/A | N/A | This Modification Proposal seeks to amend the Data Permission Matrix to add Electricity System Operator (ESO) as a new User type to the Data Permissions Matrix. No system impacts but this will need to be incorporated under Modification 0697. Approved by May Panel and awaiting implementation. No system impacts. Proposed removal from Bubbling Under.
Mod 0716 / 0716A | With Workgroup | UNC - NTSCMF | National Grid | Revision of Overrun Charge Multiplier | Oct-20 | Rule Change and System Change | N/A | UK Link | UK Link parameter change to update the multiplier value within the | Oct-20 | UK Link and Gemini | Steve Pownall | This Modification Proposal seeks to amend the multiplier in the Overrun Charge calculation at NTS Entry and Exit points. This will have system impacts to update the multiplier value in the Overrun Charge. This is expected to be a parameter change only but testing efforts are currently unknown. An alternate has been raised 0716A.
Mod 0719R | With Workgroup | UNC | SGN | Calculation of Energy Value of Gas | Any modifications as a result of 0719R will be impact assessed and system implications considered. | [5 empty] | TBC | Steve Pownall | The Offtake Arrangements Document describes arrangements between Transporters for calculating the energy value of the gas in the network. The main driver for this Review Group is the UNC OAD notice period available to NGG to terminate the provision of the existing service to the GDN, however several developments such as the growth of biomethane injection into distribution networks, a need to review the process for attributing energy values from one offtake to another and questions about whether the UNC obligations sit with the correct party also direct that a review of these arrangements is required. This could have impacts on the CDSP if the preferred solution is for the GDNs to take responsibility and use Xoserve to provide a centralised service for it.
Mod 0720S | With Workgroup | UNC - Transmission | National Grid | Amendments to the Agreed Target Quantity at the Moffatt Interconnection Point | No implementation specified | Rule Change | N/A | No system impacts | Modification seeks to implement a new methodology which does not involve code or central system changes | N/A | N/A | Steve Pownall | This Modification seeks to change the definition of Agreed Target Quantity in the Interconnection Agreement between National Grid Gas plc and GNI (UK) Ltd. No central system changes are anticipated.
Mod 0721 (Urgent) IGT141U | Awaiting Ofgem decision | UNC | Gazprom Energy | Shipper submitted AQ Corrections during COVID-19 | ASAP | Rule Change | N/A | No system impacts | No system changes as it utilises and repurposes existing record and file type | ASAP | N/A | Dave Addison | To authorise the Central Data Services Provider (CDSP) to accept requests from Shippers who submit Annual Quantity (AQ) corrections to amend the AQ in response to the changing consumption of the End User as a result of the COVID-19 crisis, by including this as a reason to do so. A majority vote from Panel was to recommend implementation. Now with Ofgem for a decision.
Mod 0722 (Urgent) IGT142U | Approved and implemented Proposed removal from Bubbling Under | UNC | Gazprom Energy | Allow Users to submit Estimated Meter Reading during COVID-19 | ASAP | Rule Change | N/A | No system impacts | No system changes as it utilises an existing process | ASAP | N/A | Dave Addison | Allow Users to submit Estimated Meter Readings as Actual Meter Readings for Non-Daily Meter sites during COVID-19 “lock-down”. A unanimous vote from Panel was to recommend implementation. Approved by Ofgem and implemented by CDSP. Proposed removal from Bubbling Under.
Mod 0723 (Urgent) IGT143U | Approved and implemented Proposed removal from Bubbling Under | UNC | NGN | Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period | ASAP | Rule Change | N/A | No system impacts | No system changes as it utilises an existing process | ASAP | N/A | Dave Addison | To enable Shipper Users to utilise the central systems Isolation flag, under specific circumstance, without warranted activities taking place, during a COVID-19 period. Allowing for sites where businesses have closed due to COVID-19 to be excluded from the Annual Quantity (AQ) calculation, and therefore from UIG allocation during the relevant period. A unanimous vote from Panel was to recommend implementation. Approved by Ofgem and implemented by CDSP. Proposed removal from Bubbling Under.
Mod 0724 (Urgent) | Approved and implemented Proposed removal from Bubbling Under | UNC | NGN | Amendment to Ratchet charges during COVID-19 period | ASAP | Rule Change | N/A | No system impacts | No system impacts however manual intervention will be required from the CDSP to cancel Ratchet Charges and enable SOQ reduction outside the Capacity window | ASAP | N/A | Dave Addison | To make Ratchet charge changes during COVID-19 period to avoid the application of incentive charges where consumption at specific sites is increased above the agreed booked capacity to support local/national needs during the COVID-19 pandemic. A unanimous vote from Panel was to recommend implementation. Approved by Ofgem and implemented by CDSP. Proposed removal from Bubbling Under.
Mod 0725 (Urgent) IGT144U | Awaiting Ofgem decision | UNC | Gazprom Energy | Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | ASAP | Rule Change | N/A | UK Link impact | Specific system parameters will need to be amended | ASAP | N/A | Dave Addison | To enable consumers to have their site SOQ updated to more accurately reflect their network use during the COVID-19 pandemic and to authorise the CDSP to temporarily accept Shipper User SOQ update requests outside of the normal period. Panel did not recommend implementation. Modification with Ofgem for a decision.
Mod IGT133 | Awaiting IGT Panel decision | IGT - Workstream | BUUK | Transition of IGT Theft Reporting into the IGT UNC | No implementation specified | Reporting Change | N/A | No system impacts | No system impacts. Changes to the IGT theft reporting | N/A | N/A | Ellie Rogers | Introduction of reporting obligations on Pipeline Operators regarding Theft activities which have previously been held under the SPAA (Supply Point Administration Agreement). No system impacts.
SCP 473 | Deferred | SPAA Change Board | SGN | Reconciliation of Shipperless and Unregistered data by the PPMIP | Nov-19 | Permissions Change | N/A | Potential system impacts | The SCP must be assessed to understand if there are any system impacts | TBC | TBC | James Barlow | This SCP seeks to allow the PPMIP to compare Shipperless and Unregistered Sites data provided by the CDSP against the data that they hold in relation to prepayment Supply Points. Where the PPMIP is able to identify the Supplier for the site, this change will require they return certain data back to the CDSP (including the Supplier ID), to enable the CDSP to register the site within central systems. A DSC CP needs to be raised to assess the system impacts. Due to the comments received during the consultation period, the SCP has been deferred.