## Slide 1: Change Management Committee
8th July 2020

## Slide 2: 2. New Change Proposals – Initial Review

## Slide 3: 2. New Change Proposals – Initial Review
Agenda Item | XRN / Title | Voting |  |  |  | DSC Service Area
 |  | Shipper Y/N | DNO Y/N | IGT Y/N | NTS Y/N | 
2.1 | XRN5007 Enhancement to reconciliation process where prevailing volume is zero | X | X |  |  | Service Area 5: Metered Volume and Metered Quantity
2.2 | XRN5188 Interim Data Loads of MAP Id into UK Link | X |  |  |  | Service Area 1: Manage Supply Point Registration
2.3 | XRN5192 CMS Reference Number in Amendment Invoice Supporting Data | X | X |  |  | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices
2.4 | XRN5193 Stop MUR Generation of GT SMPs | X | X |  |  | Service Area 2 – Provide query management Service Lines – SS SA22 05 and SS SA22 06
2.5 | XRN5195 Ceased Responsibility Date Following Shipper Withdrawal (IDL) |  |  | X |  | Service Area 21: Data flows and services to Network Operators
2.6 | XRN5196 Address Amendments Validation | X |  | X |  | Service Area 21: Data flows and services to Network Operators
2.7 | XRN5197 QMP File Validation in CMS – Current Address field | X |  | X |  | Service Area 21: Data flows and services to Network Operators
2.8 | XRN5199 Amendments to V12 of the SDT Service Description Table | N/A | N/A | N/A | N/A | N/A
2.9 | XRN5200 Shipper Pack Transition to Data Discovery Platform | X |  |  |  | Service Area 18: Provision of user reports and information

## Slide 4: 2.1 XRN5007 Enhancement to reconciliation process where prevailing volume is zero
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | Y
National Grid Transmission | 
IGT’s | 
Impacted Parties:- Shippers & DNOs | 
Voting Parties
DSC Service Area: | Service Area 5: Metered Volume and Metered Quantity
Link to Change Proposal | Link to CP
Change Details
Problem Statement
There has been a large increase in the number of MN09 exceptions with no current workaround. The functional process needs to be reviewed and corrected to ensure valid MN09 exceptions no longer occur.
Sponsor Representative | Xoserve
Change Description
To prevent valid MN09 exceptions from occurring and ensure that the resultant billing, and any related downstream processing, is correct.

## Slide 5: 2.2 XRN5188 Interim Data Loads of MAP Id into UK Link
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 
Impacted Parties:- Shippers & MAPs | 
Voting Parties
DSC Service Area: | DSC Service Area 1: Manage Supply Point Registration
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Additional data loads of MAP Id into CDSP systems is required as an interim measure to ensure the integrity of the data item until the enduring solution is in place to maintain this data item (as part of XRN4780-C).
Sponsor Representative | Xoserve
Change Description
XRN4780-B is part of June-2020 Major Release and is looking to load, on mass, MAP Id data into UK Link to support CSS. XRN4780-C is the enduring solution for obtaining MAP Id into CDSP Systems, provided by the Meter Asset Managers (MAMs), and is currently in scope of CSS delivery in June-2021. Multiple data loads of MAP Id into UK Link is needed to ensure the integrity of the data item post June-2020 and up until the enduring solution is implemented. This is due to the existing RGMA rules blanking out MAP Id in specific scenarios and the Shipper not providing the appropriate MAP Id data item within the RGMA files. MAMs will be providing this data item, however this will not be the case until XRN4780-C.

## Slide 6: 2.3 XRN5192 CMS Reference Number in Amendment Invoice Supporting Data
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | Y
National Grid Transmission | 
IGT’s | 
Impacted Parties:- Shipper & DNO | 
Voting Parties
DSC Service Area: | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Supporting information for the Amendment Invoice is made up of 2 files - ASP & AML. Both files contain a field named CMS_REFERENCE_NUMBER which is found in various record types. The purpose of this field is to provide a linkage for the shipper back to contacts raised within CMS, whether the source be Xoserve, Networks, DMSP or Shipper. Unfortunately not all contact types are being captured - in particular RFA & CDQ.
Sponsor Representative | Npower
Change Description
The system needs to be changed so that any reconciliation that is a result of a contact in CMS has the relevant CMS reference number populated in the file. As part of this we need to consider those adjustments that are entered manually but are the result of a CMS contact.

## Slide 7: 2.4 XRN5193 Stop MUR Generation of GT SMPs
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | Y
National Grid Transmission | 
IGT’s | 
Impacted Parties:- Shipper & DNO | 
Voting Parties
DSC Service Area: | Service Area 2 – Provide query management Service Lines – SS SA22 05 and SS SA22 06
Link to Change Proposal | Link to CP
Change Details
Problem Statement
The primary barrier to undertaking this process is the inability for Shippers to operate normal meter reading activities, likewise the DN’s are unable to procure meter readings to satisfy the Must-Read criteria. Therefore, this change is required to overcome this situation and avoid the MUR backlog creations.
Sponsor Representative | Xoserve
Change Description
Change the stakeholder inclusions in the Must Read monthly reporting and the generation of new CMS MUR Contacts in time for 20th Business Day of June (scheduled generation day) Stop the generation of Must Reads on GT SMPs Continue with the generation of Must Reads on IGT SMPs Notification reports going to Shippers to include IGT sites only (this may be a by product of step 1 with no change having to be made) Therefore, we need The duplicate of Notification report but only for IGTs On 20th business day, MUR contact should be generated for IGT site and it should not be generated for GT site.

## Slide 8: 2.5 XRN5195 Ceased Responsibility Date Following Shipper Withdrawal (IDL)
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | Y
Impacted Parties:- IGT | 
Voting Parties
DSC Service Area: | Service Area 21: Data flows and services to Network Operators
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Information provided in IDL is unclear as to when a Shipper has successfully withdrawn from a site and the IGT can stop billing. Some IGTs using the ‘notice of withdrawal’ as the date to stop billing, which is incorrect. In the existing process the shipper withdrawal date is an indication of when the site will withdraw but not the actual withdrawal date. In all instances the withdrawal received date is the only notice IGT’s get in relation to a withdrawal and the withdrawal becoming effective in UK Link. This means that IGT billing ceases earlier than GDN billing. AS a result, some IGT’s use this date to end bill which is incorrect and can result in loss of revenue.
Sponsor Representative | Indigo Pipelines
Change Description
Provide a simple way for IGT’s to identify when a site has truly withdrawn from a shipper in order to cease billing.

## Slide 9: 2.6 XRN5196 Address Amendments Validation
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | X
Impacted Parties:- IGT & Shipper | 
Voting Parties
DSC Service Area: | Service Area 21: Data flows and services to Network Operators
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Once a Shipper has confirmed a site, IGTs are unable to update or challenge updates on the site. For example, for address amendments, a Shipper completed an address amendment over 14 miles away. The first issue is that the address amendment was allowed and secondly the IGT had no way to challenge the update.
Sponsor Representative | BU-UK
Change Description
Provide IGTs with a formal mechanism to challenge address amendments where they believe an update is incorrect.

## Slide 10: 2.7 XRN5197 QMP File Validation in CMS – Current Address field
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | Y
Impacted Parties:- Shipper & IGT | 
Voting Parties
DSC Service Area: | Service Area 21: Data flows and services to Network Operators
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Current validation of the QMP file in CMS causes the system to reject QMP files and so prevents plot to postal address updates. In addition there is no notification sent to IGT’s to inform them that the file has been rejected, it just sits in a pending state which impacts process and adds additional work for IGTs to track the progress of site amendments.
Sponsor Representative | Indigo Pipelines
Change Description
‘Switch off’ the validation of current address in CMS to prevent the rejection of plot to postal address updates.

## Slide 11: 2.8 XRN5199 Amendments to V12 of the SDT Service Description Table
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
Impacted Parties:- All | 
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Sponsor Representative | Xoserve
Reference | Description | Reason for removal
DS-CS SA3 - 17 | Shipper Verification of meter and address details | This was a service that was operated for 3 months post nexus go live (1st June 2017) and the service line is now redundant q
DS-NCS SA23-01 | Arrangements for the CDSP to discuss CSS bid matters with Shipper Users. | No longer relevant
DS-CS SA1 - 46 | Provision of supply point data | This service requirement output is covered under the Data Enquiry service which is provided under reference: SS SA22 63 also information can be found using the Find My Supplier Service
ASGT-NC SA21-02 | Provision of interruption information to UK Transmission | Report no longer required
ASGT-NC SA21-06 | Provision of NDM meter exchange details to UK Transmission. | Report no longer required
Change Description
The DSC Service Description Table has been updated with a number of minor amendments resulting from an internal review The changes are either minor amendments to wording to add clarity or updates to show the correct UNC reference In addition, we propose to remove the following service lines: Service line ASGT-CS SA15-08 has been confirmed as a direct service as opposed to an agency service (as per UNC V 1.15.1 and V2.5.3) therefore we have removed it as a line under the Agency Services tab and have created new line for it under the Direct service Tab so it has now become DS-CS SA15 – 12

## Slide 12: 2.9 XRN5200 Shipper Pack Transition to Data Discovery Platform
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 
Impacted Parties:- Shipper | 
Voting Parties
DSC Service Area: | Service Area 18: Provision of user reports and information
Link to Change Proposal | Link to CP
Change Details
Problem Statement
A series of MI reports collectively known as ‘Shipper Packs’ have been produced by Xoserve for several years, with content ranging from operational / settlement summary reporting through to MPRN level information. The content has evolved over time to include statistical industry performance reporting, such as the suite of reporting produced for / used by the Performance Assurance Committee (PAC). As the Data Discover Platform (DDP) has evolved, its data content has expanded to include several metrics which are reported in both the Shipper Packs and DDP, an example of this is the Performance Assurance Report Register (PARR). The joint production of Shipper Packs and DDP data is resulting in duplicated reporting statistics, which is inefficient and poses potential risk of ‘regret spend’ when changes to either platforms are requested by Shippers to enhance any reporting.
Sponsor Representative | EON
Change Description
This change seeks to establish a framework and timescale for the de-commissioning of Shipper Packs content and ensure all related data and topics are delivered via reporting in DDP. It is expected that this transition away from ‘legacy’ spreadsheet iterations of reporting, will move towards integrated DDP reporting and will begin with the prioritisation of PARR reports already in DDP. The remaining Shipper Pack topics being prioritised in the DDP roadmap deliverables with this change providing an opportunity for Shippers to review Shipper Pack content at topic level and create ‘user stories’ for insertion into future DDP delivery prioritisation discussions and drop/sprint deliverables. Please see the CP for full description

## Slide 13: 3. New Change Proposals – Post Initial Review
None or this meeting

## Slide 14: 4. New Change Proposals – Post Solution Review
None for this meeting

## Slide 15: 5. Implementation Plan
Please see the following slides for an overview of:
Detail Design Changes for approval
    XRN4989 - Online End to End Credit Interest Process
    XRN5116 - Domestic Report - Must Read Prenotification
    XRN4922 CSSC Shipper BRD
    UK Link File Formats CSS Consequential Change
    Settlement Data
    CSSC Code of Connections
    Query APIs Technical Specification Secondary API Error Handling Strategy
Outages
Attached is the full Implementation Plan document.

## Slide 16: Detailed Design Summary of Responses
Chart: 
| XRN4376 Gas Charging Regime – update on UNC0678 | XRN5116 Domestic Report - Must Read Prenotification | XRN4989 Online End to End Credit Interest Process | XRN4922 Shipper BRD | UK Link File Formats CSS | CSSC Code of Connections | Query APIs Technical Specification Secondary API Error Handling Strategy | Adhoc | MiR 8 | CSSC
Approve | 1 | 2
Approve Option 1 | 2
(blank)
Comments only | 2

## Slide 17
Functional Changes |  |  |  |  | 
Change Pack ref: 2601.1 - MT - PO Release: Adhoc Voting: Shippers & NTS | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | Cadent | X |  |  | We have some comments from DNCC (our Control Room) that i am hoping that you can respond to: 1. New charge codes from the change pack – Although the change pack says there’s 4 for the NXC invoice, I think it’s a typo and there’s only 2, RRX and ARX (Transmission Service Revenue Recovery Charge & the ARX is the same but for an adjustment it seems). Can you possibly run through what these charges are for and how we would replicate the calculations? I need someone to explain what the Exit Revenue Recovery Charge is, how it is applied and how we would validate it. I think possibly that it might not apply to DNs based on a small sentence in the Ofgem impact assessment, but I need this confirming, and if so whether it will appear as a record on the invoice or not? 2. There are 2 New Exit Capacity reports in Gemini, can you just run through what these are for and why they are new? Any help with the above would be much appreciated. Note: Xoserve addressed the above comments
XRN4376 - Gas Transmission Charging Regime

## Slide 18
Functional Changes |  |  |  |  | 
Change Pack ref: 2605.1 - MT - JR Release Voting: Shipper | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | SSE | X |  |  | We support implementation of the additional changes in MiR8 (October 2020). Option 1
 | Scottish Power | X |  |  | We support implementation of the additional changes in MiR8 (Option 1)
XRN4989 Online End to End Credit Interest Process

## Slide 19
Functional Changes |  |  |  |  | 
Change Pack ref: 2605.2 - MT - JR Release Voting: Shipper | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | EDF | X |  |  | 
 | Scottish Power | X |  |  | We support the change in reporting frequency from quarterly to monthly for the Must Read Pre Notification
XRN5116 - Domestic Report - Must Read Prenotification

## Slide 20
Functional Changes |  |  |  |  | 
Change Pack ref: 2606.1 - MT - JR Release Voting: Shipper | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | OVO |  |  |  | We have the following comments on the latest version of the BRD: Section 5.2.4 – Please can you clarify your daily update timing/schedule with CSS? Depending on those timings, there may be some risk of misalignment between CSS and UK Link; therefore, potential for failed related activity attempts (e.g. Registration Deactivation Requests, etc). Sections 5.6.9 and 5.6.10 – Due to the dependency of the data within the TMC message to support other ‘Switch’ Business Processes, it is important we receive this information in good time ahead of the switch over. Otherwise, this could impede our ability to process the switch over effectively. We would recommend alternative solutions are found, so that any issues between UK Link and CSS message receipt are resolved ahead of the switch over so that TMC message can then be sent accordingly; to avoid any Participant and Consumer issues. Comment Only
 | EDF |  |  |  | In section 5.6.9 - We agree that an exception should be created in the case of the secured notification being received prior to the pending notification from CSS, however we do mot feel that the TMC should be held back in this scenario. Comment Only
XRN4922 CSSC Shipper BRD

## Slide 21
Functional Changes |  |  |  |  | 
Change Pack ref: 2606.2 - MT - JR Release: CSSC Voting: Shipper | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 |  |  |  |  | No reps received
UK Link File Formats CSS Consequential Change
CSSC Code of Connections
Functional Changes |  |  |  |  | 
Change Pack ref: 2606.3 - MT - JR Release : CSSC Voting: Shippers and DNO | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 |  |  |  |  | No reps received
Query APIs Technical Specification Secondary API Error Handling Strategy
Functional Changes |  |  |  |  | 
Change Pack ref: 2606.4 - MT - JR Release: CSSC Voting: Shipper, DNO & IGT | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 |  |  |  |  | No reps received

## Slide 22
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
 | Internet routing for UKLink | 25/07/2020 | TBC | 26/07/2020 | TBC | This is the cutover of the Internet routing for UKLink, the outage will be on the weekend and the impact will be minor, UKLink will be unable to be accessed and unable to send or receive files to corresponding systems during the maintenance window as the application is switched from our Legacy DC to TCS ECP. | The dates have pushed back a month. 08/07/2020
4550 | Gemini | 05/07/2020 | 03:00 | 05/07/2020 | 17:00 | In order to complete the Gemini Re-Platforming (GRP) project implementation, an extended outage will be required on the Gemini system on 5th July 2020. Provisional timescales for the GRP implementation are as follows: Gemini Maintenance Window: 03.00 to 5.00 Extended outage: 05.00 to 13.00 In the event of a rollback an additional outage will be required from 13.00 to 17.00 If a change is identified to the above timings, a further notification will be issued. The GRP team will work with the National Grid and Xoserve business to ensure appropriate measures are in place to manage all impacts due to the extended outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 11/12/2019
4970 | DCC | TBC | TBC | TBC | TBC | This is the cutover of the production environment for DCC the outage will be on the weekend, the impact to the industry will be minor and that any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application will be unable to send or receive files during the maintenance window as the application is switched from our Legacy DC to TCS ECP. Subject to change due to multiple inflight changes and dependencies on suppliers. | 13/05/2020
4970 | DCC | TBC | TBC | TBC | TBC | This is the outage for DCC DR testing this will be on the weekend, the impact to the industry will be minor and that any application that utilises DCC as a background application will be unable to send or receive files during the maintenance window will DR testing is conduct. Subject to change due to multiple inflight changes at the time, but only by a week. | 13/05/2020
4550 | Gemini | 08/08/2020 | 03:00 | 08/08/2020 | 08:30 | Gemini Disaster Recovery Test 2020 There is a planned Disaster Recovery test on the Gemini system on 8th and 9th August. This is an annual activity in order to confirm the capability to rehost services to an alternative data centre location should there be a catastrophic failure within the primary data centre. There will be an outage on Gemini 8th August 4am-8.30am where the system will be unavailable whilst the test is in progress. During the initial activity we will be recreating the scenario whereby the Gemini system is unusable within the primary data centre and therefore brought up within the secondary data centre. Note that the system will operate normally during times where there is no outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | New Outage 08/07/2020
4550 | Gemini | 09/08/2020 | 03:00 | 09/08/2020 | 08:30 | Gemini Disaster Recovery Test 2020 There is a planned Disaster Recovery test on the Gemini system on 8th and 9th August. (please see details above). During the second activity we will be recreating the scenario whereby the Gemini system is recovered to the primary data centre. There will also be an outage on Gemini 9th August 5am-8.30am where the system will be unavailable whilst the test is in progress. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | New Outage 08/07/2020

## Slide 23: 6. Approval of Change documents
6.1 CCR for XRN5156 COVID19 REC121 Report Amendment
  Voting: DNO
6.2 CCR for XRN5161 COVID 19 UIG_Additional_National_Data_YYYYMM Frequency Change
  Voting: Shipper
6.3 CCR for the Gemini Spring 2020 Release (covers XRN5053 and XRN5054)
  Voting: NTS
6.4 BER for XRN4645A The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows)
  Voting: Shipper

## Slide 24: 7.1 XRN5110 - Nov 20 Release - Status Update
08/07//20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design Design activities completed 19/06/20. On track to complete Design milestone and Stage Gate Track 1 Build activities completed for 2 change there was a delay for XRN4899 due to complete - 03/07/20 SIT preparation complete and activities due to start – 29/06/20. The current plan takes us into contingency but looking to complete within plan Track 2 Build activities started to plan – 22/06/20 SIT preparation activities ongoing SIT activities due to start – 20/07/20 UAT UAT preparation, including Knowledge Transfer sessions, for both tracks on target to start to plan – 29/06/20 Security Working with Information Security to complete change impact assessments Return to Green Approval of the full delivery plan 01/07/20 Change Assurance approval – 03/07/20 |  |  | 
Risks and Issues | Low Risk: Missed requirements and test scenarios due to parallelism of resources between Nov 20 and all other projects. Low Risk: COVID-19 may impact availability of key resources Low Risk: Knowledge Transfer between Build and UAT partners may not be detailed enough and items may be missed |  |  | 
Cost | BER approved - 10/06/20 Full Business Case approved XEC – 23/06/20 Forecast to complete within budget |  |  | 
Resources | SME resources have been allocated for UAT and Tech Ops resource requirements have been requested Return to Green is approval of full delivery plan by 01/07/20 |  |  | 

## Slide 25: XRN5110 - Nov 20 Delivery Timeline

## Slide 26: XRN5110 Nov 20 - Scope
Track 1
  XRN 4931 - Submission of a Space in Mandatory Data on Multiple SPA Files
  XRN 4897 - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event
  XRN 4899 - Treatment of Priority Service Register Data and Contact Details on Change of Supplier Event
2. Track 2
  XRN 4801 - Additional Information in DES
  XRN 4871b - Rachet Regime Changes
  XRN 5014 - Facilitating HyDeploy2 Live Pilot
Descoped changes
  XRN 4941 - MOD 692 – Auto Updates to Read Frequency
  XRN 4992 - Supplier of Last Resort Charge Types
To be delivered by CSSC
  XRN 4780c - MAP ID
XRN5110 November 20 Release consists of 6 changes. Implementation is planned for November 2020

## Slide 27: XRN5110 - Nov 20 Change Assurance Health Check 1
Health Check 2 planned for before UAT 06/07/20 – 17/07/20
Health Check 3 planned for before Implementation 12/10/20 – 23/10/20

## Slide 28: 7.2 XRN4996 - June 20 Release (Core UKLink Changes) - Status Update
8th July 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delivery: Implementation successful and Go Live confirmed on 27th June 5 UK Link XRN’s. Only the file format changes for xrn4850 (CNF/CNC) have been implemented. PIS: Project has entered PIS phase, project team are monitoring first usage and any defects identified CNC file processing enhancement: Workstream established to increase system capacity from 30,000 per day to enable upload of Customer Contact details. We request shippers to liaise with their Customer Advocates prior to uploading customer Contact details into UK Link |  |  | 
Risks and Issues | Risk – There is a risk that Shippers will send in bulk files with customer information through the CNF/CNC files because of the implementation of xrn4850 functionality leading to increased pressure on Xoserve systems. |  |  | 
Cost | Project Delivery costs are in line with approved BER |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases, COVID19 priorities etc.) is ongoing |  |  | 

## Slide 29: xrn4850 New Service SMS/Email Broadcast Notification (as part of the June 20 release)
8th July 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Xrn4850 Delivery: File format changes for xrn4850 (CNF/CNC) have been implemented and PO/EFT channels configured and disabled until Contract Management meeting on 15th July. Contract Management: Paper being submitted to Contract Management for approval on 15th July to seek authority from Data Controllers authorising transfer of data outside of EEA before we can commence the SMS service with Twilio New Service Implementation: Following approval from Contract Management, project team will implement the new service functionality to enable Networks to request Broadcast messages to be sent to end consumers, planned for late July/early August. PIS: PIS for the new service will commence following implementation. The original PIS duration, 3 months, will need to be extended as a result. Cost implications under analysis and will be shared. Change Requests: The CR’s from Market Trials have been captured and impact analysis is underway. Timings and costs will be shared at the next meeting for approval to be implemented during PIS/subsequent release. |  |  | 
Risks and Issues | Issue – The duration of PIS will need to be extended for the new service for xrn4850 due to the delay of this service going live meaning the service is not used within the original PIS window Risk - Contact Management committee do not approve the transfer of data outside of the EEA or there is a delay in them providing approval because of an unacceptable level of risk to them as data controllers leading to a delay to the implementation of the new service functionality and an extension to project timeline and costs |  |  | 
Cost | Project Delivery costs are in line with approved BER |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases, COVID19 priorities etc.) is ongoing |  |  | 

## Slide 30: June 20 PIS Customer Amendment file (CNC) Defect Summary
UK Link June 2020 Major Release was implemented on 27th June 2020
Following implementation, when the Customer Amendment file (CNC) was being sent to UKLink with both a ‘CON’ and ‘BRO’ update sent within the S66 record, one of the records (BRO or CON) was accepted and the other incorrectly rejected with reason code CT00032 error.
This will mean that updates are not being recorded in UKLink and not being issued to the Distribution Networks and IGTs within their daily update files
The code fix was implemented on 4th July 2020, any valid updates processed after this date will be recorded in UKLink
All Shippers who have had their updates rejected prior to the fix being implemented, will be contacted on Tuesday 7th July providing the MPRNs and to discuss options for processing the rejected records.
A lessons learnt will be conducted to identify why this issue occurred and why this was not picked up during testing. Any actions from this will be discussed at Augusts ChMC.

## Slide 31: June 20 XRN4850 Service Update
XRN4850 Delivery: File format changes for xrn4850 (CNF/CNC) have been implemented and PO/EFT channels configured and disabled until Contract Management meeting on 15th July. A paper has been submitted to seek authority from Data Controllers authorising transfer of data outside of EEA before we can commence the SMS service with Twilio.
New Service Implementation: Following approval from Contract Management, project team will implement the new service functionality to enable Networks to request Broadcast messages to be sent to end consumers, planned for July 25th.

## Slide 32: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion
- 19/09/19
Design completion
- 13/12/19
Build & Unit Test completion
- 31/01/20
System Testing completion
- 03/04/20
UAT completion
- 05/06/20
Regression Test completion
- 12/06/20
Market Trials completion
- 19/06/20
Implementation
- 27/06/20
PIS Completion
- 25/09/20 (provisional)

## Slide 33: June 20 Release Summary
June 20 Release consists of 7 changes, Implementation is planned for June 2020:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 – Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs. Descoped at ChMC on 08/01/20
** Descoped at eChMC on 22/11/19
*** Added to scope (revised scope from original)

## Slide 34: 7.3 Minor Release Drop 7 Update

## Slide 35: XRN5152 – Minor Release Drop 7 - Status Update
26/06/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Three changes in XRN5152 Minor Release Drop 7 to be implemented on 04/07/2020: XRN5036 – Updates to Must Read Process (removes AMR and SMART from Must Read contacts - precursor to Nov 2020) XRN4989 – Online Solution for Credit Interest Process (to automatically issue the supporting info through IX) XRN5065 – Addition of Email Address to DES Last Accessed Report (security enhancement) Scope / Implementation Date Approval received from ChMC – 08/04/20 Capture Phase Completed / Impacts Assessments produced / signed-off – 03/04/20 Design Phase Completed / Signed off – 24/04/20 Detailed Implementation planning to commence – w/c 01/06/20 Build Phase Completed – w/c 01/05/20 Change Packs Issued out for review – May 2020 Acceptance Testing and Assurance XRN5036 – complete – 02/06 / XRN4989 complete-02/06 / XRN5065 complete – 02/06 Code Merge complete – 29/05 Regression Testing and Assurance XRN5036 – complete – 25/06 / XRN4989 complete-25/06 / XRN5065 complete – 25/06 Go Live – 04/07 – on track PIS – XRN5036 de-scoped from MiR7 PIS as Must Read Process paused for DNs – once agreed restart date confirmed this first usage will be scoped into future Minor Release |  |  | 
Risks and Issues | There is a risk that Minor Release 7 could have resources issues during Implementation due to Gemini Migration Project going live 5th July 2020 – Xoserve Implementation approach agreed internal |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21. BER for ChMC approval – 13/05/20 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 

## Slide 36: XRN5152 – Minor Release Drop 7 Timelines
Key Dates:
Impact Assessment Completed / signed off – 03/04/20
Design Complete / signed off – 20/04/20
Build Complete MiRD7– 01/05/20
Testing Complete – 02/07/20
Implementation Complete – 04/07/20
PIS Complete – 07/08/20
Dates now baselined following completion of detailed design

## Slide 37: 7.4 UK Link Minor Release 8 – For Approval
July 2020 CHMC

## Slide 38: Minor Release Drop 8 – For Approval
Approval is sought to proceed with the delivery of Minor Release Drop 8.
Drop 8 is scheduled to be implemented in early October 2020
The three changes in scope are:
  XRN5007 - Correction in the reconciliation process when volume is zero.
  XRN5188 - Interim Data Loads of MAP Id into UK Link
  XRN5181 - Rejection of Consumption Adjustments.

## Slide 39: 7.5 UK Link Future Releases Update
July 2020 CHMC

## Slide 40: UKLink Future Releases Update
Agenda:
Future Releases update – For Information
  Future Releases Governance Timeline 2020 – 2021
  Changes in delivery
2021 Major Releases – For Information:
  June 2021 – proposed scope
  November 2021 – proposed scope
August ChMC content.
Glossary

## Slide 41: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Please note that this slide includes potential activity within UK Link over the next 24 months
Assumes 3x Minor Releases required prior to May 2021
BER Approval
10/04/18
Potential Activity
On track
At risk
Key:
Complete
BER Approved Jun-20
CSSC activity
CSSC
Scope approved – Feb ChMC
EQR Approved – March ChMC
Scope Approved – April ChMC
Potential Activity
MiR 9
MiR 8
Retro
Nov 20
June 20
MiR 7
Potential Activity
Potential Activity
Scope Approval – October ChMC
Scope Approval – Jan ChMC
MiR 10
Potential Activity
BER Approval – May ChMC
Scope Approval – July ChMC
June 21
Nov 21
Potential Activity
Potential Activity
Scope Approval – Aug 20 ChMC
Scope Approval – December 20 ChMC
EQR Approval – Aug ChMC

## Slide 42: Change Index – UK Link Allocated Change
Confirmed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DNO
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DNO
 | 5036 | Updates to must read process | In Delivery | Nov 2020 | Small | DNO
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4992 | Supplier of last resort charge type | In Delivery | Nov 2020 | Medium | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4780c | MAP ID part C (CSSC) | In Delivery | Nov 2020 | Large | CSS
 | 4941 | Auto updates to meter read frequency | In Delivery | Nov 2020 | Large | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DNO
MiR D7 Jul-20 | 5036 | Updates to Must Read Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 4989 | Online Solution for Credit Interest Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 5065 | Addition of E-mail Address to DES Last Accessed Report | In Delivery | MiR Drop 7 | Medium | Minor Release

## Slide 43: 2021 UK Link Future Releases
Proposed Release | XRN | Candidate Change Title | Comments | Current Status | Complexity | Points | Finance
Jun-21 | 4941 | MOD0692 - Auto updates to meter read frequency | Descoped from Nov 20. Dependent on Ofgem decision | Design | Large | 13 | Shipper
 | 4992 | MOD0687 – Creation of new charge to recover last resort supply payments | Descoped from Nov 20. Under appeal | Design | Large | 13 | Shipper
 | 5093 | MOD0711 – Update of AUG Table to reflect new EUC bands | HLSOs in review | In Capture | X-Large | 21 | Shipper
 | 5038 | MOD0691 – Class 2,3 or 4 meter points to Class 1 when G1.6.15 criteria are met | Depending on solution option chosen this change could be delivered via a Minor Release | In Capture | Tbd. | Tbd | Shipper
 | 5142 | New allowable values for DCC Service Flag in DXI File from DCC | Related to a SEC change | In Capture | Tbd | Tbd | DN
Nov 21 | 4990 | MOD0664 – Transfer of sites with low read submission performance |  | In Capture | Tbd. | Tbd | Shipper
 | 5063 | MOD0719R – Flow Weighted Average CV (FWACV) |  | In Capture | XXXL | Tbd | DN
 | 5186 | Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  | In Capture | Tbd. | Tbd | DN
 | 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes |  | In Capture | Tbd. | Tbd | Shipper
 | 5091 | Deferral of creation of Class change reads at transfer of ownership |  | In Capture | Tbd. | Tbd | Shipper
XRN5063 – Flow Weighted Average CV change is likely to be very complex and may not be delivered by a UK Link Major Release.
Service sustaining activity may be considered for inclusion in future releases.

## Slide 44: Available Points A
Year | 2020 |  |  |  |  |  |  | 2021 |  |  |  |  | 
Month | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Phase | Start-Up |  | Init | Design |  |  | Build / Test / Implement |  |  |  |  |  | 
Points Available | 120 |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 100 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 75 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 34 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 21 |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 5 |  |  |  |  |  |  | 
Change Packs issued for review
Change Packs issued
Implementation
Scope Approval

## Slide 45: Available Points B
Year | 2020 |  |  |  |  |  |  | 2021 |  |  |  |  | 
Month | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Phase | Start-Up |  | Init | Design |  |  | Build / Test / Implement |  |  |  |  |  | 
Points Available | 120 |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 90 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 60 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 30 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 15 |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  |  |  |  |  |  | 
Change Packs issued for review
Change Packs issued
Implementation
Scope Approval

## Slide 46: August ChMC
June 21 Major Release:
  Seek scope approval
  Present High Level Plan (up to the end of Design)
  Seek EQR approval for project costs up to end of Design Phase.
Minor Release Drop 8
  Present plan
  Confirm implementation date and PIS.
November 21 Major Release:
  Update on progress through Capture
  If applicable, discuss risks.
Service Sustaining Schedule:
  Activities to sustain UK Link service – overview.

## Slide 47: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal
HLSO(s) | High Level Solution Option(s)

## Slide 48: 7.6 UK Link POAP

## Slide 49: 7.7 Data Discovery Platform
Verbal Update

## Slide 50: 8. CSSC Programme Dashboard
Verbal Update

## Slide 51: 9.1 Bubbling Under Report

## Slide 52: 9.2 Gemini Horizon Planning

## Slide 53: 10.1 Finance and General Change Budget Update

## Slide 54: 10.2 BP21 DSC Change budget
BP 21/22 |  |  |  |  |  |  |  |  | 
Change budget | 1,850,000 |  |  |  |  |  |  |  | 
Contingency funding | 800,000 |  |  |  |  |  |  |  | 
PAC funding | 100,000 |  |  |  |  |  |  |  | 
Xoserve change funding | 250,000 |  |  |  |  |  |  |  | 
 | Shipper | DN | IGT | NTS |  | Shipper | DN | IGT | NTS
Funding split of change budget | 1,265,400 | 370,000 | 185,000 | 29,600 |  | 68.4% | 20% | 10% | 1.60%
Split of Contingency | 547,200 | 160,000 | 80,000 | 12,800 |  | 68.4% | 20% | 10% | 1.60%
PAC Funding | 68,400 | 20,000 | 10,000 | 1,600 |  | 68.4% | 20% | 10% | 1.60%
Split of Xoserve change fund | 171,000 | 50,000 | 25,000 | 4,000 |  | 68.4% | 20% | 10% | 1.60%
total | 2,052,000 | 600,000 | 300,000 | 48,000 |  |  |  |  | 
Contingency funding will cover any MT costs as we are not expecting MT |  |  |  |  |  |  |  |  | 
To Note |  |  |  |  |  |  |  |  | 
FWACV MOD - highly complex change |  |  |  |  |  |  |  |  | 
No funding considered for decarbonisation based change |  |  |  |  |  |  |  |  | 

## Slide 55: 11. AOB

## Slide 56: 11.1 Xoserve IX Refresh
Customer Update
July 2020

## Slide 57: IX Refresh Customer Update
90% of IX customers are now able to continue with their IX migration activities, following the recent update to government guidance on COVID-19
The project has completed it’s re-plan based on customer readiness. The project is forecasted to complete in February 2021
In alignment, the IX legacy support with Vodafone has been extended to February to ensure all customers remain on a fully supported solution as we continue with migrations
The project would like to request customer support in ensuring that we migrate you as quickly and smoothly as possible onto your new IX Gamma network
  The migration onto the new IX Network will allow a reduction in IX pricing
  Your IX equipment will be fully refreshed onto new hardware
  There is a risk that we will not be able to extend the legacy support past February 2021
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com

## Slide 59: 11.2 Update to Budget & Charging Methodology
Waiting update from the Cost Allocation Review due 6th/7th July before attaching the amended version