## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0664 IGT145 | Out for Consultation | UNC - UIG | Adopted by SSE | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | No implementation specified | Rule & System change | NA | UK Link | UK Link impacts to identify eligible sites and maintain performance parameters. Enhancements to processes to create a lockout period. Reports required to compare Shipper performance. | NA | UK Link | David Addison | Modification looks to create an obligation for Shippers to move Supply Points with low Valid Daily Meter Reading submission performance from Classes 2 and 3 into Class 4 following a consecutive period of poor performance. The CDSP will automatically move any Supply Points note moved by the Shipper in such a scenario (after an allowed period of time). Impacts to UK Link expected. Panel agreed to send 0664 back to WG to address the issues raised during consultation. WG have worked through the issues and a Variation Request has been drafted to include an additional business rule which accounts for a change in Supplier scenario. This requires a tweak in the CDSP solution but should be covered under the cost provided within the original ROM. XRN4990 is still within the early stages of development and is not currently in scope for a release. Panel issued the Request back to WG to back the report clearer. Variation Request at Panel unanimously accepted, 664V is now out for consultation closing 12th Oct.
Mod 0674 IGT138 | With Workgroup | UNC - UIG | Scottish Power on behalf of PAC | Performance Assurance Techniques and Controls | No implementation specified | Reporting and Invoicing | NA | NA | New reports are required and the incentive regime will need to be developed with considerations around the invoicing element. | TBC | Gemini | Emma Smith | Modification seeks to provide an effective framework for the governance of industry performance that gives industry participants mutual assurance in the accuracy of settlement volume allocation. Developing through the WG. System impacts currently unknown. Reporting is definitely expected but the way sanctions and incentives are to be applied must be developed and system impacts assessed. Modification still developing. September Panel agreed to send back to WG, returning to Panel in Jan 20.
Mod 0676R | With Workgroup | UNC - WG | Gazprom Energy | Review of Gas Transporter Joint Office Arrangements | Any modifications as a result of 0676R will be impact assessed and any implications considered. | [5 empty] | NA | TBC | To request a review of the Uniform Network Code (UNC) General, Modification Rules and Joint Gas Transporter Governance arrangements for the Joint Office of Gas Transporters. Output for the Review Group is to assess whether the current arrangements are fit for purpose and recommend modifications where appropriate. Review group still developing.
Mod 0686 (Urgent) | Awaiting Ofgem decision | UNC - Transmission | Vermilion Energy Ireland Limited | Removal of the NTS Optional Commodity Rate with adequate notice | Oct-20 | Rule and System Change | No | UK Link and Gemini | Impact assessment required | TBC | Gemini | Steve Pownall | Removal of the NTS Optional Commodity Rate1 with adequate notice. “Adequate notice” here means a notice period that is consistent with both the TAR NC and the UNC requirements. As long a notice period as possible is desirable for Users who may be subject to contractual constraints. It is not considered as an alternative to 0678 because the proposer has stated that it will be possible to implement this proposal for effect on the OCR tariff from October 2019 and any one of the 0678 (or alternatives for effect on other tariffs at the same time or any subsequent date. Panel did not recommend the implementation of modification 0686. Ofgem have decided to implement 0678A. This may impact the decision on 0686.
Mod 0687 | Awaiting Ofgem decision | UNC - DWG | Total Gas & Power (on behalf of ICoSS) | Clarification of Supplier of Last Resort Cost Recovery Process | Nov-19 | System Change | No | UK Link | Changes to introduce a new charge type for domestic and non-domestic sites in a SoLR event | Nov-20 | UK Link | Ellie Rogers | Modification seeks to provide clarity on how any costs incurred by the Gas Distribution Networks (Transporters) as part of a Last Resort Supply Payment arising from a Supplier of Last Resort event are recovered from Shippers. It proposes the introduction of a new customer charge (the SoLR customer charge) into the Gas Transportation charging statements in order to provide detail on how these costs are allocated. A Change Proposal has been raised XRN4992 has been raised to deliver the system changes for 0687. Panel voted to implement the modification and it is currently with Ofgem for a decision. ChMC approved the enduring solution for XRN4992 to be delivered within November 2020 Release. May ChMC decided to remove XRN4992 from scope of November 2020 release in order to wait for the Ofgem decision. XRN4992 is now in scope for June 2021 Major Release. An Ofgem decision is required by latest October for the ChMC to decide whether to progress in June 2021 or de-scope. This was noted by Panel and Ofgem.
Mod 0691 IGT131 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | CDSP to convert Class 3 or 4 meter points to Class 1 when G1.6.15 criteria are met | TBC | Rule, System and Reporting Change | No | UK Link | System changes will be required to identify and move sites to Class 1 when they meet the qualifying criteria. New reports will be required to identify this. | TBC | UK Link and Data | Ellie Rogers | This Modification proposes that where the requirement for a Class 2, 3 or 4 meter point to become Class 1 (number of calculations and number of months) has been met, and the Shipper has not taken steps to convert the site to Class 1 within a 20 SPSBD, that the CDSP would take steps to convert the meter point to Class 1. The Modification also proposes new Performance Assurance reports of sites where the CDSP has taken action, over the previous 12 months. A Change Proposal (XRN5038) has been raised to deliver the system changes for 0691. Release type required is currently unknown and depends on the solution option however due to the low volumes involved with this change, we will aim for delivery outside of a Major Release. August Panel determined that there were new issues requiring a view from Workgroup. Workgroup 0691S to provide a report to the October 20 Panel.
Mod 0692 IGT131 | Approved by Panel Appeal has been raised and awaiting Ofgem decision | UNC - DWG | Total Gas & Power (on behalf the UIG Taskforce) | Automatic updates to Meter Read Frequency | Jun-20 | Rule and System Change | No | UK Link | System changes required to update the MRF for sites with an AQ over 293,000kWh or with Smart or Advanced Metering equipment in operation | Nov-20 | UK Link | Ellie Rogers | To place an obligation on the CDSP to automatically update the Meter Read Frequency of a Class 3 or 4 Supply Meter Point to Monthly, if: a) The AQ increases to 293,000 kWh or above; or b) The Supply Point Register is updated to show that either Smart or Advanced metering equipment is in place. In addition to undertake a one-off exercise to update the Meter Read Frequency of all current registered Supply Meter Points to Monthly, where they meet at least one of the two criteria above. An appeal was raised regarding Panel\s decision to implement 0692. The associated XRN4941 was removed from November 2020 scope due to the outstanding appeal. The modification has been re-scoped into June 2021 Major Release. An Ofgem decision is required by latest October for the ChMC to decide whether to progress in June 2021 or de-scope. This was noted by Panel and Ofgem.
Mod 0693R | With Workgroup | UNC - UIG | Scottish Power (on behalf of the UIG Taskforce) | Treatment of kWh error arising from statutory volume-energy conversion | Any modifications as a result of 0693R will be impact assessed and system implications considered. | [5 empty] | TBC | James Rigby | The Request is to review the treatment of the error in kWh that arises from statutory volume to-energy conversion factors in order to mitigate the impact on gas settlement, reconciliation and Annual Quantities (AQs). WG are discussing the request. Any potential solutions from the review will need to be assessed for system impacts. Review Group is still developing options.
Mod 0696 | Awaiting Ofgem decision | UNC - DWG | Gazprom Energy | Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule Change | TBC | Potential system impacts | For the CDSP to correct any capacity charges identified by the Shipper, an offline process would be required. New internal screen expected to set the PMSOQ at the NExA SOQ value provided by the Transporter. | TBC | UK Link | Ellie Rogers | To the extent to which a Consumer has entered into a bi-lateral Network Exit Agreement (NExA) with the relevant Transporter then any new or additional capacity charging should only apply from the relevant date set out in the NExA. Modification looks to propose that any new or additional capacity requested under the UNC should only be chargeable from the date set out in the NExA. Modification issued back to WG by Ofgem to consider further questions. Following the addition of a new business rule, a small system change is anticipated to create a new screen to cap the PMSOQ at the NExA SOQ and a Change Proposal would be required to deliver this and to put in the offline process to conduct the capacity correction. A ROM Response for this system change has been provided. May Panel recommended the implementation on 0696. It is now with Ofgem for a decision. A Change Proposal has been raised for the associated system changes and processes (XRN5187).
Mod 0697 IGT135 | Approved for implementation (subject to no appeals) | UNC - DWG | Gazprom Energy | Alignment of the UNC TPD Section V5 and the Data Permissions Matrix | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document and process change only | TBC | N/A | Dave Addison /Ellie Rogers | This modification seeks to rationalise UNC TPD Section V5 and remove inconsistency with the Data Permissions Matrix. No system impacts resulting from this change, just documentational only. Modification approved for implementation at September Panel, subject to no appeals following 16 business days.
Mod 0701 | Awaiting Ofgem decision | UNC - DWG | NGN | Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule and System Change | N/A | UK Link | Changes to UK Link to enhance what is held against NExA sites and add rules for certain data items | TBC | TBC | Ellie Rogers | To improve visibility where a consumer has entered into a bilateral Network Exit Agreement (NExA) with the relevant Transporter, and to link capacity increased with the NExA so that the allowed capacity does not exceed the capacity as agreed in the NExA. System impacts expected to enhance what is currently held in UK Link against NExAs. New rules and logic also to be applied for NExA sites. ROM response has been provided which indicates the central system impacts. This is being reassessed in line with updated business rules. The modification will require delivery within a Major Release. May Panel recommended the implementation on 0701. It is now with Ofgem for a decision. A Change Proposal has been raised for the associated system changes and processes (XRN5186).
Mod 0705R | With Workgroup | UNC - WG | National Grid | NTS Capacity Access Review | Any modifications as a result of 0705R will be impact assessed and system implications considered. | [5 empty] | TBC | Steve Pownall | To review the principles and establish long-term strategy for the NTS capacity access regime. Ensuring the regime is appropriate for commercial behaviours experienced today, simplified and adaptable whilst being consistent with relevant obligations. To make recommendations for change and addressing short-term problems in accordance with the long-term ambition. 12 month Review Group has been set up. Central impacts currently unknown and dependent on the Review Group development which will be monitored.
Mod 0710 IGT119 | Out for Consultation | UNC - DWG | WWU | CDSP provision of Class 1 Read service | 2021 outside of the winter period | Contractual Change | N/A | Minimal system impacts | Minimal system impacts expected as it is predominantly a contractual change and only amendments to invoicing for the service | N/A | UK Link | Ellie Rogers / Dave Addison | This modification proposes that the CDSP provides the Class 1 Supply Meter Point read service. It will remove the Transporter obligation to provide a Daily Read service to Shippers for non-telemetered Class 1 Supply Meter Points. This does not affect arrangements for directly connected telemetered Supply Meter Points on DNOs or NTS networks. Minimal system impacts expected as this is predominantly a contractual change. Implementation is anticipated for summer 2021. A Change Proposal has been raised (XRN5218) to manage the process changes and the invoicing amendments. WG report has been finalised and is being issued to Panel in September. Issued to Consultation closing 8th October 2020.
Mod 0716 / 0716A | Modification 0716 Approved Proposes removal from Bubbling Under | UNC - NTSCMF | National Grid | Revision of Overrun Charge Multiplier | Oct-20 | Rule Change and System Change | N/A | UK Link | UK Link parameter change to update the multiplier value | Oct-20 | UK Link and Gemini | Steve Pownall | This Modification Proposal seeks to amend the multiplier in the Overrun Charge calculation at NTS Entry and Exit points. This will have system impacts to update the multiplier value in the Overrun Charge. This is expected to be a parameter change only but testing efforts are currently unknown. An alternate has been raised 0716A. From a system perspective, a parameter change would be required for either Modification and testing (the level at which is to be confirmed and could impact the way it is delivered by the CDSP). This would be picked up by the Gemini Projects team. July Panel recommended the implementation of both 0716 and 0716A. Ofgem published decision to approve Modification 0716. The associated changes to central systems will be picked up by the Gemini team.
Mod 0719R | Workgroup Closed Proposed removal from Bubbling Under | UNC | SGN | Calculation of Energy Value of Gas | Any modifications as a result of 0719R will be impact assessed and system implications considered. | [5 empty] | TBC | Steve Pownall | The Offtake Arrangements Document describes arrangements between Transporters for calculating the energy value of the gas in the network. The main driver for this Review Group is the UNC OAD notice period available to NGG to terminate the provision of the existing service to the GDN, however several developments such as the growth of biomethane injection into distribution networks, a need to review the process for attributing energy values from one offtake to another and questions about whether the UNC obligations sit with the correct party also direct that a review of these arrangements is required. This could have impacts on the CDSP if the preferred solution is for the GDNs to take responsibility and use Xoserve to provide a centralised service for it. Review Group closed. A change is being picked up with the CDSP and will be taken through the process.
Mod 0720S | Approved for implementation (subject to no appeals) Proposed removal from Bubbling Under | UNC - Transmission | National Grid | Amendments to the Agreed Target Quantity at the Moffatt Interconnection Point | No implementation specified | Rule Change | N/A | No system impacts | Modification seeks to implement a new methodology which does not involve code or central system changes | N/A | N/A | Steve Pownall | This Modification seeks to change the definition of Agreed Target Quantity in the Interconnection Agreement between National Grid Gas plc and GNI (UK) Ltd. No central system changes are anticipated. September Panel voted to implement, subjest to no appeals in the next 16 business days.
Mod 0727 (Urgent) | Awaiting Ofgem decision | UNC | Benoit Enault, Storengy UK Ltd | Increasing the Storage Transmission Capacity Charge Discount to 80% | Oct-20 | Rule Change | N/A | Potential system impacts | Potential Gemini and UK Link invoicing changes | Oct-20 | Gemini | Steve Pownall | The revised NTS Charging Methodology (in place from 01 October 2020) includes a discount for capacity purchased at storage sites of 50%. This Modification seeks to include a higher discount rate of 80% for such capacity, to be introduced on 01 October 2020 or as soon as possible thereafter. Central systems might be impacted. This should be picked up by the Gemini project team. With Ofgem for a decision.
Mod 0728 A/B/C/D (Urgent) | Awaiting Ofgem decision | UNC | Multiple | Introduction of a Conditional Discount for Avoiding Inefficient Bypass of the NTS | Oct-20 | Rule Change | N/A | UK Link and Gemini | Impacts expected on Gemini and UK Link invoicing systems | Oct-20 | Gemini | Steve Pownall | The revised NTS Charging Methodology (in place from 01 October 2020) does not incorporate a mechanism to dis-incentivise inefficient bypass of the NTS. This Modification seeks to introduce a new Conditional Discount to the Charging Framework so that a product to manage potential inefficient bypass will be in place as soon as possible on or after the changes introduced from UNC0678A, which become effective from 01 October 2020. Impacts are anticipated on central systems. This should be picked up by the Gemini project team. With Ofgem for a decision.
Mod 0729 | Awaiting Ofgem decision | UNC | National Grid | Applying a discount to the Revenue Recovery Charge at Storage Points | Oct-20 | Rule Change | N/A | Potential system impacts | TBC | Oct-20 | Gemini | Steve Pownall | The revised NTS Charging Methodology (in place from 01 October 2020) includes a discount for capacity purchased at storage sites of 50%, however, no such discount is applied to the application of the Revenue Recovery Charge (RRC). This Modification seeks to reflect the Storage Discount in a discount to the RRC rate to be applied to capacity held at storage sites. It is proposed that this change is introduced on 01 October 2020 or as soon as possible thereafter. Modification due to go to Panel in July. Central system impacts are anticipated which will be assessed by the Gemini project team. Ofgem rejected urgent status. Panel assigned the Modification to WG. August Panel voted 720S issued to consultation and coming back to September's meeting for a decision. September Panel could not agree on a unanimous decision to implement, and has been issued to Ofgem with a recommendation not to implement.
Mod 0730 | With Workgroup | UNC - DWG | Gazprom Energy | COVID-19 Capacity Retention Process | No implementation specified | Rule Change | Y | None anticipated | No central system impacts as we are anticipating to manage this via manual processes. | N/A | N/A | Dave Addison /Ellie Rogers | This modification seeks to allow sites (supply points) isolated in accordance with modification 0723 (Urgent) - Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period to be subject to a rebate of 50% of their LDZ Capacity Costs. Ofgem rejected urgent status and the modification has been sent to WG for development. Central system impacts are not anticipated as it is expected this process will be offline and manual but a Change Proposal may be required to put these in place. We expect implementation to be relatively quick following the Modification decision.
Mod 0731 | Issued to Workgroup | UNC | Gazprom Energy | Introduction of an Annual Modification Panel Report | No implementation specified | Rule Change | N/A | None anticipated | No central system impacts anticipated | N/A | N/A | Ellie Rogers | The Modification Panel is the body constituted under the Uniform Network Code to oversee the Modification process as set out in the Uniform Network Code General Terms and Modification Rules. With the role of an independent Chair for the Modification Panel and UNCC there is an opportunity to leverage the knowledge and experience available, to facilitate continuous improvement and to ensure the efficient and effective operation of the Modification Panel and UNCC. No central system or process impacts anticipated.
Mod 0734 | With Workgroup | UNC | Gazprom Energy | Reporting Valid Confirmed Theft of Gas into Central Systems | No implementation specified | Rule and System Change | N/A | UK Link | Impacts to CMS are anticipated but dependent on the solution | TBC | UK Link | Ellie Rogers / Dave Addison | This Modification seeks to place obligations on Shipper parties to ensure that valid confirmed theft of gas data received from Suppliers, such as consumption volumes, are appropriately entered into central systems for the purposes of Settlement. It also seeks to ensure corrections to Annual Quantities (AQ) that are required as a result of theft of gas are undertaken as required. Modification has been issued to WG for development. A Change Proposal is being raised for the October ChMC to deliver the associated solution.
Mod 0735 | Issued to Workgroup | UNC | National Grid NTS | UNC Changes as a consequence of the absence of trade agreement/s between the United Kingdom and the European Union (‘no deal’) | No implementation specified | Reference within UNC Change | N/A | None anticipated | No central system impacts anticipated | TBC | N/A | N/A | A number of minor changes to the Uniform Network Code (UNC) are required as a consequence of the end of the implementation period following the United Kingdom (UK) withdrawal from the European Union (EU). In principle, these changes modify existing references to EU regulations with reference to UK amendment regulations and where appropriate remove references to EU entities.
Mod 0736/0736A | Issued to Workgroup | UNC | Cadent (0736) Gazprom (0736A) | Clarificatory change to the AQ amendment process within TPD G2.3 | No implementation specified | Rule Change | N/A | UK Link | A change will be required to create and maintain a User Relationship Table | TBC | UK Link | Ellie Rogers/ Dave Addison | This Modification proposes to make a change to the AQ amendment process outlined in the Uniform Network Code Transportation Principles Document Section G 2.3 (UNC TPD G2.3) in order to clarify the circumstances in which such amendments can be made. 0736A applies these clarifications from the 1 April 2020. Impacts on the CDSP are anticipated and a CP is being raised. Initial option is through a manual solution rather than through the system.
SCP 450 | Deferred | SPAA Change Board | British Gas | Addition of Pressure, Temperature and Compressibility (“PTC”) to Market Doman Data (MDD) General | No implementation specified | Rule and System Change | N/A | Potential system impacts | Potential minimal allowable data item changes required to remove the incorrect allowable value | TBC | TBC | James Barlow | Within the MDD Converter Product Table there is value (“PTC”) which is being populated. This value is not listed within MDD General under A0036 – Conversion Basis Codes. This SCP seeks to add the value “PTC” to MDD General v18.8 and all future MDD release. A minor system change may be required if the value is removed but this is to be assessed once the outcome of the SCP is known.
SCP 473 | Re-issued to Impact Assessment | SPAA Change Board | SGN | Reconciliation of Shipperless and Unregistered data by the PPMIP | Nov-19 | Permissions Change | N/A | Potential system impacts | The SCP must be assessed to understand if there are any system impacts | TBC | TBC | James Barlow | This SCP seeks to allow the PPMIP to compare Shipperless and Unregistered Sites data provided by the CDSP against the data that they hold in relation to prepayment Supply Points. Where the PPMIP is able to identify the Supplier for the site, this change will require they return certain data back to the CDSP (including the Supplier ID), to enable the CDSP to register the site within central systems. A DSC CP needs to be raised to assess the system impacts.
SCP 496 | Re-issued to Impact Assessment | SPAA Change Board | Shell Energy on behalf of the CDSP | MAM to CDSP Update of MAP ID and MTD | No implementation specified | Rule and System Change | N/A | Potential system impacts | UK Link changes required | TBC | Retail and Network | James Barlow | The Central Data Service Provider (CDSP) is required to provide the Meter Asset Provider Identity (MAP Id) to the Central Switching System (CSS) via the Gas Retail Data Agent (GRDA). In order to do so the Meter Asset Manager must provide updates to the Meter Technical Details or MAP Id directly to the CDSP to supplement information received from Shippers. A Change Proposal has been raised (XRN4780-C) to cover this change.