## IP - For Approval - Design
UK Link Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4897/4899 | N/A | UK Link Manual | 2654.3 – KL – PO | 2020-08-17 | 2020-09-01 | 2020-09-08 | X | X |  | X |  | TBC | 2020-09-09 | 2020-11-01
N/A | N/A | UK Link File Formats CSS Consequential Change | 2655.1 - KL - PO | 2020-08-17 | 2020-09-01 | 2020-09-08 | X |  |  |  |  | TBC | 2020-09-09 | CSSC
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Implementation Plan - Approved last meeting
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4989 Part B | N/A | Online End to End Credit Interest Process - IIS File Format Change | 2634.2 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X |  |  |  |  | 2647 – KL – PO | 2020-08-12 | Minor Enhancement Potencial Oct 20 | We received three approval responses
5047 | N/A | Seasonal Normal Review Implementation in SAP ISU | 2634.3 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X |  |  |  |  | 2647 – KL – PO | 2020-08-12 | Adhoc TBC | We received three approval responses
N/A | N/A | UK Link File Formats CSS Consequential Change | 2635.1 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X |  |  |  |  | 2647 – KL – PO | 2020-08-12 | CSSC | No reps received
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
N/A | N/A | Change Management meeting, UK Link Release Dates and Non Business Days | 2634.1 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X | X | X | X |  | 2647 – KL – PO | 2020-08-12 | 2021 | We received three approval responses

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
| EFT | 2020-10-09 | 5:00 | 2020-10-11 | 7:00 | As part of our Xoserve Annual Programme of Resilience and Disaster Recovery (DR) testing , Xoserve will be managing and conducting an end-to-end 2020 Enhanced File Transfer (EFT) DR test to prove and confirm the procedures, resilience and capability of the newly hosted EFT services at our new Data Centre’s. The activity will be carried out over three days from October 9th, 10th and 11th 2020 during the daily UK-LINK Maintenance window between 05:00 to 07:00 UK BST. Please be aware that the confirmed EFT DR Contingency Dates have been scheduled to be carried out on the following week over three days during the 05:00 to 07:00 UK BST UK-LINK Maintenance window on October 16th, 17th and 18th 2020. Any Customer IX files that would be processed by EFT during this window will remain safely in your respective IX Folders, once EFT is back online, all IX file transfers will be synced and issued. | 2020-08-12
| SD+ | 2020-09-26 | TBC | 2020-09-27 | TBC | This is the implementation Service Now (SNOW) and integration with WIRPO’s instance of SNOW , the replacement for SD+, the outage will be on the weekend to cause less impact to the industry. SD+ will be unavailable to raise tickets but users will be able to still raise these via the normal number. Subject to change due to multiple inflight changes at the time, but only by a week. | Description updated 09/09/2020
| SD+ | 2020-12-14 | TBC | 2020-12-15 | TBC | This outage is to allow for our instance of SNOW to be integrated with TCS SNOW. This will be on the weekend to cause less impact to the industry. SD+ will be unavailable to raise tickets but users will be able to still raise these via the normal number. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-08-12
| UK Link Portal; UK Link On-line Service; DES and CMS | TBC | TBC | TBC | TBC | UK Link Disaster Recovery Test 2020 (proposed 4/5/6th December 2020) (Failover to DR site) - the UK Link system will operate normally from the DR site in the period between Failover and Failback. NB: UK Link System Application will not be available during this period – but no impacts to Users are expected | New Outage 09/09/2020
| UK Link Portal; UK Link On-line Service; DES and CMS | TBC | TBC | TBC | TBC | UK Link Disaster Recovery Test 2020 (proposed 4/5/6th December 2020) (Failback to primary site) - contingency dates for the test are Friday 15th to Sunday 17th January 2021 with the same timings as above. NB: UK Link System Application will not be available during this period – but no impacts to Users are expected | New Outage 09/09/2021
4970 | DCC | 2020-09-08 | 9:00 | 2020-09-08 | 17:00 | This is the cutover of the TTD environment for DCC. The outage will be during the week, the impact to the industry will be minor as the application cutover is switched from our Legacy DC to TCS ECP. This cutover will be done in-between the daily uploads and therefore any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application to send or receive files should run as normal. Subject to change due to multiple inflight changes and dependencies on suppliers. | Date & time added and description updated 09/09/2020
4970 | DCC | 2020-09-15 | TBC | 2020-09-16 | TBC | This is the cutover of the PROD environment for DCC and conduction of DR. The outage will be during the week, the impact to the industry will be minor as the application cutover is switched from our Legacy DC to TCS ECP. This cutover will be done in-between the daily uploads and therefore any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application to send or receive files should run as normal. Subject to change due to multiple inflight changes and dependencies on suppliers. | Dates added and description updated 09/09/2020
| UK Link | TBC | TBC | TBC | TBC | In order that the UK Link platform continues to be supported we will be carrying out a programme of upgrades to existing systems over the next few months. The upgrades to production systems are planned for December and we will aim to carry these out over the weekend to ensure impact to the industry is minimised. The detailed upgrade schedule will be provided in October. | New Outage 09/09/2021