## 19-20 Summary sheet
Budget line | £k | NTS % | GDN % | IGT% | Shipper % | NTS £k | GDN£k | IGT £k | Shipper £k
Change projects Year 1 | 2500 | 1.6% | 16% | 0.3% | 82.08% | 40 | 400 | 7.5 | 2052

## 19-20 BP change details (hidden)
Title | Description | Amount | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 165000
Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 38500
Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 330000
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 55000
Actual read following estimated transfer read calculating AQ of 1 | Interim solution for XRN4713 | 55000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 55000
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 110000
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | 0% | 100% | 0% |  | 0 | 57000 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | 7.119% | 51.04% | 1.462% | 40.38% | 11746.7058 | 84211.587 | 2412.4667 | 66629.2405
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | 0% | 100% | 0% | 0% | 0 | 58000 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 165000
Allowance for unforseen |  | 394000 | 7.119% | 51.04% | 1.462% | 40.38% | 28049.7096 | 201087.0622 | 5760.678 | 159102.5501
Total Change Budget 19-20 | [6 empty] | 39796.4155 | 400298.6491 | 8173.1447 | 2051731.7907

## Sheet2 (hidden)
Spend To date
June 19 Release ( XRN4679) | 51165.89
DDP | 50000
MOD700 | 40448

## Sheet1 (hidden)
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 |  | DN
XRN4991: MOD700 |  |  |  | 80896 | 50% | 50% |  |  | 40448 | 40448 | Excluding June 20 | 141613.89
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 2020-06-01 | 247893
DN

## 19-20 - Spend to date (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [8 empty] | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 19/20 Pipeline | 0 | 171053.49 | 10299.9 | 731583.61 | [8 empty] | 2500 | 960.833 |  | 1539.167 | 960.833
19/20 Budget | 40000 | 400000 | 7500 | 2052000
Variance | -40000 | -228946.51 | 2799.9 | -1320416.39
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 85913 | 100% |  |  |  | 85913 | 0 | 0 | 0
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 |  |  |  |  | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 271954 | 100% |  |  |  | 271954 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-06-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-06-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 |  |  |  |  | 0 | 0 | 0 | 0
XRN4677: Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | Cancelled | [5 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 | 0 | 0
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | ? | [5 empty] | 0 | 0 | 0 | 0
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | Cancelled | [5 empty] | 0 | 0 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 76367 | 100% |  |  |  | 76367 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 40000 | 100% |  |  |  | 40000 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 5434 | 100% |  |  |  | 5434 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 9139 | 50% | 50% |  |  | 4569.5 | 4569.5 | 0 | 0
XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Descoped from June 20 | [7 empty] | 0 | 0 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 5928 | 100% |  |  |  | 5928 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 8151 |  |  |  | 100% | 0 | 0 | 0 | 8151
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 8892 | 100% |  |  |  | 8892 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for June 20 |  | 2020-06-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 10868 |  | 90% |  | 10% | 0 | 9781.2 | 0 | 1086.8
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 5434 | 100% |  |  |  | 5434 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 75845 | 100% |  |  |  | 75845 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 16000 | 100% |  |  |  | 16000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0
[9 empty] | 731583.61 | 171053.49 | 0 | 10299.9

## 19-20 Final Cost view (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [9 empty] | Budget £k | Actual |  | Budget | Actual
Change Budget 19/20 Actual cost | 0 | 344531.89 | 72698.6 | 983609.8168 | [9 empty] | 2500 | 1400.8403 |  | 1099.1597 | 1400.8403
19/20 Budget | 40000 | 400000 | 7500 | 2052000 | [10 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | -40000 | -55468.11 | 65198.6 | -1068390.1832 | [9 empty] | 20/21 June 20 Release |  | 171819.3128 | 43255.2521 | 113689.8466 | 328764.4115
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £ |  | 20/21 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 75174 | 100% |  |  |  | 75174 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 | 100% |  |  |  | 24896 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 268274 | 100% |  |  |  | 268274 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-11-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7 |  |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-11-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4 |  |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 | 100% |  |  |  | 23000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | 2019-11-01 | 59097 | 33% | 67% |  |  | 19502.01 | 39594.99 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 59097 | 100% |  |  |  | 59097 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 25510 | 100% |  |  |  | 25510 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 59984 | 100% |  |  |  | 59984 | 0 | 0 | 0 |  | 32131 | 100% |  |  |  | 32131 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 97579 | 50% | 50% |  |  | 48789.5 | 48789.5 | 0 | 0 |  | 51831.2915 | 50% | 50% |  |  | 25915.6457 | 25915.6457 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 48679.6684 | 100% |  |  |  | 48679.6684 | 0 | 0 | 0 |  | 24894.0466 | 100% |  |  |  | 24894.0466 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 54902 |  |  |  | 100% | 0 | 0 | 0 | 54902 |  | 27043.7336 |  |  |  | 100% | 0 | 0 | 0 | 27043.7336
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 31990.1193 | 100% |  |  |  | 31990.1193 | 0 | 0 | 0 |  |  | 100% |  |  |  | 0 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for Nov 20 |  | 2020-11-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0 |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 167345 |  | 90% |  | 10% | 0 | 150610.5 | 0 | 16734.5 |  | 162115.1856 |  | 90% |  | 10% | 0 | 145903.667 | 0 | 16211.5186
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 57903.5192 | 100% |  |  |  | 57903.5192 | 0 | 0 | 0 |  | 30749.1543 | 100% |  |  |  | 30749.1543 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 72185 | 100% |  |  |  | 72185 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 15420 | 100% |  |  |  | 15420 | 0 | 0 | 0 | CCR | [5 empty] | 0 | 0 | 0 | 0
XRN4779 - Adding AQ to PARR Report |  |  |  | 31159 | 100% |  |  |  | 31159 | 0 | 0 | 0
XRN5064-Meter Asset enquiry API enhancement |  |  |  | 12000 | 100% |  |  |  | 12000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
[9 empty] | 983609.8168 | 344531.89 | 0 | 72698.6 | [6 empty] | 113689.8466 | 171819.3128 | 0 | 43255.2521

## 19-20 Year End Forecast (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [9 empty] | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 19/20 Pipeline | 0 | 355523.6799 | 71268.1128 | 1038827.5259 | [9 empty] | 2500 | 1465.6193 |  | 1034.3807 | 1465.6193
19/20 Budget | 40000 | 400000 | 7500 | 2052000 | [10 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | -40000 | -44476.3201 | 63768.1128 | -1013172.4741 | [9 empty] | 20/21 June 20 Release |  | 174041.5104 | 41701.2347 | 156977.8676 | 372720.6127
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £ |  | 20/21 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 85913 | 100% |  |  |  | 85913 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 | 100% |  |  |  | 24896 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 271954 | 100% |  |  |  | 271954 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-11-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7 | 2020-06-01 |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-11-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4 | 2020-06-01 |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 | 100% |  |  |  | 23000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4677: Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | Cancelled | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | ? | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | Cancelled | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 76367 | 100% |  |  |  | 76367 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 40000 | 100% |  |  |  | 40000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 59100.11 | 100% |  |  |  | 59100.11 | 0 | 0 | 0 |  | 32044 | 100% |  |  |  | 32044 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 95945.3193 | 50% | 50% |  |  | 47972.6596 | 47972.6596 | 0 | 0 |  | 84248 | 50% | 50% |  |  | 42124 | 42124 | 0 | 0
XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Approved for June 20 |  | 2020-06-01 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 47620.2555 | 100% |  |  |  | 47620.2555 | 0 | 0 | 0 |  | 24894.0466 | 100% |  |  |  | 24894.0466 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 53445.0983 |  |  |  | 100% | 0 | 0 | 0 | 53445.0983 |  | 27043.7336 |  |  |  | 100% | 0 | 0 | 0 | 27043.7336
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 30401 | 100% |  |  |  | 30401 | 0 | 0 | 0 |  |  | 100% |  |  |  | 0 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for Nov 20 |  | 2020-11-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0 | 2020-06-01 | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 167609.1448 |  | 90% |  | 10% | 0 | 150848.2303 | 0 | 16760.9145 |  | 146575.0115 |  | 90% |  | 10% | 0 | 131917.5104 | 0 | 14657.5012
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 56932.3908 | 100% |  |  |  | 56932.3908 | 0 | 0 | 0 |  | 57915.821 | 100% |  |  |  | 57915.821 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 75845 | 100% |  |  |  | 75845 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 15420 | 100% |  |  |  | 15420 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4779 - Adding AQ to PARR Report |  |  |  | 36159 | 100% |  |  |  | 36159 | 0 | 0 | 0
XRN5064-Meter Asset enquiry API enhancement |  |  |  | 12000 | 100% |  |  |  | 12000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
[9 empty] | 1038827.5259 | 355523.6799 | 0 | 71268.1128 | [6 empty] | 156977.8676 | 174041.5104 | 0 | 41701.2347

## 20-21 Year End Forecast
Current Month | [6 empty] | September
| NTS £ | GDN£ | IGT £ | Shipper £ | Total £ |  |  | NTS £ | GDN£ | IGT £ | Shipper £ | Total £ |  |  |  | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 20/21 Pipeline | 1200 | 421470.5238 | 68480.2521 | 1264639.2665 | 1755790.0425 |  | Change Budget 20/21 Pipeline | 1200 | 481470.5238 | 83480.2521 | 1244639.2665 | 1810790.0425 |  |  |  | 3000 | 1680.79 |  | 1319.21 | 1680.79
20/21 Budget | 48000 | 600000 | 9000 | 2343000 | 3000000 |  | 20/21 Budget | 48000 | 600000 | 9000 | 2343000 | 3000000 |  |  |  | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | -46800 | -178529.4762 | 59480.2521 | -1078360.7335 | -1244209.9575 |  | Variance | -46800 | -118529 | 74480 | -1098361 | -1189209.9575 |  |  | 21/22 Forecast | 0 | 0 | 0 | 0 | 0
Total
Movement since last report
[8 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total £
[7 empty] | Varience in avilable funds since last report | 0 | 60000 | 15000 | -20000 | 55000
[7 empty] | 20/21 Budget | 0 | 0 | 0 | 0 | 0
[7 empty] | Variance | 0 | 60000.4762 | 14999.7479 | -20000.2665 | 55000
Title | Description | Cost Type | CCR | 19/20 spend | Amount | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £ |  |  | 21/22 | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £
XRN4941 Auto updates to meter read frequency (MOD0692) | June-21 (unless authority decision delayed beyond 25/10/20). Cost based on BER initially produced as part of Nov-20 with aplicable UAT / risk margin added. Original BER didn't inlcude risk margin or ful UAT costs. The value listed here will be amended when / if the new BER (expeted to be approved in Nov-20 ChMC) alters cost. The cost shown here is 75% of the total estimated cost associated with this change, to represent the expected drawn down on the current financial year. | BER* |  |  | 43719 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 43719 | [7 empty] | 0 | 0 | 0 | 0
XRN4932 - Improvements to the quality of the conversion factor values held on the supply point register (MOD0681S) | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER |  | 57903.5192 | 30749.1543 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 30749.1543 | [7 empty] | 0 | 0 | 0 | 0
XRN4930 - Requirements to inform Shipper of Meter Link Code Change | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER |  | 48679.6684 | 24894.0466 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 24894.0466 | [7 empty] | 0 | 0 | 0 | 0
XRN4888 - Removing duplicate address update validation for IGT Supply Meter Points via CMS | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER |  | 54901.791 | 27043.7336 | 0% | 0% | 100% | 0% | 0 | 0 | 27043.7336 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to treatment and reporting of CYCL reads | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER |  | 59984.478 | 32130.9009 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 32130.9009 | [7 empty] | 0 | 0 | 0 | 0
XRN4850 - Notification of customer contact details to Transporters | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER |  | 167344.5788 | 162115.1856 | 0% | 90% | 10% | 0% | 0 | 145903.667 | 16211.5186 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) improvements | June 20 release - the costs shown are reflective of costs to be paid from BP20 only | BER |  | 97578.5807 | 51831.2915 | 0% | 50% | 0% | 50% | 0 | 25915.6457 | 0 | 25915.6457 | [7 empty] | 0 | 0 | 0 | 0
XRN4871B Modification 0665 - Changes to ratchet regime | Part B only - functional changes to auto calculate associated ratchet charges (November 20) | BER |  | 9880 | 103501.73 | 0% | 70% | 0% | 30% | 0 | 72451.211 | 0 | 31050.519 | [7 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | Agreed in Feb 20 CHMC to close change |  |  | 5187 | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | Agreed in Feb 20 CHMC to close change |  |  | 5434 | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes |  |  |  | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes |  |  |  | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5053 - Single sided nominations improvements | Gemini Funded change |  |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5054 - Negative implied flow rates | Gemini Funded change |  |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4801 - Additional information to made veiwable on DES | November 20 release | BER |  |  | 88703 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 88703 | [7 empty] | 0 | 0 | 0 | 0
XRN4931 - Submission of space in mandatory data on multiple SPA files | November 20 release | BER |  |  | 84034 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 84034 | [7 empty] | 0 | 0 | 0 | 0
XRN4992 - MOD0687 creation of new charge to recover Last Resort Supply Payments | June-21 release subject to Ofgem approval of mod. Cost listed is taken from original BER for November 2020 release (change was subsequently descoped). The origibal cost that was removed from Nov-20 BER didn't contain full UAT costs or risk margin. These have now been added. The cost shown represents 75% of the total BER* cost, to represent what funds are estaomted to be required to be drawn-down from current financial year | BER* |  |  | 49408 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 49408 | [7 empty] | 0 | 0 | 0 | 0
XRN5036 Updates to must read process | November 20 Release Option 1 costs 30k (progressing with this option which will be funded via Minor Release Budget) Option 2 costs 48k | BER |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5048 - Make an indicator available where a Supply Meter Point forms part of a Network Trial | Closed with no further action |  |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5038 - MOD0691 CDSP to convert class 3 or 4 meter points to Class 1 when G1.6.15 criteria is met | ROM costs |  |  |  | 70000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 70000 | [7 empty] | 0 | 0 | 0 | 0
XRN4899 - PSR - Change of Supplier event | November 20 release | BER |  |  | 120162 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 120162 | [7 empty] | 0 | 0 | 0 | 0
XRN4897 - Resolution of deleted Contact Details (contained within the S66 records) at a change of Shipper event | November 20 release | BER |  |  | 117798 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 117798 | [7 empty] | 0 | 0 | 0 | 0
XRN5070 - amendments to isolation flag | Withdrawn |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
Market Trial for 2 Major releases | Added as a placeholder at the start of the FY, but MT costs only apply to XRN4850 with associayed £ included in individual line item for this change |  |  |  |  | 1.6% | 20% | 0.3% | 78.1% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN 5072 - Class 4 with AMR/DRE installed-RGMA flow received with no RTC count |  |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5080- Failure to supply gas (FSG/GSOP1)-System changes |  |  |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5091 - Defferral of creation of class change reads at tranfer of ownership | HLSO range £120k-£200k. Candidate for Nov-21 release. Costs included in FY 20/21 are for potential EQR costs (c10% of total final cost) | HLSO * 10% to account for potential EQR (Design) costs required in FY 20/21 |  |  | 20000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 20000 | [7 empty] | 0 | 0 | 0 | 0
XRN5092 - iConversion phase2 | to be funded from Gemini |  |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5093 - Update of AUGE table to reflect new EUC band | HLSO £250k. June-21 | HLSO * 75% (to account for funds likley to be drawn from BP20) |  |  | 187500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 187500 | [7 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. |  |  |  | 60000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 60000 | [7 empty] | 0 | 0 | 0 | 0
XRN5014 - Facilitating hydeploy live trials | November 20 release | BER |  |  | 82200 | 0% | 100% | 0% | 0% | 0 | 82200 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4780B - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) |  |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN4780C - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | June-21 via CSSC - 130,000 | HLSO |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
IGT DDP access | XRN 5164 which is being deliverd via DDP Drop 8 | HLSO |  |  | 0 | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5116 Domestic Report - Must Read Prenotification | Withdrawn |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5120 MAP to UKL Monthly Comparison Service Part A | HLSO approval being sought at Sep-20 ChMC | HLSO |  |  | 140000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 140000 | [7 empty] | 0 | 0 | 0
XRN5120 MAP to UKL Monthly Comparison Service Part B | Funding split TBC as may have cross-constituency benefit
XRN5121 Supplier Portfolio Service |  |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
XRN5122 Gemini System Enhancements - Delivery |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5142 New Allowable Values for DCC Service Flag in DXI File From DCC | HLSO £200k. Previously reported against June-21 (*75% to allow for FY cross over). De-scoped from June-21 in Sep ChMC. Will now be considered in future major release scoping | HLSO £200k |  |  | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5143 Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP |  |  |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5146 Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) | HLSO |  |  |  | 5000 | 0% | 100% | 0% | 0% | 0 | 5000 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | CSS Funded |  |  |  | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5147 Optimising the Must Read process for IGT Customers |  |  |  |  | 0 | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5164 CSEP Data Assurance – Performance Monitoring Capability | Being delivered via DDP Drop 8. Funding split is 50/50 between IGTs and DNs but DNs funding from investment budget, IGTs funding from DSC Change Budget |  |  |  | 25000 | 0% | 0% | 100% | 0% | 0 | 0 | 25000 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5167 Report Product Class 4 Read Performance (MOD 672) | DDP |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5168 – MOD0721 – Shipper submitted AQ Corrections during COVID-19 | Not implemented. Costs associated with work completed before change was withdrawn |  |  |  | 15000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 15000 | [7 empty] | 0 | 0 | 0 | 0
XRN5169 – MOD0722 – Allow Users to submit Estimated Meter Readings during COVID-19 | Reporting requirements / potential costs still being assessed |  |  |  | 0 | 0% | 67% | 0% | 33% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5170 – MOD0723 – User of the Isolation Flag to identify site with abnormal load reduction during COVID-19 period | Reporting requirements / potential costs still being assessed |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5171 – MOD0724 – Amendment to Ratchet charges during COVID-19 period | Reporting requirements / potential costs still being assessed |  |  |  | 0 | 0% | 67% | 0% | 33% | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5172 MOD0725 – Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | Not implemented. Costs associated with work completed before change was withdrawn |  |  |  | 15000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 15000 | [7 empty] | 0 | 0 | 0 | 0
XRN4923-AQ calculation for RGMA (ONUPD) customer reads |  | HLSO |  |  | 20000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 20000 | [7 empty] | 0 | 0 | 0 | 0
4645a- The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) |  | HLSO |  |  | 30000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 30000 | [7 empty] | 0 | 0 | 0 | 0
XRN5007 Enhancement to reconciliation process where prevailing volume is zero | [5 empty] | 0% | 67% | 0% | 33% | 0 | 0 | 0 | 0
XRN5188 Interim Data Loads of MAP Id into UK Link | [5 empty] | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0
XRN5192 CMS Reference Number in Amendment Invoice Supporting Data | [5 empty] | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0
XRN5193 Stop MUR Generation of GT SMPs | [5 empty] | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0
XRN5195 Ceased Responsibility Date Following Shipper Withdrawal (IDL) | [5 empty] | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0
XRN5196 Address Amendments Validation | [5 empty] | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0
XRN5197 QMP File Validation in CMS – Current Address field | [5 empty] | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0
XRN5199 Amendments to V12 of the SDT Service Description Table | [5 empty] | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0
XRN5200 Shipper Pack Transition to Data Discovery Platform | Delivery via DDP |  |  |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0
XRN4990 - MOD0664 - Transfer of sites with low read submission performance | [5 empty] | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0
XRN5231 - MOD0719R - Flow Weighted Average CV (FWACV) | [5 empty] | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0
XRN5187 - MOD0696v - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExA | Funding split TBC | [8 empty] | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
XRN5186 - Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | Funding split TBC | [8 empty] | 0 | 0 | 0 | 0
XRN4876 - Changes to PARR Reporting | Some of the requiements of this change have already been delivered in previous DDP drops. Future DDP drops will continue to deliver some of the other requirements, whereas some requirements will be done outside of DDP (until related DDP content is live) | HLSO |  |  | 75000 | 1.6% | 20% | 0.3% | 78.1% | 1200 | 15000 | 225 | 58575
XRN5206 TPI/PCW Access | Funding split TBC | [8 empty] | 0 | 0 | 0 | 0
XRN5135 DNO and NTS Invoices to Shippers and DNs VAT compliance |  | HLSO |  |  | 75000 | 0% | 100% | 0% | 0% | 0 | 75000 | 0 | 0
XRN5180 Inner Tolerance Validation for replacement reads and read insertions | [5 empty] | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0
XRN5153 iConversion Phase 2 | Funding split TBC | [8 empty] | 0 | 0 | 0 | 0
XRN5218 CDSP provision of Class 1 read service | Funding split TBC
Total Change Budget 20-21 |  |  |  |  | 3000000 |  |  |  |  | 1200 | 421470.5238 | 68480.2521 | 1264639.2665 | [7 empty] | 0 | 0 | 0 | 0
[12 empty] | 48000 | 600000 | 9000 | 2343000