## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0664 IGT145 | With Workgroup | UNC - UIG | Adopted by SSE | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | No implementation specified | Rule & System change | NA | UK Link | UK Link impacts to identify eligible sites and maintain performance parameters. Enhancements to processes to create a lockout period. Reports required to compare Shipper performance. | NA | UK Link | David Addison | Modification looks to create an obligation for Shippers to move Supply Points with low Valid Daily Meter Reading submission performance from Classes 2 and 3 into Class 4 following a consecutive period of poor performance. The CDSP will automatically move any Supply Points note moved by the Shipper in such a scenario (after an allowed period of time). Impacts to UK Link expected. Panel agreed to send 0664 back to WG to address the issues raised during consultation. WG have worked through the issues and a Variation Request has been drafted to include an additional business rule which accounts for a change in Supplier scenario. This requires a tweak in the CDSP solution but should be covered under the cost provided within the original ROM. XRN4990 is still within the early stages of development and is not currently in scope for a release. Variation Request at Panel unanimously accepted, 664V out for consultation closing 12th Oct. October Panel voted that a new issue arose requiring new view from Workgroup, and will return to Panel in December 2020.
Mod 0674 IGT138 | With Workgroup | UNC - UIG | Scottish Power on behalf of PAC | Performance Assurance Techniques and Controls | No implementation specified | Reporting and Invoicing | NA | NA | New reports are required and the incentive regime will need to be developed with considerations around the invoicing element. | TBC | Gemini | Emma Smith | Modification seeks to provide an effective framework for the governance of industry performance that gives industry participants mutual assurance in the accuracy of settlement volume allocation. Developing through the WG. System impacts currently unknown. Reporting is definitely expected but the way sanctions and incentives are to be applied must be developed and system impacts assessed. Modification still developing. September Panel agreed to send back to WG, returning to Panel in Jan 20.
Mod 0676R | With Workgroup | UNC - WG | Gazprom Energy | Review of Gas Transporter Joint Office Arrangements | Any modifications as a result of 0676R will be impact assessed and any implications considered. | [5 empty] | NA | TBC | To request a review of the Uniform Network Code (UNC) General, Modification Rules and Joint Gas Transporter Governance arrangements for the Joint Office of Gas Transporters. Output for the Review Group is to assess whether the current arrangements are fit for purpose and recommend modifications where appropriate. Review group still developing.
Mod 0686 (Urgent) | Awaiting Ofgem decision | UNC - Transmission | Vermilion Energy Ireland Limited | Removal of the NTS Optional Commodity Rate with adequate notice | Oct-20 | Rule and System Change | No | UK Link and Gemini | Impact assessment required | TBC | Gemini | Steve Pownall | Removal of the NTS Optional Commodity Rate1 with adequate notice. “Adequate notice” here means a notice period that is consistent with both the TAR NC and the UNC requirements. As long a notice period as possible is desirable for Users who may be subject to contractual constraints. It is not considered as an alternative to 0678 because the proposer has stated that it will be possible to implement this proposal for effect on the OCR tariff from October 2019 and any one of the 0678 (or alternatives for effect on other tariffs at the same time or any subsequent date. Panel did not recommend the implementation of modification 0686. Ofgem have decided to implement 0678A. This may impact the decision on 0686. At November 20 Panel, Ofgem gave update that this has been de-prioritised therefore a timescale for a decision is unknown.
Mod 0687 | Awaiting Ofgem decision | UNC - DWG | Total Gas & Power (on behalf of ICoSS) | Clarification of Supplier of Last Resort Cost Recovery Process | Nov-19 | System Change | No | UK Link | Changes to introduce a new charge type for domestic and non-domestic sites in a SoLR event | Nov-20 | UK Link | Ellie Rogers | Modification seeks to provide clarity on how any costs incurred by the Gas Distribution Networks (Transporters) as part of a Last Resort Supply Payment arising from a Supplier of Last Resort event are recovered from Shippers. It proposes the introduction of a new customer charge (the SoLR customer charge) into the Gas Transportation charging statements in order to provide detail on how these costs are allocated. A Change Proposal has been raised XRN4992 has been raised to deliver the system changes for 0687. Panel voted to implement the modification and it is currently with Ofgem for a decision. ChMC approved the enduring solution for XRN4992 to be delivered within November 2020 Release. May ChMC decided to remove XRN4992 from scope of November 2020 release in order to wait for the Ofgem decision. XRN4992 is now in scope for June 2021 Major Release. An Ofgem decision is required by latest October for the ChMC to decide whether to progress in June 2021 or de-scope. This was noted by Panel and Ofgem. This is still waiting Ofgem decision. XRN4992 has now been de-scoped from the June 2021 release due to not knowing the outcome of the Modification yet. Ofgem are likely to reject the Modification. Ofgem update at WG was that this has been deprioritised whilst an alternative system for recovery levy payments is developed under REC.
Mod 0693R | With Workgroup | UNC - UIG | Scottish Power (on behalf of the UIG Taskforce) | Treatment of kWh error arising from statutory volume-energy conversion | Any modifications as a result of 0693R will be impact assessed and system implications considered. | [5 empty] | TBC | James Rigby | The Request is to review the treatment of the error in kWh that arises from statutory volume to-energy conversion factors in order to mitigate the impact on gas settlement, reconciliation and Annual Quantities (AQs). WG are discussing the request. Any potential solutions from the review will need to be assessed for system impacts. Review Group has developed options which re due to be included within a Review Group report which will request the Review group to be closed. The industry will be able to raise a Modification based on any of the proposed options if required. December 2020 Panel voted to extend 0693R reporting date to January 2021 Panel, due to limited time between completing the Report at final Workgroup on 14th December and the December Panel.
Mod 0696 | Awaiting Ofgem decision | UNC - DWG | Gazprom Energy | Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule Change | TBC | Potential system impacts | For the CDSP to correct any capacity charges identified by the Shipper, an offline process would be required. New internal screen expected to set the PMSOQ at the NExA SOQ value provided by the Transporter. | TBC | UK Link | Ellie Rogers | To the extent to which a Consumer has entered into a bi-lateral Network Exit Agreement (NExA) with the relevant Transporter then any new or additional capacity charging should only apply from the relevant date set out in the NExA. Modification looks to propose that any new or additional capacity requested under the UNC should only be chargeable from the date set out in the NExA. Modification issued back to WG by Ofgem to consider further questions. Following the addition of a new business rule, a small system change is anticipated to create a new screen to cap the PMSOQ at the NExA SOQ and a Change Proposal would be required to deliver this and to put in the offline process to conduct the capacity correction. A ROM Response for this system change has been provided. May Panel recommended the implementation on 0696. It is now with Ofgem for a decision. A Change Proposal has been raised for the associated system changes and processes (XRN5187). Ofgem update at WG was that DSC change has been implemented which flags sites with a NExA so some benefit to sites already, so modification has been deprioritised.
Mod 0701 | Awaiting Ofgem decision | UNC - DWG | NGN | Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule and System Change | N/A | UK Link | Changes to UK Link to enhance what is held against NExA sites and add rules for certain data items | TBC | TBC | Ellie Rogers | To improve visibility where a consumer has entered into a bilateral Network Exit Agreement (NExA) with the relevant Transporter, and to link capacity increased with the NExA so that the allowed capacity does not exceed the capacity as agreed in the NExA. System impacts expected to enhance what is currently held in UK Link against NExAs. New rules and logic also to be applied for NExA sites. ROM response has been provided which indicates the central system impacts. This is being reassessed in line with updated business rules. The modification will require delivery within a Major Release. May Panel recommended the implementation on 0701. It is now with Ofgem for a decision. A Change Proposal has been raised for the associated system changes and processes (XRN5186). Ofgem update at WG was that DSC Change has been implemented which flags sites with a NExA so some benefit to sites already, so Modification has been deprioritised.
Mod 0705R | With Workgroup | UNC - WG | National Grid | NTS Capacity Access Review | Any modifications as a result of 0705R will be impact assessed and system implications considered. | [5 empty] | TBC | Steve Pownall | To review the principles and establish long-term strategy for the NTS capacity access regime. Ensuring the regime is appropriate for commercial behaviours experienced today, simplified and adaptable whilst being consistent with relevant obligations. To make recommendations for change and addressing short-term problems in accordance with the long-term ambition. 12 month Review Group has been set up. Central impacts currently unknown and dependent on the Review Group development which will be monitored. Oct Panel voted that this Mod should return to workgroup with an interim report in April 2021 and a final report by Oct 2021 Panel.
Mod 0727 (Urgent) | Awaiting Ofgem decision | UNC | Benoit Enault, Storengy UK Ltd | Increasing the Storage Transmission Capacity Charge Discount to 80% | Oct-20 | Rule Change | N/A | Potential system impacts | Potential Gemini and UK Link invoicing changes | Oct-20 | Gemini | Steve Pownall | The revised NTS Charging Methodology (in place from 01 October 2020) includes a discount for capacity purchased at storage sites of 50%. This Modification seeks to include a higher discount rate of 80% for such capacity, to be introduced on 01 October 2020 or as soon as possible thereafter. Central systems might be impacted. This should be picked up by the Gemini project team. With Ofgem for a decision.
Mod 0728 A/B/C/D (Urgent) | Awaiting Ofgem decision | UNC | Multiple | Introduction of a Conditional Discount for Avoiding Inefficient Bypass of the NTS | Oct-20 | Rule Change | N/A | UK Link and Gemini | Impacts expected on Gemini and UK Link invoicing systems | Oct-20 | Gemini | Steve Pownall | The revised NTS Charging Methodology (in place from 01 October 2020) does not incorporate a mechanism to dis-incentivise inefficient bypass of the NTS. This Modification seeks to introduce a new Conditional Discount to the Charging Framework so that a product to manage potential inefficient bypass will be in place as soon as possible on or after the changes introduced from UNC0678A, which become effective from 01 October 2020. Impacts are anticipated on central systems. This should be picked up by the Gemini project team. With Ofgem for a decision. Ofgem gave an update at November 2020 Panel, a minded decision will be provided by end of the calendar year, and is an Ofgem priority.
Mod 0729 | Awaiting Ofgem decision | UNC | National Grid | Applying a discount to the Revenue Recovery Charge at Storage Points | Oct-20 | Rule Change | N/A | Potential system impacts | TBC | Oct-20 | Gemini | Steve Pownall | The revised NTS Charging Methodology (in place from 01 October 2020) includes a discount for capacity purchased at storage sites of 50%, however, no such discount is applied to the application of the Revenue Recovery Charge (RRC). This Modification seeks to reflect the Storage Discount in a discount to the RRC rate to be applied to capacity held at storage sites. It is proposed that this change is introduced on 01 October 2020 or as soon as possible thereafter. Modification due to go to Panel in July. Central system impacts are anticipated which will be assessed by the Gemini project team. Ofgem rejected urgent status. Panel assigned the Modification to WG. August Panel voted 720S issued to consultation and coming back to September's meeting for a decision. September Panel could not agree on a unanimous decision to implement, and has been issued to Ofgem with a recommendation not to implement.
Mod 0730V | Out for Consultation | UNC - DWG | Gazprom Energy | COVID-19 Capacity Retention Process | No implementation specified | Rule Change | Y | None anticipated | No central system impacts as we are anticipating to manage this via manual processes. | N/A | N/A | Dave Addison /Ellie Rogers | This modification seeks to allow sites (supply points) isolated in accordance with modification 0723 (Urgent) - Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period to be subject to a rebate of 50% of their LDZ Capacity Costs. Ofgem rejected urgent status and the modification has been sent to WG for development. Central system impacts are not anticipated as it is expected this process will be offline and manual but a Change Proposal may be required to put these in place. We expect implementation to be relatively quick following the Modification decision. October Panel voted that 720 should be issued to Consultation with a close out date of 5th November 2020. At Extraordinary Panel on 27 November, 0730 was issued back to WG due to concerns arising around the solution and legal text. A Variation Request is expected to be raised. A CP will be raised to deliver the associated central changes. A variation request has been submitted for this Modifcation and was accepted at December 2020 Panel. 730V has now been issued back out for consultation to report back to January Panel.
Mod 0731S | To be implemented (Proposed removal from Bubbling Under) | UNC | Gazprom Energy | Introduction of an Annual Modification Panel Report | No implementation specified | Rule Change | N/A | None anticipated | No central system impacts anticipated | N/A | N/A | Ellie Rogers | The Modification Panel is the body constituted under the Uniform Network Code to oversee the Modification process as set out in the Uniform Network Code General Terms and Modification Rules. With the role of an independent Chair for the Modification Panel and UNCC there is an opportunity to leverage the knowledge and experience available, to facilitate continuous improvement and to ensure the efficient and effective operation of the Modification Panel and UNCC. No central system or process impacts anticipated. Workgroup reporting date changed to Nov 2020. Nov 2020 Panel voted to issue for consultation closing 10th December 2020. December Panel voted to implement 0731S.
Mod 0734 | With Workgroup | UNC | Gazprom Energy | Reporting Valid Confirmed Theft of Gas into Central Systems | No implementation specified | Rule and System Change | N/A | UK Link | Impacts to CMS are anticipated but dependent on the solution | TBC | UK Link | Ellie Rogers / Dave Addison | This Modification seeks to place obligations on Shipper parties to ensure that valid confirmed theft of gas data received from Suppliers, such as consumption volumes, are appropriately entered into central systems for the purposes of Settlement. It also seeks to ensure corrections to Annual Quantities (AQ) that are required as a result of theft of gas are undertaken as required. Modification has been issued to WG for development. A Change Proposal has been raised to deliver the associated central changes (XRN5236). The Modification is expected to be updated to reflect WG discussions. Due to the CMS rebuild, a tactical solution is anticipated for the delivery of Mod0734 and the requirements should be filtered into the CMS rebuild team. Due to report to Panel 18th February 2021.
Mod 0735 | Voing deferred | UNC | National grid NTS | UNC Changes as a consequence of the absence of trade agreement/s between the United Kingdom and the European Union (‘no deal’) | No implementation specified | Reference within UNC Change | N/A | None anticipated | No central system impacts anticipated | TBC | N/A | N/A | A number of minor changes to the Uniform Network Code (UNC) are required as a consequence of the end of the implementation period following the United Kingdom (UK) withdrawal from the European Union (EU). In principle, these changes modify existing references to EU regulations with reference to UK amendment regulations and where appropriate remove references to EU entities. Nov 2020 Panel voted to issue for consultation closing 10th December 2020. December 2020 Panel deferred this Modification until outcome of Brexit talks are known.
Mod 0736S | To be implemented (Proposed removal from Bubbling Under) | UNC | Cadent | Clarificatory change to the AQ amendment process within TPD G2.3 | No implementation specified | Rule Change | N/A | UK Link | A change will be required to create and maintain a User Relationship Table | TBC | UK Link | Ellie Rogers/ Dave Addison | This Modification proposes to make a change to the AQ amendment process outlined in the Uniform Network Code Transportation Principles Document Section G 2.3 (UNC TPD G2.3) in order to clarify the circumstances in which such amendments can be made. 0736A applies these clarifications from the 1 April 2020. November 2020 Panel voted to decouple Modification 736 from 736A, this Mod now stands as 736 and has been issued to Consultation. A CP has been raised to deliver the solution (XRN5237). If approved, implementation is anticipated to be immediate (January 2021) and therefore a predominantly manual solution will be required. Extraordinary Panel 27th November voted to issue for Consultation closing 10th December 2020. At December 2020 Panel, this Modification was voted to be implememnted. Providing there are no appeals raised this will be implememnted on 14th January 2021.
Mod 0737 | Out for Consultation | UNC | Centrica | Transfer of NTS Entry Capacity from an abandoned ASEP | At the earliest opportunity upon direction of the Authority | Rule Change | N/A | Unknown and needs to be assessed | Currently unknown | TBC | N/A | TBC | This Modification proposes to enable the transfer of NTS Entry Capacity booked at “abandoned” donor Aggregated System Entry Points (ASEPs) to alternative recipient ASEPs where there is unsold entry capacity at the recipient ASEPs. A ROM is required to assess the central impacts. Workgroup report is completed, December 2020 Panel voted to issue out for consultation, reporting back in February 2021.
Mod 0738 | Out for Consultation | UNC | Barrow Shipping Limited | Incremental NTS Entry Capacity Surrender | No implementation specified | Rule Change | N/A | TBC | It is believed that existing capacity reduction provisions in Central Systems will be able to accommodate any reductions in entry capacity holdings. | TBC | TBC | TBC | This Modification proposes to allow incremental NTS entry capacity to be surrendered. Modification suggests the system can manage this change as is but this will need to be assessed formally. December 2020 Panel voted to issue out for consultation, reporting back in February 2021.
Mod 0739 | With Workgroup | UNC | ENI | Aggregate overrun regime for Original Capacity held at the Bacton ASEPs | At the earliest opportunity upon direction of the Authority | Rule Change and System Change | N/A | Gemini Impacts | Anticipated system impacts in the identification and reporting of Original Entry capacity Holdings and the calculation of Aggregate Overrun Quantities | TBC | TBC | TBC | This Modification is to ensure Entry Capacity acquired by Users at the Bacton ASEP, prior to Bacton splitting into two ASEPs, can be used flexibly via the introduction of an aggregate overrun regime following changes to the NTS Charging Regime. A ROM is required to assess the impacts of this change.
Mod 0741 IGT147 | With Workgroup | UNC | EON | Updating specific gender references to neutral terms | No implementation specified | UNC references change | N/A | None | N/A | N/A | N/A | N/A | This Modification is being raised to update any specific gender references such as ‘he’, ‘him’, ‘his’, ‘her’, ‘Chairman’ etc to neutral terms such as ‘their’, ‘them’, ‘they’ and ‘Chairperson’ in the Uniform Network Code. No central impacts. November 2020 Panel voted to issue to Workgroup for development and a report to be provided to January 2021 Panel.
Mod 0743S | Issued to Workgroup | UNC | National Grid NTS | Revisions to User Termination Provisions | No implementation specified | Rule Change | N/A | No identified central system impacts | N/A | N/A | N/A | TBC | Changes are required to the Uniform Network Code (UNC) following the implementation of the Corporate Insolvency and Governance Act 2020 (‘CIGA’). Whilst CIGA does not directly mandate change to the UNC, it has the effect of limiting the circumstances in which a Termination Notice can be issued to a User. Therefore it is appropriate to acknowledge these limitations in the UNC. Central system changes not anticipated but an amendment to the EBCC arrangements may be required. This is being assessed by the relevant committee.
Mod 0745 | Issued to Workgroup | UNC | National Grid | Mandatory Setting of Auction Bid Parameters | No implementation specified | Rule Change | N/A | Potential system impacts | A ROM is being sought from the CDSP, and the resulting impact analysis will be shared with the Workgroup. | TBC | TBC | TBC | This Modification proposes to mandate the setting of certain bid parameters prior to Users being able to place bids in an Auction.
Mod 0746 (Previously Mod 0736A) | Issued to Workgroup | UNC | Gazprom Energy | Clarificatory change to the AQ amendment process within TPD G2.3 | No implementation specified | Rule Change | No | No identified central system impacts | A change will be required to create and maintain a User Relationship Table. | N/A | N/A | Ellie Rogers | This Modification proposes to make a change to the AQ amendment process outlined in the Uniform Network Code Transportation Principles Document Section G 2.3 (UNC TPD G2.3) in order to clarify the circumstances in which such amendments can be made and to apply this clarification from the 1 April 2020. Nov 2020 panel issued to Workgroup 0746 with a report by the 15 April 2021 Panel. A CP will be raised to deliver the associated requirements. This is anticipated to be predominantly manual. Due to report to Panel 15th April 2021.
Mod 0747 | To be implemented (Proposed removal from Bubbling Under) | UNC | BUUK | Amendment of reference from AIGT to INA within the UNC | No implementation specified | UNC references change | N/A | No identified central system impacts | N/A | N/A | N/A | N/A | The purpose of this Modification is to amend the reference for the AIGT (Association of Independent Gas Transporters) to the INA (Independent Networks Association). The AIGT no longer exists and since early 2020 has been amalgamated into the newly formed INA which includes both Independent Gas and Electricity Network businesses. Decemeber 2020 Panel voted to approve treating this Modicifation as fast-track and that it should be implememnted.
Mod 0748 (Urgent) | Out for Consutlation | UNC | National Gris NTS | Prospective Removal of Entry Capacity Revenue from Capacity Neutrality Arrangements | As soon as practical | Rule Change | N/A | Gemini, UK Link, Invoicing | TBC | N/A | Gemini / UK Link | TBC | The purpose of the Modification is to remove capacity revenues recovered from daily interruptible and within day Entry Capacity from Capacity Neutrality arrangements prospectively from the implementation date. Following implementation of UN Modification 0678A on 01 October 2020, inappropriately high cashflows are subject to the Capacity Neutrality Arrangements (c. £0.5m per day). This Proposal seeks to remove Relevant Capacity Revenues from Capacity Neutrality so that these cashflows contribute to recovery of Allowed Revenues rather than being subject to redistribution across Entry Users. Ofgem have agreed that Urgent procedures should apply, this Modification was out for Consultation closing 11th December 2020. The Final Modification Report has been sent to Ofgem with Panel recommendation not to implement from Panel 17th December 2020.
Mod 0750FT | To be implemented (Proposed removal from Bubbling Under) | UNC | NGN | Amendment to regulations relating to Covid Modifications | As soon as practical | UNC references change | N/A | No identified central system impacts | N/A | N/A | N/A | N/A | This Modification updates the quoted regulations in the Uniform Network Code (UNC) Transitional Arrangements Document Part VI for the devolved governments with the new regulations that replace them, as well providing clarity to obligations and future proofing against further replacements that may continue to happen. Decemeber 2020 Panel voted to approve treating this Modicifation as fast-track and that it should be implememnted.
SCP 450 | Deferred | SPAA Change Board | British Gas | Addition of Pressure, Temperature and Compressibility (“PTC”) to Market Doman Data (MDD) General | No implementation specified | Rule and System Change | N/A | Potential system impacts | Potential minimal allowable data item changes required to remove the incorrect allowable value | TBC | TBC | James Barlow | Within the MDD Converter Product Table there is value (“PTC”) which is being populated. This value is not listed within MDD General under A0036 – Conversion Basis Codes. This SCP seeks to add the value “PTC” to MDD General v18.8 and all future MDD release. A minor system change may be required if the value is removed but this is to be assessed once the outcome of the SCP is known.