## Slide 1: CSSC Programme Dashboard
January 2021

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme is now at Amber-Green status based on the progress made with the action tracked by the central programme team. Out of the twelve issues that we raised seven of these have been resolved, we continue to track the remainder, these are planned to be closed by the end of January 21. Xoserve’s delivery status continues to be Green | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Programme Re-plan: Following the Ogem programme re-baseline, caveated with the actions to mitigate concerns that Xoserve raised, we have been tracking these to closure with SI & DCC. Most actions are on track Costs: Costs continue to be monitored closely Missing design changes We continue to track these with DCC and SI. DCC have completed their review. The SI will provide the results of their review of any gaps on 8th January External SIT: Testing is continuing largely to plan with volunteer licence party testing in progress currently. Xoserve have no open defects at this point External NFR SIT: Xoserve have commenced testing. We have 1 defect raised, which is ready to re-test Internal Testing: Internal Testing continues to plan addressing consequential changes and Switching Programme CRs. Transition: Internal planning activities continue alongside engagement with the SI/ Data Migration: DM NF Testing has commenced to plan on 7th December. Data delivery to Landmark for the UIT phases is on track with extraction completed successfully on 21st November. |  |  |  | DMT NFR: Continue test execution External SIT: Continue External SIT support External NFR: Continue test execution Internal Test: Continue SIT & UAT assurance DES:& Secondary APIs Continue development and system test activities. Transition: Continue Transition planning
Programme Update

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall green. Internal & External SIT support in progress. DES Delivery Drop 2 completed to plan, and remains on track for next drop.
 |  | Testing | The overall status remains Green. External SIT support in progress, no Xoserve defects are open at this point. Planning underway for all upcoming test phases such as UEPT, E2E, OT
 |  | Service Management | Impact assessment continues to understand the impact of the proposed Switching Programme SLAs alongside review of the proposed ITIL processes. Awaiting confirmed dates back from the DCC of when the remaining 1-2-1 sessions will take place to address all of the outstanding feedback against the core process maps. Planning for Operational testing is underway for the external OT phase.
 |  | Batch | The overall status is green, with testing support underway.
 |  | Gemini | The overall status is green. Planning underway to undertake a connected Gas Day testing with UK Link.
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess and deliver Switching Programme changes raised through the last few months whilst supporting test phases.

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | Internal workshops in place for the first consultation response due in January 2021. Continues to remain on track. DIscussions have been conducted with Ofgem & REC to understand dependencies around Transitional REC.
 |  | Data Migration & Provision | DMT NF has commenced on 07/12 and remains on track. Data Provision for UEPT remains on track for delivery in January. Xoserve have received the REL Data provision requests which remains the same as last years with no extra data requested.
 |  | Market Trials | Overall the workstream is green. Re-plan activities continue with both customers and Switching Programme.
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan.

## Slide 5: Key Programme Risks (1/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62741 |  | Programme | There is a risk that SIT NFR testing will be deemed invalid if carried out as currently planned because SIT Functional would not have reached the necessary level of code stability for Non functional testing to be carried out leading to additional costs related to resources and environments required to support further cycles of NFR testing once a stable code level has been achieved. High volumes of defects are currently being found in SIT which in turn is impacting progression and therefore delays in completing the SIT cycles required to establish a suitable level of code stability. The current timelines still plan for NFR testing to be carried out prior to the completion of sufficient functional SIT required to establish a stable code set. | Escalate to the SI via all established forums to instigate a near term plan review to ensure these phases are re-planned appropriately. | This risk is still relevant and will continue to be monitored until SIT is complete.. | 03/03/21

## Slide 6: Key Programme Risks (2/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This is likely to become more evident as tests such as connected 'Day in Life processing of CSS' is undertaken. Leaving this risk to be monitored | 27/02/21
61894 |  | Service Management | There is a risk that the CSS proposed SLAs do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | Update from meeting held on 17/11 • Tony advised that within the response, parties should confirm a) that the incident is in their scope b) provide acceptance of the incident c) detail high level actions taken d) change the status from New to In Progress. DCC will provide written clarification to Xoserve around what is expected within the response time. • DCC advised that they fully expected push back from all parties around the SLAs. Xoserve will provide DCC with high level risks around the proposed SLA’s whilst continuing with an internal impact assessment. We all agreed that the SLAs do not stop the processes being developed and agreed. • DCC are currently working on creating scenarios for each priority level which will be shared with parties. This will also provide clarity around some of the terminology used within the descriptions. Awaiting further info from DCC. In the meantime, we have an internal session planned to map out the types of incidents that we think we could receive and align to priority level. | 26/02/21

## Slide 7: Key Programme Risks (3/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This is likely to become more evident as tests such as connected 'Day in Life processing of CSS' is undertaken. Leaving this risk to be monitored | 26/02/21
63929 |  | Data Migration | There is a risk that low level tasks will be difficult to plan for and track because of the new SI approach, whereby the CSSIP includes summary level activity with detailed tasks being added to GetOrganised leading to low/granular level activity not being baselined, and moving around without warning or notice. | Review with the SI | SI has confirmed that this risk is also being assessed internally. The current view from the SI is that planning will be undertaken in MSP with detailed activities tracked via GetOrganised. Awaiting confirmation of this approach. | 22/01/2021
63538 |  | Programme | There is a risk that all CRs (particularly those raised in the early phases of the Switching Programme), may not been incorporated into design and build by the relevant parties because these CRs might have not been incorporated correctly into requirements leading to additional efforts required to incorporate these CRs and testing through the relevant test phases (and as a subsequence delays to already delayed timelines. | Escalate to the SI to revisit the traceability exercise to identify any gaps (if any) and reflect the impacts of these CRs on the plan | Latest updates from DCC indicate that their initial assessment will be completed by end November. | 30/11/20

## Slide 8: Key Programme Risks (4/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62942 |  | Programme | There is a risk that Xoserve systems will be out of sync with CSS during British Summer Time because CSSP intend to use UTC within the CSS solution and both UK Link and Gemini are believed to use BST leading to incorrect reporting of switches and all relevant data from Xoserve systems during the period where BST is one hour ahead of UTC. | Ofgem have now made a decision that BST will continue to be used across the gas industry so a CR is expected requiring Landmark to make the necessary changes to CSS. | Risk to remain open until CR is tested. | 31/12/20
62695 |  | Service Management | There is a risk that Xoserve is not aware of changes made to the core Service Management processes because of DCC not providing updated process maps leading to re-work to review the revised DCC process maps and update ours accordingly. | Requested copies of the revised process maps to review | Continue to work with DCC to obtain responses to the questions raised against the process maps, The processes have gone through approval within Design Forum - need to understand how any changes will be communicated to parties. | 18/12/20
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | Within the November forum, DCC advised that CSS SMS will be single source of the truth. Reports will be built into the CSS SMS, these can be extracted by SP for further reporting. These will be tested as part of OT. Will continue to monitor this to ensure that we fully understand our responsibilities. | 31/12/20
63645 |  | Service Management | There is a risk that the Performance Assurance board will be formed to assure that that Switching Service is meeting market Participants expectation. There is a risk that Xoserve will be unable to provide the appropriate supporting information in the required timescales because DCC have not confirmed what Service Providers will need to feed into the board and it was discussed at the last Switching - Monthly Engagement Session that this board could ask for anything leading to the Performance Assurance Board not providing an accurate view to market participants and this having a reputational impact on Xoserve as the required information could not be provided in time. | XOS will push DCC for clarity within the monthly forums & 1:1 sessions | Sarah Jones who represents the REC provided a link to the PAB within the monthly forum last week. An internal session will be set up to review. | 31/12/20

## Slide 9
High Level Plan

## Slide 10: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Additional Onward Dependencies for MAD Log | CR-D053 | £0.00 | 18/12/2020 | Pending PIA
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | £0.00 | 18/12/2020 | Pending PIA
Amendments to the Data Cleansing Catalogue | CR-D055 | £0.00 | 18/12/2020 | Pending PIA

## Slide 11: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 | £0.00 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | £61,000.00 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £3,500.00 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | £0.00 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 | £0.00 |  | Not Received
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 | £0.00 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | £0.00 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | £0.00 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | £0.00 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | £0.00 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | £0.00 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | £0.00 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | £0.00 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | £0.00 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | £0.00 | 13/11/2020 | On Hold
CSS Environments for Faster Switching Enduring Service | CR-D050 | £0.00 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | £0.00 | 30/11/2020 | Complete - No Xoserve Impact
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | £0.00 | 05/12/2020 | Complete - No Xoserve Impact

## Slide 12
Chart: 
| 43585 | 43616 | 43646 | 43677 | 43708 | 43738 | 43769 | 43799 | 43830 | 43861 | 43890 | 43921 | 43951 | 43982 | 44012 | 44043 | 44074 | 44104 | 44135 | 44165 | 44196 | 44227 | 44255 | 44286 | 44316 | 44347 | 44377 | 44408 | 44439 | 44469 | 44500 | 44530 | 44561 | 44592 | 44620 | 44651
Monthly FORECAST (Cumulative) | 363976.72 | 683029.7765 | 1009036.499 | 1468927.8937 | 1881004.6077 | 2628016.319 | 3342083.1863 | 4458203.008 | 5354404.1687 | 6043381.8373 | 7142886.031 | 8975402.7507 | 10111305.124 | 11388987.0723 | 13038342.6157 | 14439812.029 | 15882176.8173 | 17060919.8833 | 18317773.5297 | 18994939.193 | 19993804.6864 | 21222509.713 | 22376161.371 | 23762628.0644 | 24961663.2577 | 26462568.4044 | 27653588.211 | 28954984.2177 | 30143533.4244 | 30988952.631 | 31927708.3677 | 33179072.8444 | 34087558.581 | 34909035.3177 | 35862717.0544 | 36815905.791
Monthly BUDGET (Cumulative) | 489844.68 | 1174749.2 | 1918322.31 | 2859329.26 | 3600336.21 | 4373413.71 | 5301107.71 | 6054522.36 | 6844783.41 | 7587690.86 | 8469886.81 | 10016454.16 | 10772088.89 | 11466104.1 | 12171330.71 | 14216755.3 | 15951497.88 | 17098244.84 | 18223938.97 | 19242195.57 | 20253660.21 | 21199102.25 | 22074558.18 | 23123177.56 | 24961663.2577 | 26462568.4044 | 27653588.211 | 28954984.2177 | 30143533.4244 | 30988952.631 | 31927708.3677 | 33179072.8444 | 34087558.581 | 34909035.3177 | 35862717.0544 | 36815905.791
Monthly ACTUALS (Cumulative) | 228433.92 | 548079.88 | 1260281.72 | 2160027.93 | 2928145.54 | 3938750.3 | 4855898.385 | 5889989.03 | 6410840.7 | 6911519.115 | 7785494.945 | 9133695.43 | 10292453.24 | 11335516.495 | 13355830.295 | 14918449.525 | 16362882.755 | 17199816.6283 | 18494832.1383 | 19218128.3383
Total Approved Budget | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000