## Slide 1: Change Management Committee
10th February 2021

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: 2.1 – DSC Change Budget 20/21 (Financial Year To Date) & 21/22

## Slide 4: Budget v Spend BP20/21 Financial Year To Date
Total available funds have decreased by £78k as a result of multiple changes moving through the lifecycle (see 2nd tab in embedded s/s for details)
Position as of Jan-21
Chart: Constituency Budget v Spend BP20/21 FYTD
| NTS £ | GDN£ | IGT £ | Shipper £
Change Budget 20/21 Pipeline | 1200 | 497912.6567 | 75484.9336 | 1138295.2665
20/21 Budget | 48000 | 600000 | 9000 | 2343000
Chart: Total Budget v Spend BP20/21 FYTD
| Total £
Change Budget 20/21 Pipeline | 1712892.8568
20/21 Budget | 3000000
Chart: Varience in avilable funds
| NTS £ | GDN£ | IGT £ | Shipper £
Varience in avilable funds since last report | 0 | -41892.133 | -5004.6814 | -53685

## Slide 5: Budget v Forecasted Spend BP21/22 (as of Feb-21)
Chart: Total Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 2589600 | 500000 | 100000 | 200000 | 200000
Spend | 1113485 | 0 | 0 | 0 | 0

## Slide 6: Budget v Forecasted Spend BP21/22 Per Constituency
Chart: Shipper Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 1495000 | 288654.6185 | 57730.9237 | 115461.8474 | 115461.8474
Spend | 836385 | 0 | 0 | 0 | 0
Chart: DN Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 900000 | 173772.0111 | 34754.4022 | 69508.8044 | 69508.8044
Spend | 258100 | 0 | 0 | 0 | 0
Chart: NTS Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 54600 | 10542.1687 | 2108.4337 | 4216.8675 | 4216.8675
Spend | 0 | 0 | 0 | 0 | 0
Chart: IGT Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 140000 | 27031.2017 | 5406.2403 | 10812.4807 | 10812.4807
Spend | 19000 | 0 | 0 | 0 | 0

## Slide 7: 2.2 – Change Pipeline

## Slide 8: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
Chart: XRNs Per Category
| Pre-capture | Capture | Ready for delivery | Standalone | Nov-20 | Jun-21 | Nov-21 | MiR8 | MiR9 | MiR10 | MiR11 | PAC 21/22 | Xo Change Fund
XRNs | 15 | 26 | 2 | 8 | 4 | 1 | 6 | 3 | 2 | 0 | 0 | 0 | 0
* Pre-capture may contain changes that won’t require delivery / funding

## Slide 9: 2020-2022 DSC Change / MiR Pipeline
Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
2020 | 2021 | 2022
Approval on track
Approval at risk
Governance Approvals Key
Approved
Nov 21
Jun 21
MiR 10
MiR 9
Nov 20
Xo CF
Scope Approved – August ChMC
MiR
11
Scope / EQR
Scope
Scope
EQR
CP / BER
BER
CCR
CCR
PAC
CP / BER
Scope
CCR
CCR
Stand Alone
XRNs
4645
5164
BER
CCR
CCR
CCR
CCR
MiR 8
CCR
XRNs
5167
XRNs
5120
XRNs
5183
XRNs
5146
XRNs
5206
5237
Project RAG Key
Not Started
On Track
Warning
Plan At Risk
Complete
CSSC
Non-DSC / MiR
Retro
Activity
Potential Activity
XRNs
4876

## Slide 10: Section 3: Project mercury update
Verbal Update

## Slide 11: Section 4: Capture

## Slide 12: 4.1 New Change Proposals – Initial Review
XRN / Title | Voting |  |  |  | DSC Service Area
 | Shipper | DNO | IGT | NTS | 
XRN5298 H100 Fife Project - Phase 1 (Initial Assessment) | X | X |  |  | Service Area 1 Manage supply point registration
XRN5299 Future Billing Methodology (analysis only) |  | X |  | X | N/A
XRN5309 FSG: Automating the FSR (Mod0565) process |  | X | X |  | Service Area 7 NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices
XRN5318 Assessing Supplier MPID Reassignment (analysis only) | X | X | X | X | N/A
XRN5319 Assessing MPID Reassignment for All Party Types (analysis only) | X | X | X | X | N/A

## Slide 13: XRN5298 H100 Fife Project - Phase 1 (Initial Assessment)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | 
Voting Parties
DSC Service Area: | Service Area 1: Manage supply point registration
Link to Change Proposal | Link to CP
Change Details
Problem Statement
SGN’s strategic ambition towards Net Zero includes a network innovation, ‘proof of concept’, project; H100 Fife. This project will see SGN injecting 100% hydrogen into a new, purpose-built network which will be located in parallel to the existing natural gas network. Initially, 300 existing domestic consumers will be invited to migrate their supplies from natural gas to hydrogen for their energy requirements.
Sponsor Representative | SGN
Change Description
Phase 1: Xoserve to undertake an initial assessment to develop high-level solution options and a delivery project plan that SGN will present to Ofgem in March 2021. Xoserve should consider the impacts on, but not be limited to: • Shippers’ daily Energy Balancing (including NDM forecasting/allocation) • Meter Supply Point; AQs, SOQs and reads • Invoicing; settlement & reconciliation • LDZ Shrinkage, CV shrinkage and UIG • Faster Switching and RGMA • Implications on DN LDZ daily CV calculation (FWACV); specifically, LDZ CV capping (Thermal Energy Regulations) • Impacts of any solution on customer end gas bills. [tbc] • Potential solution might include new MPRN correction factors Phase 2: Xoserve will undertake the detailed assessment, design and development of an agreed solution design. Xoserve will implement the solution to support SGN’s H100 Fife during Q2 2023
Change Type | Regulatory
Priority Score | High

## Slide 14: XRN5299 Future Billing Methodology (analysis only)
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | 
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Cadent’s continued work on its Future Billing Methodology (FBM) Project now requires Xoserve to undertake a re-assessment of the further defined conceptual requirements. The options require further assessment to determine the best approach and measures to unlock potential to de-carbonise heat using existing gas networks.
Sponsor Representative | Cadent
Change Description
As per the attached Cadent document: CADENT NIC04 - FBM CHANGES FOR XOSERVE Note: Xoserve has previously provided XRN4323 (July 2017) that provided an initial high-level cost estimate. It might be beneficial to use this as a basis for XRN5299.
Change Type | Regulatory
Priority Score | High

## Slide 15: XRN5309 FSG: Automating the FSR (Mod0565) process
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | X
Voting Parties
DSC Service Area: | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices
Link to Change Proposal | Link to CP
Change Details
Problem Statement
SGN has raised this change proposal on behalf of all Gas Distribution Networks. The revised RIIO-2 Failure to Supply Gas (FSG) arrangements will reduce the timescale for the FSG process e.g. compensation payments from fortnightly to weekly. As a consequence, automation of the FSR manual workaround is required. Note: This change was originally in the scope of XRN5080 (within Option 2) however, due to delivery time constraints, ChMC agreed (11th Nov ’20) to descope this element and, that a new change proposal should be raised. The XRN5080 HLSO may be used as a basis for this Change Proposal.
Sponsor Representative | Scotland and Southern Gas Networks (SGN)
Change Description
Automate the FSR file (Mod0565) manual workaround, including the reporting (for output to DNs) for those MPRNs > 73,200 kWh i.e. on transfer from domestic to I&C FSG compensation payment threshold
Change Type | Non Regulatory
Priority Score | Medium

## Slide 16: XRN5318 Assessing Supplier MPID Reassignment (analysis only)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | X
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Currently the allocation of Market Participant Identity (MPID) short codes for Suppliers are linked to the Company Number issued and associated to the Organisation the Supply Licence granted. In gas, once a Supplier is allocated an MPID under a particular Company Number it cannot be changed between different Supply Licences which have been granted, so, in the event of a Supplier of Last Resort (SoLR) or company acquisition the short code cannot be simply ‘lifted and shifted’ but instead flows to refresh the IDs have to be issued or the update isn’t allowed to be completed and new unique ID is created.
Sponsor Representative | E.ON
Change Description
This XRN is being raised to explore the impacts to all CDSP systems including, but not limited to, UK Link, Gemini, DES, CMS and DDP. The investigation is to assess the implications and approximate costs to replicate the MPID reassignment principal in electricity (although not an exact process replica, it should be still designed to best suit gas). Please see the CP for full problem statement and description
Change Type | Non Regulatory
Priority Score | Medium

## Slide 17: XRN5319 Assessing MPID Reassignment for All Party Types (analysis only)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | X
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Currently the allocation of Market Participant Identity (MPID) short codes for all party types such as Suppliers, Shippers, are linked to the Company Number issued and associated to the Organisation the Licence granted. In gas, once the unique 3 digit short code is allocated to an MPID under a particular Company Number it cannot be changed between different entities which have been granted licences or another party type, such as Meter Asset Provider (MAP) or Meter Asset Manager (MAM). In the event of a Supplier of Last Resort (SoLR) or company acquisition the short code cannot be simply ‘lifted and shifted’ but instead flows to refresh the IDs have to be issued or mass movements of portfolios or data refreshes have to occur, adding cost and effort to the industry for something which could be a lot simpler and more efficient if the ‘lift and shift’ approach was able to be utilised.
Sponsor Representative | E.ON
Change Description
This XRN is being raised to explore the impacts to all CDSP systems including, but not limited to, UK Link, Gemini, DES, CMS and DDP. The investigation is to assess the implications and approximate costs to replicate the MPID reassignment principal in electricity (although not an exact process replica, it should be still designed to best suit gas). Please see the CP for full problem statement and description
Change Type | Non Regulatory
Priority Score | Medium

## Slide 18: 4.2 Change Proposals – Post Solution Review for Approval
XRN5285 COVID-19 Capacity Retention Process (Mod730V)

## Slide 19: XRN5285 COVID-19 Capacity Retention Process (Mod730V)
Proposed Release Link to Change Proposal Change Pak Comm Ref Voting Funding | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: Adhoc Link to CP Link to Change Pack ref: 2755.4 - RT - JR Voting: NTS, Shipper, DNO High level Solution cost: Option 1: 0 – 7K Service Area: Service Area 7 NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices Funding: Service Area 7 is split 17% NTS & 83% DNO | Option 1 1 solution option proposed, as is expected to be required in the short-term only. | NGN | X |  |  | NGN supports the solution option and if the MOD is approved we would like to see this as a separate line and not including in the current capacity charge.

## Slide 20: 4.3 Change Proposal Updates
XRN5218 CDSP provision of Class 1 read service (Mod 0710)

## Slide 21
Please Note: The implementation dates for each of the Capabilities are subject to change following completion of the respective Capability design activities

## Slide 22: section 5. Design & Delivery

## Slide 23: Design Change Pack
XRN5038 Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD 0691)
XRN5080 Failure to Supply Gas (FSG/GSOP1) – System Changes
XRN5135 DNO and NTS Invoices to Shippers and DNs VAT compliance

## Slide 24
XRN5038 Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD 0691)
Functional Changes |  |  |  |  | 
Change Pack ref: 2755.1 - RT – JR Release: Adhoc (Date TBC) Voting: Shipper, DNO, IGT Funding: 100% Shipper Service Area 1: Manage Supply Point Registration | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Defer | Reject | 
 | SSE | X |  |  | We agree that Xoserve's proposed process is appropriate to carry out reclassification of Supply Meter Points when the relevant criteria are met.

## Slide 25
XRN5080 Failure to Supply Gas (FSG/GSOP1) – System Changes
Functional Changes |  |  |  |  | 
Change Pack ref: 2755.2 - RT – JR Release: MiR9 Voting: DNO & Shipper Funding: 100% DNO (reapportioned) Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Defer | Reject | 
 | NGN | X |  |  | Our internal team has concerns around the GSOS12 payments now being applied at D+8 when this previously happened at D+10, they have now lost 2 days to gather data. I am aware that this is going to be discussed at the next DN Constituency meeting to address any concerns.
 | SSE | X |  |  | We agree that the changes to facilitate the amended DN GSOP compensation timescales are appropriate.

## Slide 26
XRN5135 DNO and NTS Invoices to Shippers and DNs VAT compliance
Functional Changes |  |  |  |  | 
Change Pack ref: 2755.3 - RT – JR Release: MiR9 Voting: NTS, Shipper, DNO Funding: Service Area 7 is split 17% NTS & 83% DNO Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Defer | Reject | 
 | NGN | X |  |  | NGN supports the solution option and approves of the change.
 | SSE | X |  |  | We agree that the DNO and NTS invoice VAT compliance changes are appropriate.

## Slide 27: Standalone Change Documents for Approval (BER, CCR, EQR)

## Slide 28: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5135 DNO and NTS Invoices to Shippers and DNs VAT compliance
  Voting NTS, DNO
BER for XRN4876 Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting
  Voting Shipper

## Slide 29: June 2020 Major Release

## Slide 30: XRN4996 - June 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4850 SMS/Email Notification: The new service is being utilised by Networks however usage is limited due to the limited amount of data held in UK Link. Currently there is circa 8.2 million meter points in UK Link and the team are monitoring usage. Please contact Max Pemberton at customerexperience@xoserve.com prior to submitting any contact details. Scope Variations: XRN4850 - Report automation integration is currently in progress with the DDP team with a planned Go Live of mid-February. Manual reporting will be available in the interim should the service be used. XRN4850 UK Link Portal changes – to allow special characters, increase character limits in text and email and display character number count is in progress for delivery mid-February. Project Closedown: Following completion of Post Implementation Support and approval of the Change Completion Report project closedown is in progress. |  |  | 
Risks and Issues | Risk – DN's/IGT's do not use the new SMS/Email broadcast functionality during Post Implementation Support, because of the limited number of customer contact details uploaded to UK Link or networks do not need to send broadcasts during this period. To mitigate, Networks to confirm requirements for the report details to provide % saturation of sites in each LDZ which has BRO data populated. |  |  | 
Cost | Costs have been finalised in the CCR which has been approved by Change Management |  |  | 
Resources | No resource issues identified for the remainder of the project |  |  | 
Updates as of the 26th January 2021

## Slide 31: November 2020 Major Release

## Slide 32: XRN5110 - Nov 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS All 116 instances of first usage have been captured and assured 6 defects and 19 incidents have been fixed. PIS is complete for XRN4871b and XRN5014 The following change requests have been identified and approved for: XRN4897/99 Daily Cleanse – The job dependency has been changed requiring PIS extension to 08/02/21.The extension is to monitor daily cleanse running in a period of high volume processing. The daily cleanse functionality is working as expected XRN4801 Additional Information in DES - Issue identified with active read indicator displaying incorrectly for a small volume of OPNX reads. Fix to be implemented 13/02/21 Change request has been raised and approved to fix the XRN4897/99 historical cleanse job. Data was being incorrectly deleted, there was no customer impact and the data was quickly restored. The change request covers the scenarios that were missed and resulted in the deletion. Expected implementation of the change is end of March 2021 followed by 10 weeks PIS to run the historical cleanse job. Cost of change is £54k and additional funds have been approved by the Change Management Committee 29/01/21, to cover the £34k shortfall Return to Green N/A |  |  | 
Risks and Issues | Issue: PIS has been extend for XRN4897/99 Daily Cleanse and XRN4801 Additional Info in DES Issue: XRN4897/99 Historical Cleanse Change Request needs to be completed to exit PIS Risk: XRN4897/99 delivery verifying 100% GDPR compliance – PIS plans in place to assure – risk probability being understood. Return to Green all issues is that PIS is completed for all changes |  |  | 
Cost | BER approved - 10/06/20 Full Business Case approved XEC – 23/06/20 Additional funds of £34k have been approved for the XRN4897/99 Historical Cleanse change request |  |  | 
Resources | SME & Tech Ops resources approved for XRN4897/99, Historical Cleanse, XRN4897/99 Daily Cleanse PIS extension and XRN4801 PIS extension Return to Green N/A |  |  | 
Updates as of the 01st February2020

## Slide 33: XRN5110 - Nov 20 Delivery Timeline & Progress
Updates as of the 01st February2020

## Slide 34: June 2021 Major Release

## Slide 35: XRN5253 - June 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | BER Approved at ChMC on 9th December, as confirmed in January a revised BER will be issued that includes AUGE set up costs previously discussed as part of HLSO. This was unfortunately omitted from original BER version. The intention is to issue this for approval in March. Build execution completed to plan in January System Testing commenced to plan in January User Acceptance Testing (UAT) preparation in progress Implementation Approach under final review Post Implementation Support (PIS) period under discussion with Operation teams to ensure it is sufficient and covers what is required |  |  | 
Risks and Issues | Issue: The project is progressing 2 months behind plan leading to overlap between multiple phases and risk that approvals may not fall in order. It also reduces overall delivery timescales. Mitigation: Detailed Plan up to end of Design to be completed as part of Start Up to ensure tight project control and critical path management. Following completion of overall Design phase (inclusive of Implementation Approach) this issue will be closed. |  |  | 
Cost | BER Approved at ChMC in December, revised BER to be issued in March to include AUGE set up costs incorrectly omitted from previous BER Cost RAG status will return to green on approval of updated BER inclusive of AUGE costs. |  |  | 
Resources | Resource Forecasts and Plans have been defined at a high level for future stages. Resource RAG Status will return to green on confirmation of resources required to support all testing phases. |  |  | 
Updated as of 27th January 2021

## Slide 36: XRN5253 – June 21 High-Level Plan
Updated as of 27th January 2021
Note: Final confirmation of go-live date and PIS period still pending

## Slide 37: November 2021 Major Release

## Slide 38: XRN5289 - November 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Detailed Functional Requirements have been approved Non Functional Requirements are currently being reviewed High Level Design is being reviewed and approved Design workshop plan is approved to start on the 1st February Currently planning CSSC/CSS impact assessment timeline and content |  |  | 
Risks and Issues | Not a full 6 months for Change Pack and delivery – proposing eChMC on the 5th May need agreement XRN5142 – Unknown plans from DCC on their plan of delivery and design Return to Green Gain agreement from ChMC on eChMC Set up regular touch points with DCC to understand their plan and design |  |  | 
Cost | EQR approved by ChMC on the 13th January |  |  | 
Resources | Resource Forecasts and Plans have been defined at a high level and approved until initiation this includes detailed requirements SME resource has been provided for design, approach for technical SME resource to support design has been agreed |  |  | 
Updated as of 27th January 2021

## Slide 39: XRN5289 – November 21 Release High-Level Plan
Updated as of 27th January 2021

## Slide 40: XRN5294 - Minor Release Drop 9 Update

## Slide 41: XRN5294 - Minor Release Drop 9 - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 2 changes for Minor Release Drop 9 to be implemented. The implementation date is planned for 20th March 21: XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​ XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance Acceptance Testing in progress, slightly behind plan due to resource availability. Resources available next week to cover any delayed testing assurance Minor Release Drop 8 defect fixed and tested, this can continue with implementation on 5th February 21 as per plan, on track |  |  | 
Risks and Issues | Issue due to lack of resource availability for testing assurance from w/c 18/01/21 , this is to be mitigated by increased availability of resources from w/c 01/02/21 |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 
Updated 27th January 2021

## Slide 42: Gemini Horizon Plan

## Slide 43: Section 6: Non-DSC Change Budget Impacting Programmes

## Slide 44: 6.1 CSSC Programme Dashboard
February 2021

## Slide 45
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme is now at Amber-Green status. All external test phases and Xoserve’s internal deliveries continue to track to plan | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Programme Re-plan: Following the Ogem programme re-baseline, caveated with the actions to mitigate concerns that Xoserve raised. Main actions have been closed, hence this not be reported on, going forward. Costs: Costs continue to be monitored closely Missing design changes DCC and SI undertook a detailed review and have confirmed that all changes have either been included with physical interface design or is in-flight as a CR. This closes out our concern. External SIT: Testing is continiung to plan with regression and Witness Testing underway currently External NFR SIT: Testing continues to plan with all Peak of Peak testing concluding successfully Internal Testing: UAT Assurance is currently ongoing with minimal defects being both via UAT testing & UAT assurance carried out by our SMEs. SIT integration continues for Programme CR deliveries. Defect rate continues to be low. Transition: Internal planning activities continue alongside engagement with the SI Data Migration: DM NF continues with the Programme. There is a potential of a slight delay (at the central level), however the SI are working to try and contain the delay as much as possible in order to protect the baselined completion dates. UEPT Data has been transferred to Landmark to plan and REL extract has commenced. |  |  |  | DMT NFR: Continue test execution External SIT: Continue External SIT support External NFR: Continue test execution Internal Test: Continue SIT & UAT assurance DES:& Secondary APIs Continue development and system test activities. Transition: Continue Transition planning
Programme Update

## Slide 46: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall green. Internal & External SIT support in progress. Resource constraints have been highlighted and mitigation actions are in progress to manage delivery timelines.
 |  | Testing | The overall status remains Green. External SIT support in progress, no Xoserve defects are open at this point. Planning underway for all upcoming test phases such as UEPT, E2E, OT
 |  | Service Management | Following discussions with Ofgem and DCC via the Switching Programme Design Forum, Xoserve will be submitting feedback regarding Service Management SLAs by 29/01. Preparations also underway to submit our response to the Service Design assurance activity in February.
 |  | Batch | The overall status is green, with testing support underway.
 |  | Gemini | The overall status is green. Planning underway to undertake a connected Gas Day testing with UK Link.
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess and deliver Switching Programme changes raised through the last few months whilst supporting test phases.

## Slide 47: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC consultation continues with Xoserve actively engaged in relevant RDUG meetings as well as reviewing REC schedules
 |  | Data Migration & Provision | DM NF continues with the Programme. There is a potential of a slight delay (at the central level), however the SI are working to try and contain the delay as much as possible in order to protect the baselined completion dates. UEPT Data has been transferred to Landmark to plan and REL extract has commenced.
 |  | Market Trials | The CR to remove Market Trials milestones from the Switching Programme Plan has been raised and is currently undergoing industry-wide impact assessments
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan.

## Slide 48: Key Programme Risks (1/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62741 |  | Programme | There is a risk that SIT NFR testing will be deemed invalid if carried out as currently planned because SIT Functional would not have reached the necessary level of code stability for Non functional testing to be carried out leading to additional costs related to resources and environments required to support further cycles of NFR testing once a stable code level has been achieved. High volumes of defects are currently being found in SIT which in turn is impacting progression and therefore delays in completing the SIT cycles required to establish a suitable level of code stability. The current timelines still plan for NFR testing to be carried out prior to the completion of sufficient functional SIT required to establish a stable code set. | Escalate to the SI via all established forums to instigate a near term plan review to ensure these phases are re-planned appropriately. | This risk is still relevant and will continue to be monitored until SIT is complete.. | 03/03/21

## Slide 49: Key Programme Risks (2/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This is likely to become more evident as tests such as connected 'Day in Life processing of CSS' is undertaken. Leaving this risk to be monitored | 27/02/21
61894 |  | Service Management | There is a risk that the CSS proposed SLAs do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | Update from meeting held on 17/11 • Tony advised that within the response, parties should confirm a) that the incident is in their scope b) provide acceptance of the incident c) detail high level actions taken d) change the status from New to In Progress. DCC will provide written clarification to Xoserve around what is expected within the response time. • DCC advised that they fully expected push back from all parties around the SLAs. Xoserve will provide DCC with high level risks around the proposed SLA’s whilst continuing with an internal impact assessment. We all agreed that the SLAs do not stop the processes being developed and agreed. • DCC are currently working on creating scenarios for each priority level which will be shared with parties. This will also provide clarity around some of the terminology used within the descriptions. Awaiting further info from DCC. In the meantime, we have an internal session planned to map out the types of incidents that we think we could receive and align to priority level. | 26/02/21

## Slide 50: Key Programme Risks (3/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This is likely to become more evident as tests such as connected 'Day in Life processing of CSS' is undertaken. Leaving this risk to be monitored | 26/02/21
64158 |  | Programme | There is a risk that that the Operational Choreography CR that is in progress may be approved because it might be deemed necessary by the central programme leading to further plan considerations (at both the central and individual PUI's plans) and cost implications to Xoserve | This has been raised with SI/DCC & Ofgem. This is being tracked collectively via the MAD log actions. Should this CR be approved, this action will be addressed with central bodies | This CR has now been to CAT and will be with PUIs for a detailed impact assessment | 26/02/21
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Lankmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | This has been discussed at SI Transition Group on 05/01. Ofgem is aware and tracking this risk | 30/04/21
64378 |  | Data Migration | There is a risk that DM NF may not complete on time because of cycle 1 running behind schedule and Additional CR functional testing to be completed at the start of the cycle (previously unscheduled) leading to a delay in completing DM NF and possible impact to DM Live rehearsal | Discuss with SI project and programme teams | Awaiting recover plan for cycle 1 and schedule of CR testing | 26/02/21

## Slide 51
High Level Plan

## Slide 52: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
MAD Log Changes for UIT Environment Verification | CR-D057 |  | 25/01/2021 | Pending PIA
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 |  | 25/01/2021 | Pending PIA
Changes to Support Energy Company Data] | CR-D059 |  | 25/01/2021 | Pending PIA
Operational Choreography Detection 0.5 | CR-D060 |  | 25/01/2021 | Pending PIA
Operational Choreography Rectification 0.3 | CR-D061 |  | 25/01/2021 | Pending PIA
Removal of Transition Stage 1 Delta files from the Data Migration Solution | CR-D062 |  | 27/01/2021 | Pending PIA

## Slide 53: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 | £0.00 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | £61,000.00 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £3,500.00 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | £0.00 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 | £0.00 |  | Not Received
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 | £0.00 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | £0.00 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | £0.00 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | £0.00 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | £0.00 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | £0.00 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | £0.00 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | £0.00 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | £0.00 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | £0.00 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 | £0.00 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | £0.00 | 30/11/2020 | Complete - No Xoserve Impact
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | £0.00 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact

## Slide 54: 6.2 IX Refresh
Customer Update
February 2021

## Slide 55: IX Refresh Customer Update
The project is currently experiencing limited impact regarding the current COVID-19 lockdown
The project end date is February 2021. Our current run rate is tracking a February completion
98% of all migrations have been completed
  4 IX sites remaining
Work has commenced to decommission legacy IX equipment
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com

## Slide 57: 6.3 CMS Rebuild Update
February Updates
Jo Williams

## Slide 58: CMS Rebuild - Progress to date
Summary of progress to date
CMS is a dated system which is coming to end of life support, rather than a lift and shift of current processes the project team wanted to understand the following from the actual users of CMS perspective: What are their current processes and activities What are their current pain points What would their ideal version of the process be 18 External Initial Requirements Workshops have been held to date 483 requirements captured, this figure may include duplication Common themes include: Customer Effort System functionality Visibility All Workshop outputs will be published here: https://www.xoserve.com/systems/contact-management-service/contact-management-service-cms-rebuild-project/ Potential Suppliers are being engaged to understand high level requirements to obtain figures and timescales for High Level Solution Options Internal recommended "to be" workshops have commenced to understand what systems the solution will need to integrate with
Key Milestones | Due
Initial Workshops Completed | 22/01/2021
To Be Workshops Commence | 08/02/2021
HLSO – Target Date | March
Next Steps
Refine the requirements which will be: Remove duplication Add our understanding to the requirements and ratify with customers Understand areas of conflict in requirements Continue internal and schedule external recommended “To Be" workshops Identify possible solutions and seek approval on solution and design from: CoMC ChMC DSG

## Slide 59: CMS Rebuild Next Steps
Dec | Jan | Feb | March
Hints & Tips Refreshers published
Commentary
Workshops to date have recieved great feedback to date and the findings are consitent accross the board
Progress published – Website, CoMC and DSG
External “To Be” Solution Options
Painpoint & Req Workshops
Completed
On Track
At Risk
It is currently unclear if there is any misalignment on the To be solutions across the processes and these may require several iterations to come to an agreed approach.
Overall Agreement of “To Be” processes
Internal “To Be” Solution Options

## Slide 60: Section 7: Any Other Business

## Slide 61: February KVI Survey
As part of our Key Value Indicator (KVI) Framework we would like to request your feedback on our Change Management function. You can give your feedback through this survey, which will only take a few minutes of your time to complete.
Your comments will remain anonymous unless you choose to include your contact details. As with previous Surveys, we appreciate being able to contact those who have left their contact details to explore feedback in further detail and discuss any actions we can take.
The scope of your feedback should include UK Link scheduled Releases, UK Link Minor Releases, Minor Enhancements, and Gemini Releases between 1st October 2020 – 31st January 2021.

## Slide 62: APPENDIX

## Slide 63: Portfolio POAP

## Slide 64: June 2020 Major Release

## Slide 65: XRN4996 - June 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4850 SMS/Email Notification: The new service is being utilised by Networks however usage is limited due to the limited amount of data held in UK Link. Currently there is circa 8.2 million meter points in UK Link and the team are monitoring usage. Please contact Max Pemberton at customerexperience@xoserve.com prior to submitting any contact details. Scope Variations: XRN4850 - Report automation integration is currently in progress with the DDP team with a planned Go Live of mid-February. Manual reporting will be available in the interim should the service be used. XRN4850 UK Link Portal changes – to allow special characters, increase character limits in text and email and display character number count is in progress for delivery mid-February. Project Closedown: Following completion of Post Implementation Support and approval of the Change Completion Report project closedown is in progress. |  |  | 
Risks and Issues | Risk – DN's/IGT's do not use the new SMS/Email broadcast functionality during Post Implementation Support, because of the limited number of customer contact details uploaded to UK Link or networks do not need to send broadcasts during this period. To mitigate, Networks to confirm requirements for the report details to provide % saturation of sites in each LDZ which has BRO data populated. |  |  | 
Cost | Costs have been finalised in the CCR which has been approved by Change Management |  |  | 
Resources | No resource issues identified for the remainder of the project |  |  | 
Updates as of the 26th January 2021

## Slide 66: XRN4850 – SMS/Email Broadcast Notification Timeline
Project closedown is in progress.
Daily/Monthly Network Usage report and Portal CR delivery in progress, delivery mechanism confirmed as DDP
Updates as of the 26th January 2021
TODAY

## Slide 67: XRN4996 - June 20 Release Summary
June 20 Release consists of 7 changes, Implementation was completed for June 20:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 - Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters (UKLink file formats, new service to follow)
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining change requests. Descoped at ChMC on 8th January 2020
** Descoped at eChMC on 22nd November 2019
*** Added to scope (revised scope from original)
Updates as of the 26th January 2021

## Slide 68: November 2020 Major Release

## Slide 69: XRN5110 - Nov 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS All 116 instances of first usage have been captured and assured 6 defects and 19 incidents have been fixed. PIS is complete for XRN4871b and XRN5014 The following change requests have been identified and approved for: XRN4897/99 Daily Cleanse – The job dependency has been changed requiring PIS extension to 08/02/21.The extension is to monitor daily cleanse running in a period of high volume processing. The daily cleanse functionality is working as expected XRN4801 Additional Information in DES - Issue identified with active read indicator displaying incorrectly for a small volume of OPNX reads. Fix to be implemented 13/02/21 Change request has been raised and approved to fix the XRN4897/99 historical cleanse job. Data was being incorrectly deleted, there was no customer impact and the data was quickly restored. The change request covers the scenarios that were missed and resulted in the deletion. Expected implementation of the change is end of March 2021 followed by 10 weeks PIS to run the historical cleanse job. Cost of change is £54k and additional funds have been approved by the Change Management Committee 29/01/21, to cover the £34k shortfall Return to Green N/A |  |  | 
Risks and Issues | Issue: PIS has been extend for XRN4897/99 Daily Cleanse and XRN4801 Additional Info in DES Issue: XRN4897/99 Historical Cleanse Change Request needs to be completed to exit PIS Risk: XRN4897/99 delivery verifying 100% GDPR compliance – PIS plans in place to assure – risk probability being understood. Return to Green all issues is that PIS is completed for all changes |  |  | 
Cost | BER approved - 10/06/20 Full Business Case approved XEC – 23/06/20 Additional funds of £34k have been approved for the XRN4897/99 Historical Cleanse change request |  |  | 
Resources | SME & Tech Ops resources approved for XRN4897/99, Historical Cleanse, XRN4897/99 Daily Cleanse PIS extension and XRN4801 PIS extension Return to Green N/A |  |  | 
Updates as of the 01st February2020

## Slide 70: XRN5110 - Nov 20 Delivery Timeline & Progress
Updates as of the 01st February2020

## Slide 71
XRN5110 - Nov 20 PIS First Usage and Defects
Updates as of the 01st February2020

## Slide 72
XRN5110 - Nov 20 PIS Defect Details
Updates as of the 01st February2020

## Slide 73
In Scope
  XRN 4897 - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event
  XRN 4899 - Treatment of Priority Service Register Data and Contact Details on Change of Supplier Event
  XRN 4801 - Additional Information in DES
  XRN 4871b - Rachet Regime Changes
  XRN 5014 - Facilitating HyDeploy2 Live Pilot
Descoped changes
  XRN 4931 - Submission of a Space in Mandatory Data on Multiple SPA Files
  XRN 4941 - MOD 692 – Auto Updates to Read Frequency
  XRN 4992 - Supplier of Last Resort Charge Types
To be delivered by CSSC
  XRN 4780c - MAP ID
XRN5110 November 20 Release consists of 5 changes. Implementation is planned for November 2020
XRN5110 - Nov 20 Scope

## Slide 74: June 2021 Major Release

## Slide 75: XRN5253 - June 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | BER Approved at ChMC on 9th December, as confirmed in January a revised BER will be issued that includes AUGE set up costs previously discussed as part of HLSO. This was unfortunately omitted from original BER version. The intention is to issue this for approval in March. Build execution completed to plan in January System Testing commenced to plan in January User Acceptance Testing (UAT) preparation in progress Implementation Approach under final review Post Implementation Support (PIS) period under discussion with Operation teams to ensure it is sufficient and covers what is required |  |  | 
Risks and Issues | Issue: The project is progressing 2 months behind plan leading to overlap between multiple phases and risk that approvals may not fall in order. It also reduces overall delivery timescales. Mitigation: Detailed Plan up to end of Design to be completed as part of Start Up to ensure tight project control and critical path management. Following completion of overall Design phase (inclusive of Implementation Approach) this issue will be closed. |  |  | 
Cost | BER Approved at ChMC in December, revised BER to be issued in March to include AUGE set up costs incorrectly omitted from previous BER Cost RAG status will return to green on approval of updated BER inclusive of AUGE costs. |  |  | 
Resources | Resource Forecasts and Plans have been defined at a high level for future stages. Resource RAG Status will return to green on confirmation of resources required to support all testing phases. |  |  | 
Updated as of 27th January 2021

## Slide 76: XRN5253 – June 21 High-Level Plan
Updated as of 27th January 2021
Note: Final confirmation of go-live date and PIS period still pending

## Slide 77: XRN5253 - June 21 Release Summary
In Scope
XRN5093 - MOD0711 – Update of AUG Table to reflect new EUC bands
De-Scoped at Extraordinary Change Management Committee on 26th October 2020
XRN4992 - MOD0687 – Creation of new charge to recover last resort supply payments
De-Scoped at Change Management Committee on 11th November 2020
XRN4941 - MOD0692 - Auto updates to meter read frequency
June 21 Release now consists of 1 change.
Updated as of 27th January 2021

## Slide 78: November 2021 Major Release

## Slide 79: XRN5289 - November 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Detailed Functional Requirements have been approved Non Functional Requirements are currently being reviewed High Level Design is being reviewed and approved Design workshop plan is approved to start on the 1st February Currently planning CSSC/CSS impact assessment timeline and content |  |  | 
Risks and Issues | Not a full 6 months for Change Pack and delivery – proposing eChMC on the 5th May need agreement XRN5142 – Unknown plans from DCC on their plan of delivery and design Return to Green Gain agreement from ChMC on eChMC Set up regular touch points with DCC to understand their plan and design |  |  | 
Cost | EQR approved by ChMC on the 13th January |  |  | 
Resources | Resource Forecasts and Plans have been defined at a high level and approved until initiation this includes detailed requirements SME resource has been provided for design, approach for technical SME resource to support design has been agreed |  |  | 
Updated as of 27th January 2021

## Slide 80: XRN5289 – November 21 Release High-Level Plan
Updated as of 27th January 2021

## Slide 81: XRN5289 - November 21 Release Summary
In Scope
XRN4941 - MOD0692 - Auto updates to meter read frequency
XRN5007 - Enhancement to reconciliation process where prevailing volume is zero
XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes
XRN5091 - Deferral of creation of Class change reads at transfer of ownership
XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC
XRN5180 - Inner tolerance validation for replacement reads and read insertions
Out of Scope
Approved to removed from 13th January 21 ChMC
XRN5186* MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs
XRN5187* MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs
The initial scope of the November 2021 Major Release consists of 8 changes
Updated as of 27th January 2021

## Slide 82: XRN5294 - Minor Release Drop 9 Update

## Slide 83: XRN5294 - Minor Release Drop 9 - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 2 changes for Minor Release Drop 9 to be implemented. The implementation date is planned for 20th March 21: XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​ XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance Acceptance Testing in progress, slightly behind plan due to resource availability. Resources available next week to cover any delayed testing assurance Minor Release Drop 8 defect fixed and tested, this can continue with implementation on 5th February 21 as per plan, on track |  |  | 
Risks and Issues | Issue due to lack of resource availability for testing assurance from w/c 18/01/21 , this is to be mitigated by increased availability of resources from w/c 01/02/21 |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 
Updated 27th January 2021

## Slide 84: XRN5294 - Minor Release Drop 9 Timelines
Updated 27th January 2021

## Slide 85: XRN5294 - Minor Release 9 Summary
There are 2 changes for Minor Release 9 to be implemented. The proposed implementation date is 20th March 21:
  XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​
  XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance
Updated 27th January 2021