## Slide 1: CMS Rebuild Update
February Updates
Jo Williams

## Slide 2: CMS Rebuild - Progress to date
Summary of progress to date
CMS is a dated system which is coming to end of life support, rather than a lift and shift of current processes the project team wanted to understand the following from the actual users of CMS perspective: What are their current processes and activities What are their current pain points What would their ideal version of the process be 18 External Initial Requirements Workshops have been held to date 483 requirements captured, this figure may include duplication Common themes include: Customer Effort System functionality Visibility All Workshop outputs will be published here: https://www.xoserve.com/systems/contact-management-service/contact-management-service-cms-rebuild-project/ Potential Suppliers are being engaged to understand high level requirements to obtain figures and timescales for High Level Solution Options Internal recommended "to be" workshops have commenced to understand what systems the solution will need to integrate with
Key Milestones | Due
Initial Workshops Completed | 22/01/2021
To Be Workshops Commence | 08/02/2021
HLSO – Target Date | March
Next Steps
Refine the requirements which will be: Remove duplication Add our understanding to the requirements and ratify with customers Understand areas of conflict in requirements Continue internal and schedule external recommended “To Be" workshops Identify possible solutions and seek approval on solution and design from: CoMC ChMC DSG

## Slide 3: CMS Rebuild Next Steps
Dec | Jan | Feb | March
Hints & Tips Refreshers published
Commentary
Workshops to date have recieved great feedback to date and the findings are consitent accross the board
Progress published – Website, CoMC and DSG
External “To Be” Solution Options
Painpoint & Req Workshops
Completed
On Track
At Risk
It is currently unclear if there is any misalignment on the To be solutions across the processes and these may require several iterations to come to an agreed approach.
Overall Agreement of “To Be” processes
Internal “To Be” Solution Options