## Slide 1: REC Update
Contract Management Committee
21 April 2021

## Slide 2: Planned Meetings Update & Key Milestones
CSS & GES (V3)
2020 |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Data Permissions Alignment
Drafting commences​
V3 Opens
REC v2 Code Consolidation
Fortnightly
RDUG
Code Consolidation (V2)
Go Lives
Ofgem Consultation
GES/CDSP FS
Contract Signature
REC/XO
Contractual​s'
V2 Closes
V3 Closes
REC Go-Live
Enduring RECCo. Board Appointed
REC Manager Proc Completed
Opens
Closes
V3 Designated
V2 Designated
V1.1 Designated
REC V1.1
V2 Opens
REC V3 Fast Switching
REC V1.1 Interim Governance
Key:
Meeting Scheduled
Meeting Completed
Meeting Originally Planned
Latest Milestone Date
Original Milestone Date
Completed Milestone
REC Licence Changes
Opens
Closes
CC Statutory Licence Consultation
Opens
Closes
Opens
Closes
FS Statutory Licence Consultation

## Slide 3: Ofgem Consultation
REC V2 - REC Code Consolidation Schedules
  (REC Transition; SPAA Transition; Data Access; Transfer of Consumer Data; Smart Meter Installation; Prepayment; Qualification and Maintenance; Secure Data Exchange; Market Exit; Meter Operations; Metering Governance)
  Response submitted.
REC V3 - Faster Switching Schedules
  (Data Access Schedule; Interpretation; Data Management; Registration Service; Registrable Measurement Point Lifecycle; Address Management; Switching Service Management)
  Data Access Schedule – comments due back 09/03/21
  Consultation commenced 01 April – responses due 30 July

## Slide 4: SCR- Impacts to UNC
SCR –Code Consolidation REC V2 (Sept 2021)
  Minimum changes as deletion of BEIS wording completed as a result of Mod697 implementation.
  Changes required as a result of consultation responses – these are still unknown.
  Mod762 raised to add RECCo to the DPM
  SCR – Faster Switching REC V3 (summer 2022)
  Amendments to UNC to align with REC (B;G;M; GT-D)

## Slide 5: Next Steps
UNC Consequential Changes will be published by Ofgem in the next 2-4 weeks
Discussions to be held with RECCo ahead of GES contract negotiations:
  DSC Customer access to gas enquiry services
  Scope of GES