## Slide 1: XRN5253 June 21 Major Release - Status Update
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Testing phase progressing to plan System, user and regression testing completed to plan in May Performance testing commenced to plan and due to finish by 11th June Go-live will take place on Saturday 26th June Post implementation support period agreed based on 1st usage timelines for MOD0700 (see next slide) Decision In June ChMC None |  | 
Risks and Issues | None applicable |  | 
Cost | Forecast costs on track to complete within approved BER |  | 
Scope | XRN5093 - MOD0711 – Update of AUG Table to reflect new EUC bands Descoped - XRN4992 - MOD0687 – Creation of new charge to recover last resort supply payments – Descoped at Extraordinary ChMC on 26th October 2020 Descoped - XRN4941 - MOD0692 - Auto updates to meter read frequency – Descoped at ChMC on 11th November 2020 |  | 
Slide updated on 28th May 2021
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 2: Post Implementation Support (PIS) Period
The below timeline details the PIS periods required for this Release based on 1st usage timings
NOTE: The 3 PIS Periods have been put in place to align to 1st usage