## Slide 1: XRN5371 - Minor Release Drop 10 - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule |  | Risks and Issues | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Scope approved during May ChMC Currently in Design phase XRN5246: Solution Change pack to be issued in June Implementation date agreed for 4th September with a contingency date of 2nd October 2021 Decision in June ChMC: None |  |  | 
Risks and Issues | None applicable |  |  | 
Cost | On track to complete within approved spend |  |  | 
Scope | XRN5309 - FSG Automation of FSR Process XRN5188 - MAP ID Data Upload to UK Link XRN5246 - Confirmation File Performance improvements |  |  | 
Slide Updated on 28th May 2021
Complete
On Track
At Risk
Overdue
Not Baselined