## Slide 1: CSSC Programme Dashboard
June 2021

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status. The wider Switching Programme is reporting an Amber-Green status with the Amber portion being related to the planning activities around Transition Xoserve have successfully entered UEPT. Preparation continues for Transition, Business Change and Service Management activities. The inaugural Switching Programme Post Implementation Working Group was conducted on 26/05. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Transition: Live Rehearsal Cycle 1 continues to plan along with preparations for LR Cycle 2, which is more reflective of Transition. Artefact reviews continue with the Switching Programme, alongside internal workshops. CR-D071 (Treatment of Inflights during Transition) has now been approved Internal & External Testing: All testing activities are on track with planning Data Migration: REL cycle 4 data work has completed and has been delivered 1 week early. A request has been received for Cycle 5 (non-rel) Analysis reports due for delivery on July. Work on track Business Change: Internal knowledge transfer sessions continue. Target Operating Model activities are on track Service Management: Xoserve had raised a CR to align Service Management Response SLAs. This is currently under industry impact analysis. |  |  |  | Live Rehearsal: Continue Cycle 1 Internal Test: Progress CR testing and any relevant regression tests DES:& Secondary APIs Continue development and system test activities. Transition: Continue Live Rehearsal & Transition planning MAP C: Change Packs approved, delivery continues to plan REC: Continue REC schedule review as per Ofgem timelines Business Change: Continue awareness and knowledge transfer session
Programme Update

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall Green: Delivery on track for E2E
 |  | Testing | The overall status remains Green. Successful entry into UEPT, at the point of writing this, no significant defects have been seen Planning complete for all upcoming for OT.
 |  | Service Management | Internal Service Management activities continue to feed into OT and internal OAT A CR has been raised (CR-072) and discussed at Change Advisory Workgroup (CAT) to align Switching Programme SLAs to match Xoserve’s existing response times. Currently undergoing impact assessment.
 |  | Batch | The overall status is green, with testing support underway for UEPT/E2E activities
 |  | Gemini | The overall status is green
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess, deliver and test Switching Programme changes raised through the last few months

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC consultation continues with Xoserve actively engaged in relevant RDUG meetings as well as reviewing REC schedules
 |  | Data Migration | REL cycle 4 data work has completed and has been delivered 1 week early. A request has been received for Cycle 5 (non-rel) Analysis reports due for delivery on July.
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan for all upcoming activities. Awaiting confirmation from DCC and REC around the need for enduring environments post Go-live
 |  | MAP C (XRN-4780C) | Delivery continues, with a plan to incorporate delivery governance into the November 21 major release
 |  | SoLR (XRN-5144) | Industry discussion continue with Ofgem

## Slide 5: Key Programme Risks (1/3)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
65184 |  | Programme | There is a risk that supplier resources working on the programme will be diverted to support BAU activities and service provision because of the COVID-19 situation in India affecting significant numbers of people either directly or their friends and family leading to potential delays in CR and defect delivery, reduced support for environment provision and maintenance, delays to data migration and testing support. | Work with suppliers to understand pinch points within delivery teams and prioritise resource allocations accordingly to reduce impact | Suppliers continue to provide regular reports no impact to the programme currently. | 31/05/21
65244 |  | Transition & Cutover | There is a risk that the Xoserve DMLR Cycle 2 schedule will have to be changed at very short notice As the SI as not following the transition runbook for LR testing, and are planning to review / revise the plan as LR Cycle 1 progresses leading to very short notice changes, with potential resource conflicts and additional work to bring transition runbook into line | Request DMLR Cycle 2 stage 1 plan at the end of cycle 1 stage 1 | Xoserve to request that the cycle 2 stage 1 plan is issued shortly after the end of cycle 1 stage 1, rather than waiting until the whole cycle has completed | 25/06/21
65175 |  | Transition & Cutover | There is a risk that the overall Transition timeline may change because the Transition test stage 1 plan exceeds the 6 week limit leading to additional time required for transition as activity durations are confirmed in Transition testing and transferred to the Runbook | Liaise with the SI to close gaps and ensure plans are aligned to agreed Transition timelines | A revised plan was shared on 04/05. A review of this plan indicated several Microsoft project plan issues. A third review is planned once Darren issues a revised plan (ETA18/05) | 08/11/21
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | Continues to be monitored until Tranche 1 of E2E is complete | 01/08/21
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | Continues to be monitored until Tranche 1 of E2E is complete | 01/08/21

## Slide 6: Key Programme Risks (2/3)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | CR-D072 received for IA in respect of SLAs. To be reviewed and sent back by 20/5 | 31/06/21
65156 |  | Transition & Cutover | There is risk that the change freeze scope could impact Transition because the scope of Programme Change Freeze from 03/01/22 is not clearly defined leading to impacts during actual Transition | Work with the SI to collectively define the scope of Change Freeze | Update at the SI Transition Group from Ofgem is that a view will be tabled at the next SI Transition Group | 26/07/21
64002 |  | Programme | There is a risk that ongoing pipeline of customer driven and regulatory change within the industry could impact the CSSC and wider Switching Programme delivery because of technical conflict with the design of other changes and demand on resources across Xoserve and the customer teams involved in Switching Programme delivery leading to additional regression testing activity, CRs raised to modify solutions already developed and tested by the programme, delays to the overall Switching Programme, and therefore unplanned costs for Xoserve. | 1. Discuss the potential for change moratoria with Ofgem that could restrict the volume of change being made and in particular mitigate some of this risk in relation to coding impacts 2. Investigate the availability of and if necessary invest in tooling to support more enhanced branching and merging in terms of development to mitigate the technical impact of any non-CSSC changes. 3. Work with the SI to monitor for any potential impact on programme resources, including customer resources, that may result from change initiatives running in parallel with critical path Switching Programme phases. | Update at the SI Transition Group is that this is a risk that will be need to be accepted. Will be marked accepted once the corresponding Switching Programme risk is accepted by Ofgem | 30/06/22
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | CR-D072 received for IA in respect of SLAs. To be reviewed and sent back by 20/5 | 31/06/21

## Slide 7
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64158 |  | Programme | There is a risk that that the Operational Choreography CR that is in progress may be approved because it might be deemed necessary by the central programme leading to further plan considerations (at both the central and individual PUI's plans) and cost implications to Xoserve | This has been raised with SI/DCC & Ofgem. This is being tracked collectively via the MAD log actions. Should this CR be approved, this action will be addressed with central bodies | Awaiting update/confirm from Ofgem | 04/06/21
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Update at the SI Transition Group is that this is a risk that will be need to be accepted. Will be marked accepted once the corresponding Switching Programme risk is accepted by Ofgem | 28/05/21
65176 |  | Transition and Cutover | There is a risk that the Runbook may not be properly tested because schedules to be used across test phases (DM LR / Transition testing) are being developed separately leading to potential for discrepancies and for insights from one activity being missed by the other | Liaise with the SI to ensure that all plans are aligned. Request early sight of plans to ensure adequate review in advance | Risk raised with SI in light of LR plan issue, showing a change in sequencing for DM LR | 28/05/21

## Slide 8
High Level Plan

## Slide 9: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created

## Slide 10: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £25,500.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 |  | 19/03/2021 | Approved - Internal CR Created
REL Dissemination to iDNO and DNO | CR-D069 |  | 15/03/2021 | Pending PIA
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Pending SI Response
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Pending SI Response
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | £0.00 | 07/05/2021 | Complete

## Slide 11: Switching Programme CR Position – Pending Xoserve Impact Assessment
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 |  | 14/05/2021 | Pending PIA
Engagement for Early E2E Testing v0.2 | CR-D082 |  | 14/05/2021 | Pending PIA
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 |  | 24/05/2021 | Pending PIA

## Slide 12: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn

## Slide 13: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact

## Slide 14: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
In-Flight Reg ID Dissemination | CR-D066 |  | Not Received
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact

## Slide 15
Chart: 
| 43585 | 43616 | 43646 | 43677 | 43708 | 43738 | 43769 | 43799 | 43830 | 43861 | 43890 | 43921 | 43951 | 43982 | 44012 | 44043 | 44074 | 44104 | 44135 | 44165 | 44196 | 44227 | 44255 | 44286 | 44316 | 44347 | 44377 | 44408 | 44439 | 44469 | 44500 | 44530 | 44561 | 44592 | 44620 | 44651
Monthly FORECAST (Cumulative) | 363976.72 | 683029.7765 | 1009036.499 | 1468927.8937 | 1881004.6077 | 2628016.319 | 3342083.1863 | 4458203.008 | 5354404.1687 | 6043381.8373 | 7142886.031 | 8975402.7507 | 10111305.124 | 11388987.0723 | 13038342.6157 | 14439812.029 | 15676651.8173 | 16871244.8833 | 18128098.5297 | 18805264.193 | 19805071.6864 | 20880560.8003 | 21535840.0351 | 22900836.2051 | 23741581.4017 | 25221791.4217 | 26707177.1517 | 28201768.6017 | 29607615.4517 | 30437600.9017 | 31329066.8517 | 32623882.8017 | 33498013.0351 | 34501787.2684 | 35906770.5017 | 36746041.8051
Monthly BUDGET (Cumulative) | 489844.68 | 1174749.2 | 1918322.31 | 2859329.26 | 3600336.21 | 4373413.71 | 5301107.71 | 6054522.36 | 6844783.41 | 7587690.86 | 8469886.81 | 10016454.16 | 10772088.89 | 11466104.1 | 12171330.71 | 14216755.3 | 15951497.88 | 17098244.84 | 18223938.97 | 19242195.57 | 20253660.21 | 21199102.25 | 22074558.18 | 23123177.56 | 23741581.4017 | 25221791.4217 | 26707177.1517 | 28201768.6017 | 29607615.4517 | 30437600.9017 | 31329066.8517 | 32623882.8017 | 33498013.0351 | 34501787.2684 | 35906770.5017 | 36746041.8051
Monthly ACTUALS (Cumulative) | 228433.92 | 548079.88 | 1260281.72 | 2160027.93 | 2928145.54 | 3938750.3 | 4855898.385 | 5889989.03 | 6410840.7 | 6911519.115 | 7785494.945 | 8810593.43 | 9969351.24 | 11012414.495 | 13032728.295 | 14595347.525 | 16039780.755 | 16876714.6283 | 18171730.1383 | 18895026.3383 | 20150164.6083 | 21211022.3383 | 21965343.9083 | 23586832.8183 | 24501593.2083 | 25981803.2283 | 27467188.9583 | 28961780.4083 | 30367627.2583 | 31197612.7083 | 32089078.6583 | 33383894.6083 | 34258024.8417 | 35261799.075 | 36666782.3083 | 37506053.6117
Total Approved Budget | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000