## Slide 1: Change Pipeline

## Slide 2: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: Delivery Pipeline
| Ready for delivery | Standalone | Unallocated | CSSC | Jun 21 | Nov 21 | Standalone | MiR10 | Awaiting Delivery | In Delivery
Total | 3 | 1 | 2 | 4 | 1 | 6 | 7 | 2
Chart: Change Development
| Solution Consultation | Capture | Initial Review | Pre-capture
Total | 4 | 23 | 3 | 28
Chart: Changes From Last Period
| New MOD | New CP
Total | 4 | 1

## Slide 3
2020-2022 DSC Change / MiR Pipeline
 | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Minor Releases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Major Releases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Standalone Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
June 2021 (DBTI + PIS/Closedown)
Nov 2021 Analysis / Design
November 2021 Build/Test Implement/PIS
MiR 9
MiR 10
MiR 11
MiR 12
Regression
PIS
Retro (MOD 0651)
Key:
On Track
Potential Activity
Nov 21 IA
November 2022 Build/Test/Implement/PIS
*Nov 2022 Analysis / Design
XRN
5206
5237
XRN
5146
XRN
5038
XOS Change Fund 21/22
PAC
BER
CCR
Scope
CCR
CCR
Scope
Scope
CCR
CCR
PAC XRN4876
BER
CCR
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved
Nov 20 PIS
CCR
XRN
4780C
XRN
5231
BER
EQR 5379 5231
XRN
5183
BER
5183
* Subject to no delays/impact from CSSC implementation
* Feb 23 & June 23 Release development and scoping
EXTERNAL(MT/UEPT/E2E/Defect Mgmt)
Planning
Transition
Go Live Range
XRN
4780C