## Slide 1: XRN5253 June 21 Major Release - Status Update
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Project On Track Project Go Live Successfully completed on 26/06/21 Post Implementation Support (PIS) Period 1 commenced to plan on 28/06/21 and completed on 09/07/21 Further PIS periods 2 & 3 scheduled between September and December to cover all 1st Usage. Decision In August ChMC No decisions are required this month. |  | 
Risks and Issues | None Applicable |  | 
Cost | Forecast costs on track to complete within approved BER |  | 
Scope | In Scope (XRN5093) - MOD0711 – Update of AUG Table to reflect new EUC bands Descoped (XRN4992) - MOD0687 – Creation of new charge to recover last resort supply payments – Descoped at Extraordinary ChMC on 26th October 2020 Descoped (XRN4941) - MOD0692 - Auto updates to meter read frequency – Descoped at ChMC on 11th November 2020 |  | 
Slide updated on 21st July 2021
Complete
On Track
At Risk
Overdue
Not Baselined