## Slide 1: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS AUG 2021 - JULY 2023
August 2021

## Slide 2
Programmes & Projects 2021-2023 |  |  |  | 2021 |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | 
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | MOD0745 - Setting of Auction Bid Parameter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | MOD0728B – UK Link & Gemini Delivered as part of CP5341 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain | PM Nicky Patmore | Gemini Customer Enhancements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes |  | CSS Cons Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | CSS Cons Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Manisha Bhardwaj | Single Sign on Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | PM Matthew Stephens | API Enhancements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS AUG 2021 – JULY 2023
Implementation
19th Sept 21
Implementation
26th Sept 21 (C)
Build/Test – Aug to Sept 21
UKL Implementation
27th Aug 21
Regression Testing UKL
2nd Aug to 20th Aug 21
Design to PIS – Oct 21 to Jan 22 – Indicative timeline
Design to PIS – Sept 21 to Apr 22 – Indicative timeline
PIS July - Sept 21
Gemini Implementation
19th Sept 21
Pre-Implementation - Sept to Oct 21
Content: External Test Phase Jul - Dec 21
Build/Test – Aug to Sept 21
PIS Gemini - Sept to Dec 21
PIS UKL - Sept to Nov 21
Design to PIS – Sept 21 to Dec 21– Indicative timeline
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk