## Slide 1: REC Update
Contract Management Committee
18 August 2021

## Slide 2: Planned Meetings Update & Key Milestones
CSS & GES (V3)
2020 |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Drafting commences​
V3 Opens
REC v2 Code Consolidation
Code Consolidation (V2)
Go Lives
Ofgem Consultation
CDSP FS
Contract Signature
REC/XO
Contractual​s'
V2 Closes
V3 Closes
GES Contract Signature
Enduring RECCo. Board Appointed
REC Manager Proc Completed
Opens
Closes
V3 Designated
V2 Designated
V1.1 Designated
REC V1.1
V2 Opens
REC V3 Fast Switching
REC V1.1 Interim Governance
Key:
Meeting Scheduled
Meeting Completed
Meeting Originally Planned
Latest Milestone Date
Original Milestone Date
Completed Milestone
REC Licence Changes
Opens
Closes
CC Statutory Licence Consultation
Opens
Closes
Opens
Closes
FS Statutory Licence Consultation
REC Consultation
Performance Assurance
Opens
Closes
Proposed Licence Changes Consultation
Designated
Designated
Response

## Slide 3: Ofgem Consultation Update
REC V2 - REC Code Consolidation Consultation
  Decision published 30 April 2021
  CR -D092 submitted on 21 June 2021 to implement V2 schedules, any further amendments will need to be raised via change control process.
CM Performance Assurance Consultation
  Decision published 2 July 2021
RCC Statutory Licence Changes Consultation
  Decision published 2 July 2021
REC V3 – Faster Switching Schedules
  (Data Access Schedule; Interpretation; Data Management; Registration Service; Registrable Measurement Point Lifecycle; Address Management; Switching Service Management)
  CR-75 – introducing CSS Interface Provider role
  Consultation commenced 01 April – responses due 30 July
  Xoserve response to Q2.1 and Q2.2 shared with CoMC
  Xoserve submitted response 30 July.

## Slide 4: SCR- Impacts to UNC
SCR –Code Consolidation REC V2 (Sept 2021)
  Amendments to UNC to align with REC (B;G;M; GT-D)
  Mod submitted by Ofgem for presentation at Mod Panel on 20 May /IGT Panel 28 May
  Notice to implement Mod768 issued 2 July
  Implementation to take effect 01 Sept 2021
SCR – Faster Switching REC V3 (summer 2022)
  Queried consequential changes published –awaiting further update

## Slide 5: Release of Protected Information to RECCo
UNC Mod 0762 and IGT UNC Mod 155 added the Retail Energy Code Company as a new User type to the Data Permissions Matrix – implemented with effect from 12 July 2021 (UNC) and 23 July 2021(IGT UNC)
Progressed work with the Performance Assurance (RPA) Code Manager in parallel with Mod development
  Anonymised data extract provided to RPA for assessment
  DRR approved at June CoMC
  Amended DRR presented at July CoMC for approval

## Slide 6: Next Steps
DSC CP has been raised (XRN5352 – Development of the REC Performance Assurance reporting)
  The change will be delivered to RECCo under the framework agreement agreed with Xoserve.
  CP raised to cover support costs to:
    Perform analysis,
    Verify accessibility of data
    Generate sample reports (and redact / pseudonymise data until UNC / IGT UNC Mods approved)
    Continue to develop final RPA reporting
Discussions to be held with RECCo ahead of GES contract negotiations:
  DSC Customer access to gas enquiry services - decision still pending
  Scope of GES - to be baselined as part of V3 consultation response review

## Slide 7: Data Access – Discussion
V3 response to Q2.1 and Q2.2 discussed at July 21 CoMC
Further discussion held with RECCo regarding DSC parties’ continued access to services via the DSC rather than REC

## Slide 8: Other CM Engagements
Engagement ongoing with the Technical Assurance Code Manager
  Provision of metadata for EMAR population
  Need to define the process for provision of on-going change (and integration of the Change Management processes)

## Slide 9: Other CM Engagements – for awareness
Engagement initiated with the Governance Code Manager
  Awaiting confirmation of what products are expected at what stage during the change cycle
    IA level – ROM? HLSO?
    Design products – High Level Solution options? Revised interface design formats (file formats / screens / rejection codes?)
      Impacts are not possible to assess until available
      We need to assess how this will integrate with the DSC change processes
  Initial proposal flagged that major releases would be implemented in line with electricity (Thursday evening), and that there would be three major releases (Feb / June / Nov)
    Views?
    Mitigations? – relaxation of SLAs, amending invoice cycles