## Slide 1: XRN5253 June 21 Major Release - Status Update
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Project on track Post implementation support (PIS) period 2 successfully concluded on 28/10/21 Period 3 commenced to plan on 08/11/21 and is on track to complete on 10/12/21 Decision in December ChMC None |  | 
Risks and Issues | None Applicable |  | 
Cost | Forecast costs on track to complete within approved BER |  | 
Scope | In Scope (XRN5093) - MOD0711 – Update of AUG Table to reflect new EUC bands Descoped (XRN4992) - MOD0687 – Creation of new charge to recover last resort supply payments – Descoped at Extraordinary ChMC on 26th October 2020 Descoped (XRN4941) - MOD0692 - Auto updates to meter read frequency – Descoped at ChMC on 11th November 2020 |  | 
Slide updated on 23rd November 2021
Complete
On Track
At Risk
Overdue
Not Baselined