## Slide 1: Q1 2022 Change & Operations Deliverability Confidence

## Slide 2: Overview
There is a significant amount of change planned between January and April 2022. This brings inherent risk into our delivery and support of critical production services and processes.
This deck pulls out the levels of change congestion, BAU activities during the period and what contingency options exist.

## Slide 3
Build and Test
High Level POAP
24
November 21 Release
FWACV
EFT Upgrade
M2C
CSSC DM Out
CSSC DM In
Gemini Regulatory
Gemini Sustain
JAN FEB MAR APR
IDR
22
IDR
16
Cutover
26
24
2
9
16
19
27
IDR
Test
IDR
Single Sign On (likely to move right)
27
13
6
20
SiteMinder Upgrade (4 nodes)
27
Minor Release 11 TBC
22
Delay to Post M2C means additional testing
FWACV Consequential Changes to Gemini
IDR
22/03/22
IDR
Delays impact CSSC DM without break of DEP
Risk to CSSC Go-Live
Subject to movement based on Ofgem discussions
SOLR, Nov 22 Release Design and BAU Processes
1
27
Clock Change
See Slide 8
20
FYAQ Jobs
SOLR - Bulb timescales unknown
Test
Parallel run and Test
M2C delays into April will impact design and further deployment
Test

## Slide 4
Key Messages
High levels of industry and needed technical change
Significant levels of key operational (business and technical) involvement in critical BAU processes, transition to introduce change and potential incident management and resolution.
Significant additional and uncertain workload caused by SOLR; most recently Bulb
We recommend seeking to minimise the level of change:
  Do not commit to MiR11
  Deliver FWACV on-premise before M2C and transition to cloud, post cutover of M2C
  Move M2C (either Easter or Jubilee weekends to utilise extended non-business days and provide assurance around the plan)
  Monitor likely CSS deployments and influence best placement of CSSC deliveries
All to preserve the integrity of the following UKL and Gemini priorities (either because they're a customer-impacting priority or because they're an upstream dependency to a customer-impacting priority):
  UKL: Nov 21, EFT, MTC, CSSC (all deployments)
  Gemini: Gemini Sustain and Regulatory modification changes
  Flow Weighted Average CV post risk mitigation activities