## Slide 1: XRN5231 Flow Weighted Average CV
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Overall Status set to Amber due to multiple phases progressing in parallel and the need to baseline the Dual Run, Cutover & transition phases and Go Live date Build completion now 05/01/22 to incorporate several CRs (inclusive of Gemini Consequential Changes) System Testing due to complete by 07/01/22 (1 week extension to plan but no overall impact) System Integration Testing due to commence on 04/01/22 (1 week behind plan but no overall impact) Gemini Consequential changes tracking to plan, and System Testing completed on 27/12/12 Focus Groups for project continued through December 21 with National Grid and DN reps Dual Run and Market Trials approach discussed at Focus Groups with approach published on 24/12/21. Planned start of testing is 10/01/22 Cutover and Transition Approach to be shared for review & approval by 31/01/22 Notional Implementation date set for 26/03/22, contingency options defined and shared to Focus Group. To be discussed further with DNs & NG |  | 
Risks and Issues | There is a risk that change congestion with UK Link move to Cloud, Gemini Regulation and Sustaining change during Q1 & 2 2022 where cutover & implementation dates may need to be prioritised There is a risk that until the transition & cutover approach is agreed between Xoserve, National Grid & DNs to confirm the length of Post Implementation Support and what support dependencies are required from National Grid as the existing service provider There is a risk that National Grid have served notice to terminate the current FWACV service on the 31st March 2022 and the project plan does not meet an implementation date of the new service from the 01st April 2022, resulting in the need to negotiate an extension of the service by National Grid |  | 
Cost | Forecast costs tracking to approved BER costs |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  | 
Complete
On Track
At Risk
Overdue
Not Baselined