## Slide 1: XRN5231 Flow Weighted Average CV
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall Status set to Red due to Dual Run / Market Trials baseline plan being delayed by an issue, the impacts to the downstream phases and Go Live readiness for 1st April. System Testing and System Integration Testing Completed (07/01) UAT In progress. Execution tracking to plan however delays against Assurance have pushed expected completion to 11/02. Additional activities/ unknown requirements have also been identified which may further extend overall testing period A number of challenges currently exist against the project putting 1st April Service Go Live Date at risk, these include: Dual Run (DR)/Market Trials (MT) – delays to connectivity setup/testing and Master Data load is currently 4 weeks behind plan Data Migration – challenges around Master data and transformation approach need to be resolved Go Live – the volume of planned parallel activities, delays to DR/MT start and Business Readiness/ Data Migration mean that the notional system Go Live date is now at risk Next Steps: The re-plan assessment of the defined contingency implementation options are being defined and will be presented to Focus Group Full project readiness criteria to be defined, reviewed and approved by all stakeholders Implementation options (including current planned date) to be assessed, agreed and presented to the DSC Change Management Committee |  |  | 
Risks and Issues | There is a risk that we will not be able to implement the service from 1st April due to delays in Dual Run/Market Trials and volume of Cutover, Transition & Business Readiness activities in the plan to be completed and to meet the agreed readiness criteria by all stakeholders e.g., Xoserve, DNs, NG and Grain LNG There is a risk that change congestion with UK Link move to cloud, Gemini regulation and sustaining change during Q1 2022 will lead to reassessment and reprioritization of cutover & implementation dates for FWACV There is a risk that the FWACV project plan does not achieve the implementation date for the new service from 1st April 2022; resulting in National Grid and the DNs being required to negotiate and agree an extension of the existing service currently provided by National Grid Master Data assurance - there is a risk that stakeholders might have issues and errors within the master data (MD). National Grid are providing MD from 5+ separate systems and is unable to support the transformation of MD into our target data templates. To mitigate this risk, Xoserve will transform National Grid’s MD into the target data model. There will be a requirement for DNs / NG to assure the data transformed (e.g., Supply Meter Points, Site Types, LDZ attribution maps) to ensure that the data is accurate and fit for purpose to support the new FWACV service |  |  | 
Cost | Forecast costs tracking to approved BER costs at present. Revised plan options will generate the need to assess this position. |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 
Complete
On Track
At Risk
Overdue
Not Baselined