## Slide 1: Change Management Committee
12th January 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: DSC Change Budget 21/22 YTD

## Slide 4: Budget v Committed Spend BP21/22
Chart: Total Committed Spend v Approved Budget
| Budget | Spend
 | 3589600 | 2616839.1166
No movement since January-22
Full view of budget - Link
Chart: Shipper Budget v Spend
| Budget | Spend
 | 2073012.3133 | 1329719.0123
Chart: DN Budget v Spend
| Budget | Spend
 | 1248246.62 | 1253245.8415
Chart: IGT Budget v Spend
| Budget | Spend
 | 194765.1631 | 33874.2628
Chart: NT Budget v Spend
| Budget | Spend
 | 73575.9036 | 0
At this stage, Shippers have committed 64% of approved BP21 Budget
DNs have committed 100%
IGTs have committed 17% and NTS 0%

## Slide 5: Change Pipeline

## Slide 6: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: Change Development
| Capture | Initial Review | Pre-capture | Solution Review
Total | 18 | 6 | 40 | 2
Chart: Delivery Pipeline
| CSSC | Standalone | Unallocated | Proposed Nov 22
Total | 4 | 12 | 5 | 1
Chart: Changes From Last Period
| New Mod | New CP | CP Implemented | MOD to be implemented
Total | 9 | 3 | 5 | 1

## Slide 7
2021-2022 DSC Change / MiR Pipeline
Key:
On Track
Potential Activity
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved

## Slide 8: Section 3: Capture

## Slide 9: New Change Proposals – Initial Review
For Approval
XRN5471 Services to release data to UNC parties
XRN5472 Creation of a UK Link API to consume daily weather data for Demand Estimation processes
XRN54xx - Meter Asset Detail Proactive Monitoring Service
For Information
XRN5470 New Service Line for SDT v21

## Slide 10: XRN5471 Services to release data to UNC parties
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
DSC parties have indicated that they consider that they have specific use cases for access to data for them to fulfil activities necessary for them under UNC and Licence. They have indicated that they expect that they have specific data requirements based on particular use cases and would like to specify the necessary data that their users will wish to access rather than necessarily progressing through a series of screens to access a standard set of data. They anticipate that this service would be discrete from the Data Enquiry Service. It is expected that this will need to provide a User Interface – and based upon prescribed search criteria (that will need to be defined for each use case) will return a specified set of data items (which again will be specified per use case). This needs to be a low cost solution option that allows access to data for designated individuals within DSC parties organisations. This service would be available to core DSC customers. [This may be extended to Service Providers – such as the DMSP at some point in the future]. It is expected that users will need to access this data via a user interface (screen) and it is not expected that this will be a machine to machine API.
Change Type | Non Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | X

## Slide 11: XRN5472 Creation of a UK Link API to consume daily weather data for Demand Estimation processes
DSC Service Area: | Service Area 5: Demand Estimation Obligations
Link to Change Proposal | Link to CP
Sponsor Representative | Correla
Change Description
The current CDSP Weather Data Service Provider has informally given notice that it will not be able to support the current mechanism (FTP) of delivering daily weather data (forecasts and observations) to UK Link beyond March 2023. The weather data is delivered from one of their legacy delivery systems which they are phasing out and replacing with APIs. If the change is not made there will be a requirement to find an alternative service provider in 12 months who would be willing to support a bespoke file format using an outdated transfer mechanism. The change required is to move away from receiving weather data by FTP in a specific file format to 'pulling' the data needed from the Weather Data Service Provider, via APIs, into the relevant weather data table in UK Link.
Change Type | Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | X

## Slide 12: XRN5473 Meter Asset Detail Proactive Monitoring Service
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
Following implementation of XRN4780-C, the Meter Asset Manager (MAM)/Meter Equipment Manager (MEM) will be required to provide a copy of meter asset transactions to the Central Data Service Provider (CDSP). The purpose of this provision is in order to supplement Shipper provided data should it not contain a valid Meter Asset Provider identity (MAP Id). This change has been raised to investigate, and develop, a service to assess the asset details received from MAM/MEM against those held on the Supply Point Register and, subsequently, received from the Shipper User. The objective of these assessments is to proactively highlight where there may be inconsistencies in the data recorded on the Supply Point Register leading, potentially, to settlement issues and support customers in investigating these inconsistencies to allow them to take any necessary corrective action to improve overall data quality. This proposal will initially provide an impact assessment defining the service and costs, and investigate the data permissions required in order to provide this service.
Change Type | Non Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 

## Slide 13: XRN5470 New Service Line for SDT v21
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
A new service line ASGT-CS SA8-41 has been created to support Mod 0788 – ‘Minimising the market impacts of ‘Supplier Undertaking’ operation. This is associated with XRN5443 which was raised to implement the solution required to be delivered as set out in the Mod Full Details of the Service line can be viewed within the embedded version of the Service Description Table (v21.1) within the CP
Change Type | Documentation
Priority Score | Low
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
For Information Only. This CP will be presented at CoMC for approval on 16/02/2022 | 
Service Requirement Description | Service Requirement Trigger
To provide the ability for Suppliers who are operating under a DoU following the Termination of the Shipper User, to utilise other existing Shipper User relationships to source additional supplies of gas and make trade nominations to the Terminated Shipper User account to balance that portfolio and mitigate increased costs, until a new ‘Registered User’ is appointed. | Supplier populates and submits the ‘Supplier – Failed Shipper replacement form’ which can be located on Xoserve.com. This is sent to the Shipper contact provided on the form.

## Slide 14: Change Proposals – Post Solution Review for Approval
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664)

## Slide 15: XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664)
Solution Review Consultation Summary
Change Pack Ref | HLSO Cost | Funding | Preferred Option | Voting | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  |  |  | Approve | Defer | Reject
2955.1 - MT - PO | 70-150K | SA1: Manage Shipper Transfer 100% Shipper | Option 1 | Shippers | Potential Nov 22 | 4990 |  |  | 
Org | Status | Comments
 |  | No Representations received

## Slide 16: section 4. Design & Delivery

## Slide 17: Detailed Design Change Packs
XRN4992a - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process (Interim Solution)
XRN5393 - Gemini Spring 22 Release (UNC MODS 0752S, 0755S & 0759S)
XRN5463 - Technical Debt reduction - Prime and Sub process enhancement
XRN5464 - Technical Debt Reduction - Class 1 and 2
UK Link Cloud Programme Change Pack

## Slide 18: XRN4992a - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process (Interim Solution)
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2955.2 - MT - PO | Service Area 1: Manage Shipper Transfers Split: 100% Shippers | Shipper, DNO | Ad hoc Release (April 22) | 4992 | 3 |  | 
Org | Status | Comments
WWU | Approve | WWU supports this change. We deem the change to be necessary given that on 20 January 2022, Ofgem approved UNC modification 0797 which sought to create a new specific charge type which is to be added to the current Distribution Network Transportation Charging Methodology for first use in the 2022/23 charging year. Given the short timeframe the above change appears to be a pragmatic solution to implement the required changes.
NGN | Approve | Northern Gas Networks supports the solution for MOD0797 and agrees with the targeted implementation date.
EON | Approve | We are concerned at the tight timescales for shippers to be able to implement the changes required in time for an April delivery. As per our representation on modification 0687V and 0797 our preference would be to focus on a robust, enduring solution, taking time to properly understand the solution and its impacts. We will require test files to be made available to test ensure we can process the invoices successfully prior to implementation; will Xoserve be able to confirm when we could be provided with these? We understand that the enduring solution is a candidate for Nov '22 release; solution design should commence as soon as possible for this so that we are not again faced with the same situation regarding timescales; equally, we would not want an interim solution to be in any longer than absolutely necessary. Whilst shippers will not be provided with any backing/additional data for the interim solution, we would expect to be provided with this for the enduring so that we may validate the charges more easily. Finally, the modification title requires amendment to reflect the fact this is now related to 0797 not 0687V

## Slide 19: XRN5393 - Gemini Spring 22 Release (UNC MODS 0752S, 0755S & 0759S)
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2955.4 - MT - PO | Service Area14: Gemini Services Split: 100% NTS | NTS, Shippers | Ad hoc Release 24th April | 5393 |  |  | 
Org | Status | Comments
 |  | No Representations received

## Slide 20: XRN5463 - Technical Debt reduction - Prime and Sub process enhancement
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2955.6 - MT - PO | Service Area 4: Meter Read/Asset processing | Shipper | Ad hoc Release – ASAP post approval | 5463 |  |  | 
Org | Status | Comments
 |  | No Representations received

## Slide 21: XRN5464 - Technical Debt Reduction - Class 1 and 2
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2955.7 - MT - PO | Service Area 3: Manage updates to customer portfolio | Shipper | Ad hoc Release – ASAP post approval | 5464 |  |  | 
Org | Status | Comments
 |  | No Representations received

## Slide 22: UK Link Cloud Programme Change Pack
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
2955.8 - MT - PO | N/A – Document Change | Shipper, DNO & IGT | Ad hoc Release – May 2022 |  |  | 
Org | Status | Comments
 |  | No Representations received

## Slide 23: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5450 Demand tool to support Urgent Modification 0788
  Voting NTS
BER for XRN5458 Urgent Modification 0791 - Contingency Gas Procurement Arrangements when a Supplier acts under a Deed of Undertaking
  Voting NTS
CCR for XRN5443 - Urgent Modification 0788 - Minimising the market impacts of ‘Supplier Undertaking’ operation
  Voting NTS
CCR for XRN5235 Request for access to SOQ data & capacity figures which influence transportation charges
  Voting Shipper
CCR for XRN5377 Addition of ‘Class’ field to supply point data reports
  Voting DNO
EQR for XRN5379 Class 1 Read Service Procurement Exercise (Mod 0710)
  Voting Shipper,

## Slide 24: XRN5253 June 21 Major Release - Status Update
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Project on track Project closedown activities in progress Decision In February ChMC Approval of Change Completion Report |  | 
Risks and Issues | None Applicable |  | 
Cost | Forecast costs on track to complete within approved BER |  | 
Scope | In Scope (XRN5093) - MOD0711 – Update of AUG Table to reflect new EUC bands Descoped (XRN4992) - MOD0687 – Creation of new charge to recover last resort supply payments – Descoped at Extraordinary ChMC on 26th October 2020 Descoped (XRN4941) - MOD0692 - Auto updates to meter read frequency – Descoped at ChMC on 11th November 2020 |  | 
Slide updated on 26th January 2022
Complete
On Track
At Risk
Overdue
Not Baselined
CCR for XRN5253 June 21 Release
  Voting Shippers

## Slide 25: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN5142: Final usage (.IQL) to be completed 31/01/22 Deferred Changes: Additional regression testing cycle completed on 19/01/22 Go Live approved and communications issued Implementation successful and Go Live on 22/01/22 First usage and data cleanse progressing against plan Comms issued for information in relation to INC0137773 raised during post implementation support XRN4992a: Impact assessment for tactical solution completed; change can be delivered during current release plan; there will be a slight change to remaining milestones XRN5188b: Impact assessment completed; change can be delivered during current release post implementation support period Decision in February ChMC: Approval of updated BER for inclusion of XRN4992a and XRN5188b into scope of November 21 release |  |  | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope – XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope – XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope – XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process In Scope – XRN5188b - Interim Data Loads of MAP Id into UK Link Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 26th February 2022
Complete
On Track
At Risk
Overdue
Not Baselined
Deferred go-live date: 22/01/2022 Contingency date: 29/01/2022

## Slide 26: Revised BER for XRN5289 – November 21 - Voting Shipper, DNO, IGT

## Slide 27: Dec 21 - April 22 Changes in Design – Shipper Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
 |  |  |  | Changes are progressing on track against plan High Level Design scheduled to complete 11/02/22
XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements scheduled to complete 10/02/22 Detailed Design scheduled to commence on 04/02/22
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | April 2022 – Consultation May 2022 - Approval | 67208 – Customers have not yet approved the High-Level Solution Option which is progressing through design in parallel. Mitigation: Accept Risk; Low risk as only 1 solution option identified and expecting approval in February ChMC. |  | Detailed Requirements scheduled to complete 01/02/22 Detailed Design scheduled to commence on 01/02/22
XRN4992B - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements scheduled to complete 31/01/22 Detailed Design scheduled to commence on 28/01/22
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements scheduled to complete on 11/02/22 Detailed Design scheduled to commence on 08/02/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements scheduled to complete on 04/02/22 Detailed Design scheduled to commence on 01/02/22
Slide updated on 26th January 2022

## Slide 28: Dec 21 - April 22 Changes in Design – DN Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
 | April 2022 |  |  | Changes are progressing on track against plan High Level Design scheduled to complete 02/02/22
XRN4900 - Biomethane/Propane Reduction | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements scheduled to complete 01/02/22 Detailed Design scheduled to commence on 02/02/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements scheduled to complete 04/02/22 Detailed Design scheduled to commence on 01/02/22
XRN5298 - H100 Fife Project – Hydrogen Network Trial | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements scheduled to complete 02/02/22 Detailed Design scheduled to commence on 27/01/22
Slide updated on 26th January 2022

## Slide 29: XRN5231 Flow Weighted Average CV
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall Status set to Red due to Dual Run / Market Trials baseline plan being delayed by an issue, the impacts to the downstream phases and Go Live readiness for 1st April. System Testing and System Integration Testing Completed (07/01) UAT In progress. Execution tracking to plan however delays against Assurance have pushed expected completion to 11/02. Additional activities/ unknown requirements have also been identified which may further extend overall testing period A number of challenges currently exist against the project putting 1st April Service Go Live Date at risk, these include: Dual Run (DR)/Market Trials (MT) – delays to connectivity setup/testing and Master Data load is currently 4 weeks behind plan Data Migration – challenges around Master data and transformation approach need to be resolved Go Live – the volume of planned parallel activities, delays to DR/MT start and Business Readiness/ Data Migration mean that the notional system Go Live date is now at risk Next Steps: The re-plan assessment of the defined contingency implementation options are being defined and will be presented to Focus Group Full project readiness criteria to be defined, reviewed and approved by all stakeholders Implementation options (including current planned date) to be assessed, agreed and presented to the DSC Change Management Committee |  |  | 
Risks and Issues | There is a risk that we will not be able to implement the service from 1st April due to delays in Dual Run/Market Trials and volume of Cutover, Transition & Business Readiness activities in the plan to be completed and to meet the agreed readiness criteria by all stakeholders e.g., Xoserve, DNs, NG and Grain LNG There is a risk that change congestion with UK Link move to cloud, Gemini regulation and sustaining change during Q1 2022 will lead to reassessment and reprioritization of cutover & implementation dates for FWACV There is a risk that the FWACV project plan does not achieve the implementation date for the new service from 1st April 2022; resulting in National Grid and the DNs being required to negotiate and agree an extension of the existing service currently provided by National Grid Master Data assurance - there is a risk that stakeholders might have issues and errors within the master data (MD). National Grid are providing MD from 5+ separate systems and is unable to support the transformation of MD into our target data templates. To mitigate this risk, Xoserve will transform National Grid’s MD into the target data model. There will be a requirement for DNs / NG to assure the data transformed (e.g., Supply Meter Points, Site Types, LDZ attribution maps) to ensure that the data is accurate and fit for purpose to support the new FWACV service |  |  | 
Cost | Forecast costs tracking to approved BER costs at present. Revised plan options will generate the need to assess this position. |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 30: Decarbonisation
January 2022
Victoria Mustard

## Slide 32
Heat Map on CDSP Systems & Communications
UKLink
Ability to flag (& remove flag) & make visible an MPRN/CV Zone on a decarb project
Ability to accept and process files containing CV for MPRN/ CV Zone
Calculate energy using correct CV
Ability to amend CV for Class 1 and 2 sites at MPRN level on GFD+1 (by GFD+5 at the latest)
Ability to amend CV for Class 3 & 4 sites at MPRN and/or CV Zone
Gemini
Possible requirement to add additional EUCs/meter IDs
No impacts to daily gas demand & UIG (assumption correct AQ/energy applied)
No impact to NTS sites (site CV applied)
No impact to energy balancing processes
CV not used for energy calculation of LDZ sites
BW, DES & DDP
Ability to identify an MPRN in a Decarb project
Reporting includes notification that an MPRN is in a Decarb project/ fuel type
CMS
Potential for minor impacts
Note: replacement CMS not yet assessed
UKLink File Flows
Change/new file to notify Shipper that an MPRN is on a Decarb project
Change to notify DN of a change on a decarb project
Change to flows notifying CDSP of the CV
Change to invoicing files to show CV Zone
Complexity Levels
No impact
Low
Medium
High
Note: Analysis carried out on current systems only, impacts on new systems not yet implemented TBD
Updated 5th January 2022

## Slide 33
Heat Map on DSC Business Processes
1. Maintain Gas Industry Stakeholders
Initial assessment does not identify any impacts unless separate contracts are required for blended/hydrogen gas
2. Maintain Supply Meter Point Register
Create Supply Meter Point & assign to LDZ/CV Zone
Maintain LDZ /CV Zone
Amend Supply Meter Point
Manage Supply Point Nomination
Manage Supply Point Confirmation
Manage Asset Change/Update
Generate portfolio
4. Settle Meter Point Consumption
Validate read & calculate Supply Meter Point energy
Validate consumption adjustment & calculate Supply Point energy
Calculate AQ
Reconcile Supply Point energy
7. Enable and Support Operational Processes
Provide Access to Data & Management Information
Manage Customer Contacts (queries)
3. Predict, Allocate & Balance Daily Energy
Validate CV
Gas Nominations
Gas Allocations
UIG
Energy balancing
5. Invoice & Collect Charges
Perform charge calculations
Issue Invoices
Complexity Levels
No impact
Low
Medium
High
Note: CDSP/DSC processes only have been assessed. Customer processes yet to be assessed
Updated 5th January 2022

## Slide 34: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS JAN 2022 - JAN 2024
January 2022

## Slide 35
Programmes & Projects 2022-2024 |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 – Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Hannah Reddy | Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Emma Catton | Single Sign on Experience |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | API Enhancements |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS JAN 2022 – JAN 2024
Design to PIS -Dec 21 to Feb 22 – Indicative timeline
Design to PIS – Sept 21 to May 22 – Indicative timeline
Design to PIS – Jan 22 to Apr 22 – Indicative timeline
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Testing – Dec 21 to Mar 22
PIS – From Apr 22 to Jun 22
Change Deployment
Apr 22
Pre-implementation/IDR
Mar 22 to Apr 22
Design to PIS - Nov 21 to Mar 22 – Indicative timeline

## Slide 36: Non-DSC Change Budget Impacting Programmes
CSSC Programme Update
Move to Cloud
CMS Rebuild Update

## Slide 37: CSSC Programme Dashboard
February 2022

## Slide 38
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme remains at a Green status and all Programme activities remain on track with all key internal and eternal milestones being met Xoserve raised a CR (CR-D129) to include an NFR to ensure all Secured Active Messages from CSS reach UK Link within a stipulated time following Gate Closure. Discussions have been held with Ofgem (details below) | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini: Based on the CSS design and the Programme testing carried out to date, normal operation should be satisfied from CSS with enough time to process secured active messages. However, there is a risk that some messages may be received late or in an extreme circumstance experience a system failure which could result in a disconnect. Following discussions with Ofgem, DCC/Landmark and ourselves have been instructed to look at exceptions processes and Service Management measures to mitigate the issue should it occur. An RTO of one hour was stipulated on CSS as part of design in DB4 requirements. This RTO will allow ensure CSS will be operational within an hour of any P1 failure, which in turn protects PUI processes as this will allow us to accept and process the secured active messages and keep systems in sync. It has recently come to our attention that the REC schedule pertinent to CSS is referring to an RTO of four hours rather than the one-hour RTO. This would mean that CSS has four hours to recover and if a failure was seen at gate closure Xoserve and other parties would not receive secured active messages within the expected NFR. We continue to work this through with the Central Programme and REC Transition: The Programme have approved 18th of July as the Go-live date. Transition Testing is being undertaken currently, with Transition Stage 2 being inflight. Xoserve have had 2 minor defects which have been addressed without any implications to timelines. Internal and external activities are now focussed on Business and Operational readiness. |  |  |  | Transition: Completion of transition testing stage 2 and commencement of stage 3. Operational Readiness: Planned activities are on track
e

## Slide 39: Move To Cloud Programme: Change Management Update
February 2022

## Slide 40: Move to Cloud Overview
First step of UK Link Road Map (XRN5245) was to re-platform the systems within current On Premise Data Centres to Cloud in order to achieve the following key objectives:
  Migrate our operating systems from Linux to Windows and UK Link system databases from Oracle to SQL Server
  Upgrade out of support technologies e.g. UKL Portal
  Decommission On Premise Data Centres for UK Link Systems
Key benefits identified as a result of completion of this change are:
  Keeping the infrastructure and Application in line with industry best practices and maintain the supportability
  Better ability to accommodate for change development and implementations
Progress and Timeline:
  Testing and Implementation Dress Rehearsals (IDRs) phases are currently planned to complete by 11th March 2022
  Testing is on track to complete as planned. IDR1 is currently in progress
  Implementation and Cutover is currently planned from 15th April to 19th April 2022 (Easter Weekend)
  Post Implementation Support is planned to commence from 19th April 2022 7:00 AM BST

## Slide 41: Summary
Move to Cloud has completed multiple rounds of testing and practice runs in the last 3 months culminating in the first Implementation Dress Rehearsal (IDR1)
The migration timelines, outages, process/file impacts to customers have now been understood as a result of this activity. The proposed Migration timelines over 2 weekends have been determined to minimise customer impacts for least disruption.
1st Implementation (Full UKLink)
Easter weekend (15th to 19th April 2022) is proposed for the majority of the cutover activities to prevent impact to normal business day processes for customers as the vast majority of files/processes run on supply point business days.
Fewer processes run on these (non business) days however, a small number of impacts have been highlighted in Slides 6-8* as they may have customer considerations or impacts. (for details, please refer to the detailed change pack being published).
Impacts to DES and Portal availability and use of Twilio services envisaged during Easter weekend
2nd Implementation (Part UKLink)
New UKLink Portal and DES screens proposed to cutover during 7th to 9th May 2022 (please refer to the previously issued Change Pack)
Impacts to DES and Portal availability and use of Twilio services over the cutover is envisaged during this period.
Full details of the impacts to different parties are to be included within a change pack for this committee’s consideration and approval.
* At the time of writing this pack, we are simulating IDR1 , more detail will be available post IDR1 and will be included in the Change Pack.
This communication is to the best of our knowledge pre IDR results and subject to change; this communication will be revised appropriately for the March 2022 Change Management Committee update.

## Slide 42: Next Steps
Send change pack outlining details of impacted files, processes and systems
March Change Management committee for approval.

## Slide 43: Appendices - Process/File Impact Summary

## Slide 44: Move to Cloud Implementation Activities
What are we doing?
  In order to progress Implementation and Cutover activities from On Prem Data Centre to the Cloud Data Centre, a planned extended outage from 15th April 9.00 to 19th April 2022 7:00 BST will be required.
  It is anticipated that minimal disruption will be caused as a result of this change, therefore Easter weekend has been chosen for the Cutover activities due to additional non business days.
  Services will resume as normal business day on 19th April (Tuesday) post maintenance at 7:00 BST
  We will continue to communicate via various forums.
How will this impact you?
  All external access to the online screens (via DES / Portal existing platform) will be unavailable during the window mentioned above.
  Some file flow impacts anticipated. Please refer to next slide for further information.
  Broadcast services via Twilio will be impacted during the migration period (more detail in the change pack)
  All inbound files will be held in a queue at our Enhanced File Transfer (EFT) interface to be processed as soon as migration activities are complete at various points during the Cutover period.
  Any impacts to files and reports being generated will be fully defined and confirmed post completion of IDRs as an update to this Change Management committee. Please refer to next slide for those that are known at this stage from various internal assessments.
* This communication is to the best of our knowledge pre IDR results and subject to change; this communication will be revised appropriately for the March 2022 Change Management Committee update.

## Slide 45
Market Participant(s) | Send/Receive files early | Delay in receiving outbound files/reports | Files not sent during migration period | Files to be sent On Time | Potential Rejections*
Shippers | MDR files will be sent out early (~1 hour earlier than scheduled on 15th April) | RAT; PRN; (Normal Schedule – sent out at~17:00 hours) LPA (to be issued from 23:00 hours on 15th April) (Normal schedule: sent out at ~16:30 from our systems) Modified Schedule: to be issued from 23:00 hours on 15th April | N/A | N/A | CNC*
GT/IGT or agents | N/A | PMN; (Normal schedule: sent out at ~17:00 from our systems) DNE; (Normal schedule: sent out at ~17:10 from our systems) Modified Schedule: to be issued from 23:00 hours on 15th April | N/A | N/A | N/A
DMSP | DLC morning files requested on time (files requested at usual time – a request to send no later than 08:30 a.m. schedule on 15th April) | N/A | Evening DLC delivery receipts not sent on 15th April | N/A | N/A
National Grid | N/A | CMA; COT; (Normal schedule: sent out at ~12:00 & 17:00 from our systems) Modified Schedule: to be issued from 23:00 hours on 15th April | CWF File due at 12:00 and 15:00 on 15th April will not be sent | CWF Files at 08:00 and 23:00 to be sent on time AIA On time | N/A
MAM | Low impact - TBC (in scope post November 2021 release implementation) |  |  |  | 
MAP | Low impact - TBC (in scope post November 2021 release implementation) |  |  |  | 
Key impacts to files during Move to Cloud Cutover
Notes:
*Please see slide 6 for mitigation actions
Xoserve communicating with DMSPs on DLC files
Any files and reports not referenced here will be delivered post cutover completion (estimated to be from 23:00 hours Saturday 15th of April 2022)

## Slide 46: Impacts contd..
What will you need to do ?
  Recognise the unavailability of the UK Link systems as per the previous slides.
  Please advise your teams of the outage as appropriate to avoid raising tickets during the migration period
  Ensure inbound files contain standard BAU volumes during Easter weekend, 14th and 19th April 2022 (Please refer to the next slide for known file flow impacts over the period)
  Where an action for industry has been identified and you have queries, please contact the project team for further help.
  Note the request for sending a limited set of files earlier than usual on 15th of April (Shippers and DMSPs only)
  Potential mitigation against CNC file rejections (Shippers only) – Shippers are requested to mitigate against rejections for any CNC files sent on 15th April by issuing the file with an effective date greater or equal to 16th April in order to avoid system rejections (files will be processed late)
  Recognise that any reports due over the Easter weekend (including bank holidays) will be processed later than normal and are expected to be sent out to relevant parties post 7 a.m. Monday 18th of April 2022
  Next Steps
  We will continue to notify any changes via various forums
  Contact for any queries. .box.xoserve.uklinkroadmapprogramme@xoserve.com

## Slide 47: Portal Go Live - impacts
What are we doing?
  To complete implementation and cutover activities for the new DES & Portal screens, these systems will be unavailable for use from 09:00 on the 7th May 2022 until 07:00 on the 9th May 2022.
How will this impact you?
  All DES & portal screen will be unavailable during the window above. This will not impact other activities such as inbound file processing.
  All users will be migrated to the new portal and will receive an email approximately 1 week prior to this with their temporary password - this is only required for the initial logon.
What will you need to do?
  Recognise unavailability of the UK Link systems as per above update.
  Please advise your teams of the outage as well to avoid raising tickets.
  Users to login through the newly generated temporary password (emailed beforehand)
  Next Steps
  We will continue to notify any changes via various forums
  Contact for any queries. .box.xoserve.uklinkroadmapprogramme@xoserve.com

## Slide 48: CMS Rebuild
Update

## Slide 49: Progress to Date
CoMC were presented with two options on 21/12/21:
  Option 1 - Correla Product with an Xoserve Subscription
  Option 2 - DSC Investment – fully funded by DSC customers
CoMC voted for option 1, full presentation and minutes can be found here: https://www.gasgovernance.co.uk/dsc-contract/211221
Since then, the Product Team have been mobilising and scoping the services that will be delivered in Release one in Q4 of 2022.
Dedicated ”Customer focus groups" will be set up to ensure customers remain engaged throughout
Further updates will be provided in March ChMC

## Slide 50: Section 6: Any Other Business
KVI Customer Change Survey

## Slide 51: KVI Customer Change Survey
We would like to request your feedback on our Change Management performance
The scope of your feedback should include changes that we have developed and delivered for DSC customers within the last quarter. As a reminder, please see below a summary of the changes we have supported our customers in developing and delivering during this period;
Full Details
You can give your feedback through this Survey
Chart: Q3 Number of Changes Developed and Delivered
| Regulatory Modifications | Change Development | Analysis Implemented | Change Implemented
No. worked on | 11 | 8 | 2 | 13

## Slide 52: APPENDIX

## Slide 53: Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
XRN 5339 | EFT | 27/02/2022 | 04:45 | 27/02/2022 | 09:00 | EFT Upgrade PROD interim upgrade The first change will upgrade the existing application version from 7.4.10 to 7.4.13. As part of this change, an extended outage is needed to complete the Production upgrade activities. This extended outage is being scheduled for Sunday 27th February and will be aligned to the UKLink maintenance window in order to cause minimum disruption to the services. During the outage all files will be put on hold whilst upgrade activities are completed. Once the upgrade is complete all files and systems will continue to perform as usual. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 6th March. | 13/10/2021 Times and description updated 09/02/2022
XRN 5339 | EFT | 13/03/2022 | 05:45 | 13/032022 | 10:30 | EFT Upgrade File share operation system upgrade We will then upgrade the windows operating system (OS) of the EFT file share server, and an extended outage is expected to complete this upgrade activity. During the outage all files will be put on hold whilst upgrade activities are completed. Once the upgrade is complete all files and systems will continue to perform as usual. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 20th March. | 13/10/2021 Times and description updated 09/02/2022
XRN 5339 | EFT | 20/03/2022 | 04:45 | 20/03/2022 | 09:00 | Following successful implementation of the previous EFT upgrade implementations above, this change will see the EFT application version upgraded from 7.4.13 to 8.0.5, this will complete the final step in the EFT upgrade implementations. As part of this change, an extended outage is required to complete the production upgrade activities. This extended outage is being scheduled for Sunday 20th March and will be aligned to the UKLink maintenance window in order to cause minimum disruption to the services. Any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 27th March. | 13/10/2021 Times and description updated 09/02/2022
XRN 5339 | EFT | 26/03/2022 | TBC | 27/03/2022 | TBC | EFT Upgrade DR Testing As part the Enhanced File Transfer (EFT) upgrade project, we will conduct Disaster Recovery (DR) testing. The EFT DR test will prove and confirm the procedures, resilience and capability of the newly upgraded EFT. As EFT runs across two sites, we will fail over to one site then failback to service normal and test the other site the following week. During the outage all files will be put on hold whilst all upgrade activities are completed. Once complete all files and systems will continue to perform as usual. Timescales for the extended outage are currently under review and will be notified as soon as available. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 5th & 6th April. | 09/02/2022 New

## Slide 54: Portfolio POAP

## Slide 55: CSSC Programme Dashboard
February 2022

## Slide 56
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme remains at a Green status and all Programme activities remain on track with all key internal and eternal milestones being met Xoserve raised a CR (CR-D129) to include an NFR to ensure all Secured Active Messages from CSS reach UK Link within a stipulated time following Gate Closure. Discussions have been held with Ofgem (details below) | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini: Based on the CSS design and the Programme testing carried out to date, normal operation should be satisfied from CSS with enough time to process secured active messages. However, there is a risk that some messages may be received late or in an extreme circumstance experience a system failure which could result in a disconnect. Following discussions with Ofgem, DCC/Landmark and ourselves have been instructed to look at exceptions processes and Service Management measures to mitigate the issue should it occur. An RTO of one hour was stipulated on CSS as part of design in DB4 requirements. This RTO will allow ensure CSS will be operational within an hour of any P1 failure, which in turn protects PUI processes as this will allow us to accept and process the secured active messages and keep systems in sync. It has recently come to our attention that the REC schedule pertinent to CSS is referring to an RTO of four hours rather than the one-hour RTO. This would mean that CSS has four hours to recover and if a failure was seen at gate closure Xoserve and other parties would not receive secured active messages within the expected NFR. We continue to work this through with the Central Programme and REC Transition: The Programme have approved 18th of July as the Go-live date. Transition Testing is being undertaken currently, with Transition Stage 2 being inflight. Xoserve have had 2 minor defects which have been addressed without any implications to timelines. Internal and external activities are now focussed on Business and Operational readiness. |  |  |  | Transition: Completion of transition testing stage 2 and commencement of stage 3. Operational Readiness: Planned activities are on track
e

## Slide 57: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | UEPT/E2E support continues
 |  | Testing | UEPT low priority testing continues. This will conclude at the end of February
 |  | Service Management | Continued operational readiness support. Internal workshops being held with relevant business teams to continue to work through scenarios in readiness for early life support and Go Live
 |  | Batch | All internal activities are on track and being managed across workstreams as well as working with other Programmes where activities require monitoring and regression tests following Programme CR releases
 |  | Gemini | Readiness for Go Live activities are being undertaken
 |  | Reporting | Continued review and awareness sessions being held with the wider business as part of our business change activities
 |  | UK Link | We continue to work on the approval and implementation of internal CR’s within the Programme release timelines

## Slide 58: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC version 3 consultation is complete.
 |  | Data | REL Cycle 5 has been delivered to Landmark in advance of the delivery milestone. Landmark are working on providing the REL cycle 4 analysis reports. Once analysed we will issue to the wider industry for industry cleanse. Continue to work with transition workstream for planning for cutover and transition.
 |  | Environments | All activities continuing to track to plan for all upcoming activities. Environment readiness for Transition is in progress. Environment requirements will continue to be assessed in line with the Cloud Programme for combined activities.
 |  | MAP C (XRN-4780C) | Successfully implemented as part of the November 21 release (Go-Live in January 22)
 |  | SoLR (XRN-5144) | Industry consultation concluded. Chosen SOLR option to be implemented
 |  | Transition | Transition Testing on track to schedule. All activities continue to be on track

## Slide 59: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Discussed at Delivery Group 25/01. Minutes pending. | 01/03/22
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | MDD data cleansing is with Customer Advocates to process. Additionally, further work is ongoing on REL reports | 18/07/22
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | DCC engagement with DCC will ramp up in 2022 we will ensure reporting requirements are on the agenda | 25/02/22
64002 |  | Programme | There is a risk that ongoing pipeline of customer driven and regulatory change within the industry could impact the CSSC and wider Switching Programme delivery because of technical conflict with the design of other changes and demand on resources across Xoserve and the customer teams involved in Switching Programme delivery leading to additional regression testing activity, CRs raised to modify solutions already developed and tested by the programme, delays to the overall Switching Programme, and therefore unplanned costs for Xoserve. | 1. Discuss the potential for change moratoria with Ofgem that could restrict the volume of change being made and in particular mitigate some of this risk in relation to coding impacts 2. Investigate the availability of and if necessary invest in tooling to support more enhanced branching and merging in terms of development to mitigate the technical impact of any non-CSSC changes. 3. Work with the SI to monitor for any potential impact on programme resources, including customer resources, that may result from change initiatives running in parallel with critical path Switching Programme phases. | SoLR impacts could manifest itself during the upcoming months - continues to be monitored | 31/03/22
65122 |  | Transition/ Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all programme work groups to monitor and mitigate this risk. | Continue to monitor, low exposure at this point | 28/02/22
66480 |  | Programme | There is a risk that the Go Live date could be pushed out further because of the current market situation in the Gas Industry with suppliers going out of business leading to additional cost to the programme, significant re-planning and impacts to other Correla initiatives | Regular communication with OFGEM to understand their strategy to address this issue | Continues to be monitored | 21/01/22

## Slide 60: Key Programme Risks (2/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
66599 |  | Programme | There is a risk that the Transition phase of the Switching Programme may be adversely impacted as a result of SoLR activities consuming the focus and efforts of Business and Operational teams who had been planned to be focused on Switching Programme Transition activities leading to a potential impact to Transitional activities as planned currently (March 2022) | Liaise with Switching Programme stakeholders to agree mitigations | Continues to be monitored | 28/02/22
66906 |  | Programme | There is a risk that UK Link may become out of sync because CSS may send secure active messages later than expected (circa 5:35pm) because of any upstream delays from CSS leading to a data mismatches between UK Link and CSS and more importantly Gemini and settlement issues which are incredibly difficult to correct. | - Xoserve have raised CR-D129 to mitigate this risk. - Discussions ongoing with programme stakeholders | Session undertaken with Ofgem with actions in place. This will be tracked until mitigation actions are completed | 31/01/22
66907 |  | Programme | There is a risk that the SLAs stipulated with the CSS NFRs (1 Hr RTO) will not be met post CSS Go-live because REC is using the Switching BCDR document as the base for REC Service Definitions which has a 4 hour RTO defined with a maximum time of 8 hours for CSS to come back into operation leading to a massive impact on UK Link downstream processing, particularly with Gemini and settlement | This is being raised with REC and relevant Ofgem stakeholders | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 31/01/22
66908 |  | Programme | There is a risk that the industry has not defined and agreed joint processes should key central components such as CSS go down during key times in the day (e.g. Gate Closure) because CSS BC/DR processes have been approved without addressing the queries and caveats called out during the consultation process leading to the possibility that should a DR event occur, downstream impacts are not understand or mitigated | This will be raised with REC and Ofgem | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 28/02/22

## Slide 61
High Level Plan

## Slide 62: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect newupdated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | £18,500.00 | 26/11/2021 | Approved - Internal CR Created

## Slide 63: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 64: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact

## Slide 65
CR Name | CR Ref | Date Raised | Status
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Withdrawn
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)

## Slide 66
CR Name | CR Ref | Date Raised | Status
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Complete - No Xoserve Impact
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)