## Slide 1: Move To Cloud Programme: Change Management Update
February 2022

## Slide 2: Move to Cloud Overview
First step of UK Link Road Map (XRN5245) was to re-platform the systems within current On Premise Data Centres to Cloud in order to achieve the following key objectives:
  Migrate our operating systems from Linux to Windows and UK Link system databases from Oracle to SQL Server
  Upgrade out of support technologies e.g. UKL Portal
  Decommission On Premise Data Centres for UK Link Systems
Key benefits identified as a result of completion of this change are:
  Keeping the infrastructure and Application in line with industry best practices and maintain the supportability
  Better ability to accommodate for change development and implementations
Progress and Timeline:
  Testing and Implementation Dress Rehearsals (IDRs) phases are currently planned to complete by 11th March 2022
  Testing is on track to complete as planned. IDR1 is currently in progress
  Implementation and Cutover is currently planned from 15th April to 19th April 2022 (Easter Weekend)
  Post Implementation Support is planned to commence from 19th April 2022 7:00 AM BST

## Slide 3: Summary
Move to Cloud has completed multiple rounds of testing and practice runs in the last 3 months culminating in the first Implementation Dress Rehearsal (IDR1)
The migration timelines, outages, process/file impacts to customers have now been understood as a result of this activity. The proposed Migration timelines over 2 weekends have been determined to minimise customer impacts for least disruption.
1st Implementation (Full UKLink)
Easter weekend (15th to 19th April 2022) is proposed for the majority of the cutover activities to prevent impact to normal business day processes for customers as the vast majority of files/processes run on supply point business days.
Fewer processes run on these (non business) days however, a small number of impacts have been highlighted in Slides 6-8* as they may have customer considerations or impacts. (for details, please refer to the detailed change pack being published).
Impacts to DES and Portal availability and use of Twilio services envisaged during Easter weekend
2nd Implementation (Part UKLink)
New UKLink Portal and DES screens proposed to cutover during 7th to 9th May 2022 (please refer to the previously issued Change Pack)
Impacts to DES and Portal availability and use of Twilio services over the cutover is envisaged during this period.
Full details of the impacts to different parties are to be included within a change pack for this committee’s consideration and approval.
* At the time of writing this pack, we are simulating IDR1 , more detail will be available post IDR1 and will be included in the Change Pack.
This communication is to the best of our knowledge pre IDR results and subject to change; this communication will be revised appropriately for the March 2022 Change Management Committee update.

## Slide 4: Next Steps
Send change pack outlining details of impacted files, processes and systems
March Change Management committee for approval.

## Slide 5: Appendices - Process/File Impact Summary

## Slide 6: Move to Cloud Implementation Activities
What are we doing?
  In order to progress Implementation and Cutover activities from On Prem Data Centre to the Cloud Data Centre, a planned extended outage from 15th April 9.00 to 19th April 2022 7:00 BST will be required.
  It is anticipated that minimal disruption will be caused as a result of this change, therefore Easter weekend has been chosen for the Cutover activities due to additional non business days.
  Services will resume as normal business day on 19th April (Tuesday) post maintenance at 7:00 BST
  We will continue to communicate via various forums.
How will this impact you?
  All external access to the online screens (via DES / Portal existing platform) will be unavailable during the window mentioned above.
  Some file flow impacts anticipated. Please refer to next slide for further information.
  Broadcast services via Twilio will be impacted during the migration period (more detail in the change pack)
  All inbound files will be held in a queue at our Enhanced File Transfer (EFT) interface to be processed as soon as migration activities are complete at various points during the Cutover period.
  Any impacts to files and reports being generated will be fully defined and confirmed post completion of IDRs as an update to this Change Management committee. Please refer to next slide for those that are known at this stage from various internal assessments.
* This communication is to the best of our knowledge pre IDR results and subject to change; this communication will be revised appropriately for the March 2022 Change Management Committee update.

## Slide 7
Market Participant(s) | Send/Receive files early | Delay in receiving outbound files/reports | Files not sent during migration period | Files to be sent On Time | Potential Rejections*
Shippers | MDR files will be sent out early (~1 hour earlier than scheduled on 15th April) | RAT; PRN; (Normal Schedule – sent out at~17:00 hours) LPA (to be issued from 23:00 hours on 15th April) (Normal schedule: sent out at ~16:30 from our systems) Modified Schedule: to be issued from 23:00 hours on 15th April | N/A | N/A | CNC*
GT/IGT or agents | N/A | PMN; (Normal schedule: sent out at ~17:00 from our systems) DNE; (Normal schedule: sent out at ~17:10 from our systems) Modified Schedule: to be issued from 23:00 hours on 15th April | N/A | N/A | N/A
DMSP | DLC morning files requested on time (files requested at usual time – a request to send no later than 08:30 a.m. schedule on 15th April) | N/A | Evening DLC delivery receipts not sent on 15th April | N/A | N/A
National Grid | N/A | CMA; COT; (Normal schedule: sent out at ~12:00 & 17:00 from our systems) Modified Schedule: to be issued from 23:00 hours on 15th April | CWF File due at 12:00 and 15:00 on 15th April will not be sent | CWF Files at 08:00 and 23:00 to be sent on time AIA On time | N/A
MAM | Low impact - TBC (in scope post November 2021 release implementation) |  |  |  | 
MAP | Low impact - TBC (in scope post November 2021 release implementation) |  |  |  | 
Key impacts to files during Move to Cloud Cutover
Notes:
*Please see slide 6 for mitigation actions
Xoserve communicating with DMSPs on DLC files
Any files and reports not referenced here will be delivered post cutover completion (estimated to be from 23:00 hours Saturday 15th of April 2022)

## Slide 8: Impacts contd..
What will you need to do ?
  Recognise the unavailability of the UK Link systems as per the previous slides.
  Please advise your teams of the outage as appropriate to avoid raising tickets during the migration period
  Ensure inbound files contain standard BAU volumes during Easter weekend, 14th and 19th April 2022 (Please refer to the next slide for known file flow impacts over the period)
  Where an action for industry has been identified and you have queries, please contact the project team for further help.
  Note the request for sending a limited set of files earlier than usual on 15th of April (Shippers and DMSPs only)
  Potential mitigation against CNC file rejections (Shippers only) – Shippers are requested to mitigate against rejections for any CNC files sent on 15th April by issuing the file with an effective date greater or equal to 16th April in order to avoid system rejections (files will be processed late)
  Recognise that any reports due over the Easter weekend (including bank holidays) will be processed later than normal and are expected to be sent out to relevant parties post 7 a.m. Monday 18th of April 2022
  Next Steps
  We will continue to notify any changes via various forums
  Contact for any queries. .box.xoserve.uklinkroadmapprogramme@xoserve.com

## Slide 9: Portal Go Live - impacts
What are we doing?
  To complete implementation and cutover activities for the new DES & Portal screens, these systems will be unavailable for use from 09:00 on the 7th May 2022 until 07:00 on the 9th May 2022.
How will this impact you?
  All DES & portal screen will be unavailable during the window above. This will not impact other activities such as inbound file processing.
  All users will be migrated to the new portal and will receive an email approximately 1 week prior to this with their temporary password - this is only required for the initial logon.
What will you need to do?
  Recognise unavailability of the UK Link systems as per above update.
  Please advise your teams of the outage as well to avoid raising tickets.
  Users to login through the newly generated temporary password (emailed beforehand)
  Next Steps
  We will continue to notify any changes via various forums
  Contact for any queries. .box.xoserve.uklinkroadmapprogramme@xoserve.com