## Slide 1: Dec 21 - April 22 Changes in Design – Shipper Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) |  |  |  | Change Pack approved at ChMC on 11/05/22
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | June 2022 - Approval |  |  | Change Pack deferred at ChMC on 11/05/22 to include consultation comments into Change Pack Seeking approval at ChMC on 08/06/22
XRN4992B - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | June 2022 - Approval | Risk ID 67431: There is a risk that a MOD may be raised to include IGT sites into SoLR charging. e Mitigation: Accept risk. Design will be completed as per the current scope and has been issued for consultation in May 2022. This will not form part of any Nov22 Release. |  | Change Pack issued to ChMC for consultation on 16/05/22 Seeking approval at ChMC on 08/06/22
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | June 2022 – Consultation​ ​July 2022 - Approval |  |  | Change Pack submission date revised to 13/06/22 as quality criteria for submission not met Seeking approval at ChMC on 13/07/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | June 2022 – Consultation July 2022 - Approval |  |  | Change Pack submission date revised to 13/06/22 as quality criteria for submission not met Seeking approval at ChMC on 13/07/22
Slide updated on 26th May 2022
Notes: u

## Slide 2: Dec 21 - April 22 Changes in Design – DN Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4900 - Biomethane/Propane Reduction | May 2022 – Consultation ​June 2022 - Approval | Risk ID 67731: There is a risk that the physical works required on Customer site will not be completed in line with a Nov 22 Release Date. Mitigation: Align to a future release post Nov22 release |  | Change Pack issued to ChMC for consultation on 16/05/22 Seeking approval at ChMC on 08/06/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | June 2022 – Consultation July 2022 - Approval |  |  | Change Pack submission date revised to 13/06/22 as quality criteria for submission not met Seeking approval at ChMC on 13/07/22
XRN5298 - H100 Fife Project – Hydrogen Network Trial | June 2022 - Approval | Issue ID 67645: The detailed design change pack was not be approved as MOD0799 is still outstanding​ Mitigation: Accept risk. Decision will be taken at ChMC in June as to whether this will be taken into delivery for Nov22. Risk ID 67482: There is a risk that the CV range will not be updated for hydrogen because a change is required to Gemini leading to the CV for hydrogen being rejected Mitigation: Monitor change request to be raised by SGN and align to implementation release for this change. |  | Change Pack deferred at ChMC on 11/05/22 as UNC MOD0799 is still under consultation Seeking approval at ChMC on 08/06/22
Slide updated on 26th May 2022