## Slide 1: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Deferred Changes: Post Implementation Support completed for XRN 4780C to plan Data cleanse for XRN5072 completed XRN4992a: Post Implementation Support on track to complete on 26/05 Issue identified with the level of aggregation in the RTB invoice, fix identified and build/test in progress, deployment planned for 27/05 XRN5188b: Post Implementation Support on track to complete on 26/05 MAP ID data interim load on track to complete by 25/05 CCR planned to be presented in July ChMC Decision in June ChMC: None |  | XRN5289 | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope - XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope - XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope - XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process In Scope - XRN5188b - Interim Data Loads of MAP Id into UK Link Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 25th May 2022
Complete
On Track
At Risk
Overdue
Not Baselined