## Slide 1: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking Amber, Start up and initiation phase is in progress. Build commenced on 28th November and is in progress. ​Progress update:​ Start Up and Initiation phase is currently in progress all documents being produced including the detailed project plan that underpins the high-level timeline Build phase commenced on 28th December on track for completion 10/02/23 System Testing scenarios review in progress, approval expected 06/01/23 Return to Green: Approved detailed project plan expected 30th December Decision in January ChMC: None |  | Implementation date of 24th June; with a contingency implementation date of 1st July | 
Risks and Issues | None to raise |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  | 
Slide updated on 20/12/2022
Complete
On Track
At Risk
Overdue