## Slide 1: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber. Design phase continues for all three XRNs scoped for this release. Build completed as planned for 5379 and 5472 but this is at risk due to status of design. Testing is underway for 5379 and 5472. Return to green is completion of design as planned and approved detailed project plan for delivery including touch-points with DM and NDM service providers. Progress update: UK Link build complete as planned for 5379 and 5472, build for 5143 due to commence this week DM and NDM SP onboarding activities preparation underway Engagement with the service provider continues for 5379 including resolving of design queries Project in startup and initiation phase including development of detailed project plan. PID, comms plan and RACI have been approved. Decision in February ChMC: Approval is being sought to descope 5472 from March-23 due to the weather data supplier making available the file based solution for long enough to allow Xoserve to move to their strategic platform in one implementation as opposed to two implementations in 2023 |  | Implementation date of 25th March with a go-live of 1st April, the contingency implementation date is 1st April with a go-live of 1st April | 
Risks and Issues | 68566 (I) Delay to test commencement for March-23 impacting delivery plan, work underway to mitigate this before using available contingency 68488 & 68489: (R) The design has not yet completed for the changes in this release, therefore the aspirational delivery timescales are at risk 68126: (R) The NDM service provider (SP) is not yet agreed, until the NDM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April 68498: (R) The DM SP is agreed, but not yet fully engaged, until the DM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) XRN5472 - Creation of a UK Link API to consume daily weather data for Demand Estimation processes |  |  | 
Slide updated on 24th January 2022
Complete
On Track
At Risk
Overdue