## Slide 1: REC Change
8th March 2023

## Slide 2: Introduction
The following 9 slides have been included in this months ChMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review by REC Code Managers – due to CM workload/prioritisation
This month we have included a line describing, from our perspective, the expected Change impact on us as the CDSP and/or GRDA
Note: We are currently undertaking a review of all REC Change and have began removing Changes which we have confirmed have no impact to Gas services. In the coming months, we will continue to monitor the Changes listed and add/remove from this pack as required.
We have included an additional slide at the end of this pack which outlines the approach to be taken regarding resources to account for the increase in REC Change, as requested by the committee last month.
Further information on the Changes can be found on the REC Portal

## Slide 3: Overview of In Progress REC Changes (high level)
Chart: 
| Approved awaiting implementation | Consultation | Solution development | Party Impact Assessment | Final Assessment | New
In Progress | 4 | 1 | 3 | 1 | 2 | 1
Chart: All Change
| Monitoring | Currently working on | Upcoming activity | XRN Changes
All Change | 2 | 5 | 3 | 2
In Progress Change
6

## Slide 4: REC Change Pipeline – In progress
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0025 | Service Provider Performance Charges (DCC) | N/A | Deloitte (RPA) | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | Standalone | High | 
This Change was raised to introduce Service Provider Performance Charges linked to performance against service levels defined in the REC. We are monitoring this change as it references future performance charges on other service providers – including the GRDS. |  |  |  |  |  |  |  |  | 
R0047 | Metering Code of Practice Consolidation Review | N/A | RECCo | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | Standalone | High | N/A
This Change was raised to to consolidate the current Metering Codes of Practice into a single set of arrangements. Although we are not a directly impacted party, if and when this takes place, we may need to adapt our interactions with MEMs, DNOs and Suppliers. |  |  |  |  |  |  |  |  | 
R0052 | GES Service Definition Document | N/A | Deloitte | GES | Approved - awaiting implementation | 24/02/2023 – Proposed Implementation date | Major, Feb 23 | Medium | N/A
This Change was raised to align the frequency of certain reports detailed in the GES Service definition with the Retail Energy Code. As the GES Service provider, we need to monitor the outputs of this Change to ensure that everything is aligned following implementation. |  |  |  |  |  |  |  |  | 
Please note that we have provided our view of the Change summary and impacts however we recommend that DSC Customers monitor the REC Portal to form their own opinion regarding the impact to their organisation
Currently working on
Key:
Upcoming
Monitoring

## Slide 5
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0055 | Switching Operator Outage Notification Lead Time | XRN 5595 | DCC | GRDS, GES | Approved - awaiting implementation | 24/02/2023 – Proposed Implementation date | Major, Feb 23 | Medium | N/A
This is a documentation Change that was raised to align the outage notification time. The original time was 10 working days (WD) however in the CSS Provider’s (DCC) processes and the Switching Operator Change Management Process Category 3 document the notification time is 8 WD. As a result of this Change, as a Switching Data Service Provider, we need to amend internal documents that include processes surrounding interactions with the CSS Provider, to allow for the revised 8WD notice. |  |  |  |  |  |  |  |  | 
R0063 | Addition of key information to all Service Now tickets | N/A | St Clements Ltd (on behalf of DNOs) | - | Solution development | 21/02/2023 – Presenting solution to the Change Panel | TBC | Medium | N/A
This Change was raised to improve the information that’s included on DCC’s Service Now Tickets which have been asynchronously rejected. We interact with DCC via SNow so we need to monitor and input into development. |  |  |  |  |  |  |  |  | 
R0067 | Introduction of CSS refresh functionality | XRN 5567 / UNC Mod expected | Capgemini (RTS) | GRDS | Party Impact Assessment | 01/03/2023 – Detailed Impact Assessment closeout (this is the 2nd DIA that has been released as a result of replanning) | Legal text – Major, June 23 Technical Change - Standalone | High | 
This Change will introduce a resend and refresh functionality to help with the message interactions between the CSS and Switching Data Service Providers. Currently, there are cases were messages are being received after Gate Closure or not being received at all. We are one of the impacted Service Providers which means this Change is very important to us so that we are able to complete customer switches successfully. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring

## Slide 6
Currently working on
Key:
Upcoming
Monitoring
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0070 | Provision of Enduring Test Environments | N/A | Capgemini | GRDS, GES | Solution Development | 02/2023 – Awaiting Impact Assessment from Code Managers | Standalone | High | N/A
This Change was raised to introduce an obligation under the Retail Energy Code for the CSS or the Switching Operator (SO) to provide enduring test environments for REC parties to make the necessary system changes for REC Change Proposals (CPs) or internal system updates. We need to monitor this to ensure that the obligations on GRDS are understood, and that we contribute to the development of this Change. |  |  |  |  |  |  |  |  | 
R0073 | Introduction of a Housekeeping Change Proposal Process | N/A | Gemserv | - | Final Assessment | 24/02/2023 – Consolidated Consultation Response and Final Change Report published | TBC | Low | N/A
This Change was introduced to create a process which allows parties to amend typographical errors, formatting, and consistency errors (such as Paragraph numbering), out-of-date references to documents and updating addresses (including email) in the Retail Energy Code. Although it is a housekeeping Change, there are also amendments to legal text that we need to be involved in. Its important we monitor the outputs of this Change to capture any amendments that might be needed to our internal documents as a result, or if it creates inadvertent Change. |  |  |  |  |  |  |  |  | 

## Slide 7
Currently working on
Key:
Upcoming
Monitoring
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0074 | Release of Community View Data Items to MEMs in GES | N/A | Xoserve | GES | Final Assessment | 24/02/2023 - Changes to the DAM 27/02/2023 – Functional Change planning | Changes to the DAM – Major, Feb 23 Functional Change - TBC | High | 
This Change was raised to enable MEMs to ‘Community View’ access to a limited set of data in the GES, for sites where they are not the appointed MEM. As the GES Provider we are heavily involved in the planning and delivery of this Change. |  |  |  |  |  |  |  |  | 
R0091 | Clarifications to the Theft Detection Incentive Scheme | XRN 5236 MOD 0734 | Deloitte (RPA) | - | Consultation | 10/03/2023 – Consultation closeout | TBC | Low | N/A
Following implementation of UNC Mod 0734 the RECCo are responsible for providing details of Confirmed Theft to the CDSP. We expect this to be the REC change that implements this obligation. |  |  |  |  |  |  |  |  | 

## Slide 8
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority | Attachments
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | N/A | DCC | - | Solution development | 10/03/2023 -Preliminary Change Report and consultation closeout | TBC | Low | 
Currently, the CSS Provider is obligated to undertake system organisation control type 2 (SOC2) assessments on the CSS’s cloud-based infrastructure. This Change was raised to assess if the SOC2 assessment provides a proportionate level of assurance or the best value for money and if it should be change to ‘independently assessed’. We are monitoring to determine whether there are impacts to GRDS / GES. |  |  |  |  |  |  |  |  | 
R0088 | Make Shipper NExA values available on the GES portal | XRN 5186 MOD 0701 | Xoserve | - | New | w/c 27/02/2023 – Lead analyst being assigned 02/2023 - Impact assessment | Major, June 23 to align with | Medium | 
XRN 5186 - Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs makes additional information available to GES Users which require reflection in the REC. Although all of the technical change has already been developed. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
REC IA Demand

## Slide 9
REC Related XRN Changes
Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority
Processing of CSS Switch Requests Received in ‘Time Period 5 | XRN 5535A | Xoserve | GRDS | In Delivery | 13/03/2023 – Detailed Design Change Pack for approval | TBC | High
Resolution of Address Interactions between DCC and CDSP | XRN 5546 | Xoserve | GRDS | Under development | Regular conversations with DCC as work is ongoing | TBC | Medium
Currently working on
Key:
Upcoming
Monitoring

## Slide 10: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment
R0056 | EES/GES additional service request for Housing Associations to be added to the Matrix | Initial Assessment
R0059 | Maintenance of Qualification Schedule Change | Initial Assessment
R0068 | REC Data Protection Changes | Initial Assessment
R0069 | Amendments to Sample Access Agreement | Initial Assessment
R0071 | DCC access to EES and GES | Initial Assessment
R0075 | Enabling Software Product Qualification | Initial Assessment
R0080 | Improvements to "Failed to deliver" CSS messages | Initial Assessment
R0081 | CSS Market message retry strategy | Initial Assessment
R0082 | Formalising the Submission of PPMIP Unallocated Transaction Report (UTR) Files | Initial Assessment
R0084 | Housekeeping changes to the approved legal text for R0047 | Initial Assessment
R0085 | Switching Programme Designation of the Steady State Commencement Date | Initial Assessment
R0087 | MAP GES data access | Initial Assessment

## Slide 11: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0089 | Removal of Pre-COVID AQ Value from Data Access Matrix | Initial Assessment
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | Initial Assessment
R0093 | Uplift to CSS Maximum Demand Volumes during MHHS Migration Period | Initial Assessment
R0094 | Clarify obligations on gas meter exchanges that occur close to CoS | Initial Assessment
R0095 | Changes to allow DNOs to reinstate disconnected MPANs | Initial Assessment
R0096 | CSS Message Regeneration Functionality | Initial Assessment
R0097 | Consequential Change for CSS Smart Meter Data Retriever Appointments | Initial Assessment

## Slide 12: For Information
Background
In October-22, ChMC agreed to include 350k in BP23 (within the General Change budget) for use against REC Change, specifically to mitigate against the expected increase in REC Change demand, as at the time, this was unknown.
Forward Projections
The REC have advised that this upward trend is not looking to tail off but potentially increase further as the year progresses, as well as expressing the desire for increased engagement with the development of change.
Observations
In recent months, we’ve seen the number of REC Change Requests being raised exceed even the expected increase, with a large number awaiting initial assessment by the REC Code Manager.
DSC Risk
As a result, without increasing resources to carry out impact assessments, DSC change development will suffer and get deprioritised or even cease entirely as REC change takes priority.
Driver
This includes an increasing backlog on Gas related change proposals that ultimately will require varying levels of Impact Assessments to be carried out by the CDSP within the formal timescales set out in the REC.
Mitigation
CDSP will, from April-23, drawdown on the General Change budget (BP23) to increase its ability to progress REC Impact Assessments ensuring its continued conformity to regulatory obligations, while still being able to develop DSC related change.