## Slide 1: June 23 Release Scope Deferral Impact Assessment
ChMC Decision Required

## Slide 2
Impact Assessment - Deferring Implementation of XRN5186
Background
Northern Gas Networks have requested an impact assessment be undertaken by the June-23 Project Team to assess what options are available if XRN5186 (MOD0701) is deferred and implemented at a later date
Assumption
Four options have been identified and were considered within this Impact Assessment
The options and costs provided have considered an alternative implementation date for the related June-23 scope
Considerations
Impacts on Release capacity for November-23 have not been assessed at this stage
Potential that moving June-23 could lead to delay in delivery of other DSC change
Increase risk profile of November-23 if multiple changes are progressed in tandem
Options
Remove XRN5186 from June-23 Release after completion of related project deliverables up until 28/04
Remove XRN5186 from June-23 Release after completion of related project deliverables up until 09/06
Stop the delivery of June-23 Release after completion of all project deliverables up until 28/04
Stop the delivery of June-23 Release after completion of all project deliverables up until 09/06
*Options 1 and 3 were assessed but discounted as no benefit could be identified in stopping project activities earlier than is necessary to achieve the objective – i.e. both prevent project deliverables from being progressed and completed earlier than is necessary

## Slide 3
Impact Assessment – Project Plan Option Timeline
The above plan reflects that both Option 2 (Defer XRN5186) and Option 4 (Defer XRN5186 & XRN5091) would stop circa 9th June 2023
Performance Testing, Implementation Dress Rehearsals, Implementation and Post Implementation Support activities would need to be planned for delivery at a later date

## Slide 4
Options | Description | Pros | Cons | Activities required if deferred
Remove XRN5186 from June23 Release after completion of Regression Test phase *Xoserve Recommended Option* | This option will look to complete all testing (excluding Performance Test) prior to removing XRN5186 from the Release. Any outstanding activities and implementation of XRN5186 to take place at a later date De-scoped change work would stop approx. 09/06/23 | All test phases will be completed except Performance Test. Build and all test will be complete for AMT Market Flow and Gas Enquiry Service Provides additional opportunity for all DNs and Shippers to align their NExA and Capacity values Developed system code will remain stable in project track whilst alternative delivery date is confirmed Allows XRN5091 to progress and avoid delay of Shipper benefitting change Minimises regret spend to customers by proceeding with delivery of XRN5186 as far as reasonably possible whilst also delivering XRN5091 | Will lead to additional work to re-plan delivery of XRN5186 Checks will need to be performed against system code to ensure tested solution remains fit for purpose Possible risk of additional test activities (e.g. Regression Testing) Risk of knowledge loss to carry out 1st usage activities – additional effort to ensure all project resource are up to speed on project deliverables Review and possible re-test of AMT Market Flow code and integration | Environment and system code checks required Review of AMT Market Flow code and integration Performance Test Implementation Dress Rehearsal Pre-implementation activities Implementation and cut over activities Post Implementation Support Low risk that additional Build and Test activities are identified due to common system code and workflow changes to support other Release deliverables (Supply Point Administration processes)
Stop the delivery of June23 Release after completion of Regression Test phase | This option will stop the delivery of both associated changes once all testing (excluding Performance Test) have concluded. Any outstanding activities and implementation moved for both changes to a later date De-scoped change work would stop approx. 09/06/23 | All test phases will be completed except Performance Test. Build and all test will be complete for AMT Market Flow and Gas Enquiry Service Provides additional opportunity for all DNs and Shippers to align their NExA and Capacity values Developed system code will remain stable in project track whilst alternative delivery date is confirmed | Will lead to additional work to re-plan delivery of both XRN5186 and XRN5091 Checks will need to be performed against system code to ensure tested solution remains fit for purpose Possible risk of additional test activities (e.g. Regression Testing) Risk of knowledge loss to carry out 1st usage activities – additional effort to ensure all project resource are up to speed on project deliverables Review and possible re-test of AMT Market Flow code and integration Impact to Change Pipeline if entire Release is deferred Risk that additional project efforts may be identified dependent on Nov-23 Release Scope | Environment and system code checks required Review of AMT Market Flow code and integration Performance Test Implementation Dress Rehearsal Pre-implementation activities Implementation and cut over activities Post Implementation Support Moderate risk that additional Build and Test activities are identified due to common system code and workflow changes to support other Release deliverables (Meter Read and Settlement processes)
Impact Assessment – Option Comparison

## Slide 5
 | Option2 Defer XRN5186 Only | Option4 Defer XRN5186 & XRN5091
XRN5091 Approved BER Cost | £218,760 | £218,760
XRN5186 Approved BER Cost | £245,192 | £245,192
Total June-23 BER Cost | £463,952 | £463,952
June-23 Costs up until Scope Change | £333,419 | £333,419
Cost Reduction to June-23 BER | £65,513 | £130,533
Cost to Deliver remainder of June-23 Scope | £65,020 | N/A
Cost of known additional work and risk margin to Deliver Changes Later | £34,619 | £66,193
Total Cost to Deliver Deferred Changes later | £100,132 | £196,726
IA for Deferring Implementation – Financial Details

## Slide 6: Summary and June-23 Scope Decision
Final Considerations
Additional costs to deliver XRN5186 are based on delivering the change as an independent project
These costs reflect known risks that may materialise during the remaining project activities
Any unspent risk margin would be returned to customers once change is successfully delivered
Combining XRN5186 with other changes within a Release would allow costs to be saved through shared Project resource, technology and support costs
DSC ChMC Decision – Approval of Xoserve recommendation (Option 2) - defer implementation of XRN5186 to November-23 Release
Vote required from DN and Shipper Customer Classes

## Slide 7: June 2023 Major Release Update

## Slide 8: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking Green, Start up and initiation phase is completed. Build in progress for class change requirement. ​Progress update:​ Start up and initiation completed on 02/02 Build complete for all ISU build for XRN5186 and XRN5091 against original plan Build phase extended to include received delivery plans for Market Flow and GES changes and the missed requirement for Class Change (issue 68667); on track to complete including documentation by 28/04 Build for Market Flow changes relating to XRN5186 to commence on 27/02 System integration testing in progress on track to be completed 03/03 User Acceptance Testing scenarios in review approval to be provided on 24/02 Decision in March ChMC: Decision required on impact assessment to descope XRN5186 from June23 or stop June23 altogether and implement later. |  | Implementation date of 24th June, with a contingency implementation date of 1st July | 
Risks and Issues | Issue 68667 – The build for a “Class change” requirement was missed from xrn5091. Mitigation Action – A delivery timeline has been agreed with supplier, the build for this requirement to be completed on 03/03 Issue :There is an issue that some of the customer data held is inaccurate prior to the implementation of XRN5186. Mitigation Action – Xoserve are current working with customers to understand the best solution for this issue prior to the implementation of this change Issue: There is an associated issue that the current migration rules pre-implementation for XRN5186 are not currently defined and agreed. Mitigation Action - As above Issue: There is a risk that the June23 delivery could have one or both of its changes descoped pending a decision at the March ChMC meeting. Mitigation Action: An impact assessment is currently being carried out to understand all the available options. Xoserve will share options for approval at the March ChMC. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  | 
Slide updated on 21st February 2023
Complete
On Track
At Risk
Overdue