## Slide 1: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | The overall status is Green; implementation planned for 24/06. Implementation contingency date 01/07 Decision received from ChMC on the 08/03 to descope XRN5186. XRN5186 will be descoped at the end of the regression testing phase on the 19/05 System integration testing for all ISU build completed on 03/03 Build in progress for Market Flow changes to complete on 07/04 GES build in progress for xrn5186 to complete on 11/04 User acceptance testing execution and assurance in progress to be completed on 07/04 Regression test case scenarios in review to be approved by 07/04 Regression testing execution to commence on 11/04 Decision in April ChMC:.No decision required |  | Implementation date of 24th June, with a contingency implementation date of 1st July | 
Risks and Issues | Risk 68719 - There is a risk that some of the customer data held is inaccurate prior to the implementation of XRN5186. Mitigation Action – Xoserve are currently working with customers to understand the best solution for this prior to the implementation of this change Risk 68721 - There is an associated risk (68719) that the current migration rules pre-implementation for XRN5186 are not currently defined and agreed. Mitigation Action - There is an action on June23 project team to provide further detail around current working assumptions for all scenarios at Go-live to be provided on 06/04. This will require validation by customers. Dependency 68747 - There is a dependency on Xoserve to provide clarification on the migration rules to be applied for XRN5186 prior to implementation. Mitigation Action - Project team to provide all possible scenarios and current working assumptions that could impact the implementation of xrn5186 and data volumes for each scenario 06/04. Dependency 68748 - There is a dependency on DNS to provide updated details around the NExA SHQ/SOQ held in the system before the capacity window closes on the 31st of October. Mitigation Action – Xoserve to continue to send out monthly report as per the agreed interim process to all DNs/Shippers notifying them of current vales held in the system Dependency 68754 - There is a dependency on RECCO to update the data permission matrix prior to the implementation of XRN5186. Mitigation Action - Delivery timeline has been shared with RECCO regular conversations in place between BA on June23 project and RECCO |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  | 
Slide updated on 29th March 2023
Complete
On Track
At Risk
Overdue