## Slide 1: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | The overall status is Green; implementation planned for 24/06. Decision received from ChMC on the 08/03 to descope XRN5186. XRN5186 will be descoped at the end of the regression testing phase on the 19/05 Build and test completed for all GES and AMT Market Flow elements for XRN5186 All user acceptance testing (UAT) execution and assurance completed for XRN5186 UAT execution for XNR5091 completed , however there are several test cases that will require re-execution due to failed assurance. This has delayed completion of UAT phase. UAT assurance re-planned to complete on 12/05 Regression testing execution commenced for XRN5091 and XRN5186 – 10/04 Regression testing assurance for XRN5186 in progress commenced -17/04 Performance testing test case review to commence -25/04 Decision in May ChMC: No decision required |  | Implementation date of 24th June, with a contingency implementation date of 1st July | 
Risks and Issues | Issue 68792 – There is currently an issue that the completion date for UAT has been missed due to the high number of failed test cases. Mitigation Action – Analysis has been carried out to understand the root cause of the number of failures and the UAT assurance completion dates have been re-planned and additional business process consultant resources allocated to complete all planned activities within the Testing milestone Risk 68719 - There is a risk that some of the customer data held is inaccurate prior to the implementation of XRN5186. Mitigation Action – Xoserve are currently working with customers to understand the best solution for this prior to the implementation of this change Risk 68721 - There is an associated risk (68719) that the current migration rules pre-implementation for XRN5186 are not currently defined and agreed. Mitigation Action - There is an action on June23 project team to provide further detail around current working assumptions for all scenarios at Go-live to be provided on 06/04. This will require validation by customers. Dependency 68747 - There is a dependency on Xoserve to provide clarification on the migration rules to be applied for XRN5186 prior to implementation. Mitigation Action - Project team to provide all possible scenarios and current working assumptions that could impact the implementation of XRN5186 and data volumes for each scenario 26/04 Dependency 68748 - There is a dependency on DNS to provide updated details around the NExA SHQ/SOQ held in the system before the capacity window closes on the 31st of October. Mitigation Action – Correla to continue to send out monthly report as per the agreed interim process to all DNs/Shippers notifying them of current vales held in the system |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs (to be descoped as at 19/05/23, post regression testing phase). |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 24th April 2023