## Slide 1: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on track; Green. Return to green for schedule is completion is to firm up end of PIS date as 26th May, action to close this due by 14th April Progress update: Design completed Project Startup and Initiation phase complete Project Build phase complete Project Testing complete Project implementation and go-live complete on 1st April for both 5143 and 5379 Project PIS started First usage being managed, evidenced and assured during PIS, due to complete by 26th May Decision in April ChMC: None |  | Implementation date of 25th March with a go-live of 1st April, the contingency implementation date is 1st April with a go-live of 1st April | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) |  |  | 
Informal Slide updated on 11th April 2023
Complete
On Track
At Risk
Overdue