## Slide 1: REC Change

## Slide 2: Introduction
The following 7 slides have been included in this months CoMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review by REC Code Managers – due to CM workload/prioritisation
Expected incoming Impact Assessments
Further information on the Changes can be found on the REC Portal

## Slide 3: REC Change Pipeline – In progress
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0056 | EES/GES Additional Service Request for Housing Associations to be added to the Data Access Matrix | N/A | Correla | GES | Solution Development | 08/01/24 – IIA expected | TBC | Low | N/A
This Change was raised to allow Housing associations access to data in both GES and EES by adding them to the Data Access Matrix. As the GES provider, we need to monitor this Change and give input when needed to ensure that the correct data items are being provided to the appropriate parties. |  |  |  |  |  |  |  |  | 
R0063 | Addition of key information to all Service Now tickets | N/A | St Clements Ltd (on behalf of DNOs) | - | Approved – Awaiting Delivery | 12/04/24 - Implementation | 12/04/23 | Medium | N/A
This Change was raised to improve the information that’s included on DCC’s Service Now Tickets which have been asynchronously rejected. We interact with DCC via SNow so we need to monitor and input into development. |  |  |  |  |  |  |  |  | 
R0067 | Introduction of CSS refresh functionality | XRN 5567 / UNC Mod 836 | Capgemini (RTS) | GRDS | Approved – Awaiting Delivery | 04/12/23 – DCC Go/No Go Decision | 09/12/23 | High | High
This Change will introduce a resend and refresh functionality to help with the message interactions between the CSS and Switching Data Service Providers. Currently, there are cases where messages are being received after Gate Closure or not being received at all. We are one of the impacted Service Providers which means this Change is very important to us so that we are able to complete customer switches successfully. |  |  |  |  |  |  |  |  | 
Please note that we have provided our view of the Change summary and impacts however we recommend that DSC Customers monitor the REC Portal to form their own opinion regarding the impact to their organisation
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 4
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0070 | Provision of Enduring Test Environments | N/A | Capgemini | GRDS, GES | Solution Development/ On Hold | 03/01/24 – IA response date | Standalone |  | High
This Change was raised to introduce an obligation under the Retail Energy Code for the CSS or the Switching Operator (SO) to provide enduring test environments for REC parties to make the necessary system changes for REC Change Proposals (CPs) or internal system updates. We need to monitor this to ensure that the obligations on GRDS are understood, and that we contribute to the development of this Change. |  |  |  |  |  |  |  |  | 
R0071 | DCC access to EES and GES | N/A | DCC | GES | Awaiting Implementation | Project initiation 05/01/24 – 1st Project update | 23/02/23 | Medium | N/A
As the CSS Provider and Switching Operator, DCC have requested access to GES in order to help resolve Service Now tickets. This Change seeks to introduce a new Enquiry Service User Category to the Data Access Schedule and to reflect the required data item access in the Data Access Matrices. We are currently in early engagement with our Service Provider and the DCC to work through the scenarios that are impacting them to find the best resolution and required data items. |  |  |  |  |  |  |  |  | 
R0080 | Improvements to ‘Failed to Deliver’ CSS Messages | N/A | DCC | - | Service Provider Impact Assessment | TBC – IA currently with DCC | TBC | Medium | N/A
This Change Proposal has been raised to explore how and why, since CSS Go-Live, a number of messages have not been successfully delivered due to failures of CSS User's gateway. This results in CSS exhausting the 12-hour retry period. We are keen that we monitor this Change to ensure that there are no impacts to any current message related Change Requests or the way in which we send and receive messages from CSS. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 5
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0087 | MAP - GES Portfolio Dashboard | N/A | Correla | GES | Initial Assessment | 08/01/24 – IIA expected | TBC | Low | N/A
This Change was raised to grant access for MAPs to the Gas Enquiry Service. Previously, they received data related to their gas portfolio and they would like this to continue under the REC. Internal discussions have commenced and we are in conversations with the Code Manager to receive an Impact Assessment |  |  |  |  |  |  |  |  | 
R0089 | Removal of Pre-COVID AQ Value from Data Access Matrix | N/A | Xoserve | - | Initial Assessment | 08/01/24 – IIA expected | TBC | Low | N/A
This Change was raised to remove the mentioned data item as it is no longer accessible following the Covid pandemic. There were extended periods where certain sites were precluded from operation, Supply Meter Point AQs could have been non-representative of the normal expected Annual Quantity. Because of this, ‘Pre-COVID AQ Value’ was added as an additional data item in the DAM and made available via the DPM. This service was not migrated to REC and has no expired within the DSC. |  |  |  |  |  |  |  |  | 
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | N/A | DCC | GES | Impact Assessment | w/c 08/01/24 – Workgroup | N/A | High | N/A
This Change was raised to review the current Service Level Agreements (SLAs) that are outlined in the REC Service Definition. As the requirements for the Central Switching Service (CSS) were identified during the Design, Build and Test Phase of the Ofgem-led Switching Programme, DCC are proposing that an assessment takes place to ensure that the requirements are appropriate for the physical systems design and the actual behaviours of users, compared to the assumptions that were made in the early design phase. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 6
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0094 | Clarify obligations on gas meter exchanges that occur close to CoS | N/A | OVO | - | Solution Development | 11/12/23 – PIA response date | N/A | Medium | N/A
This Change was raised to address an issue with the 'Switch with a Concurrent Change of MEM process and ensure accurate Meter Technical Details are available to the gaining Supplier and MEM. We have been having early engagement with RPS to assess the impact on us as either the CDSP or GRDA. |  |  |  |  |  |  |  |  | 
R0096 | CSS Message Regeneration Functionality | N/A | RTS (Capgemini) | - | Service Provider Impact Assessment | TBC – IA currently with DCC | TBC | Medium | N/A
This Change was raised to identify and regenerate messages from CSS that failed initial generation, such that the message recipient is not impacted. We are keen that we monitor this Change to ensure that there are no impacts to any current message related Change Requests or the way in which we send and receive messages from CSS. |  |  |  |  |  |  |  |  | 
R0105 | Review of ONAGE SLAs | N/A | Natalie Hitchman | - | Initial Assessment | TBC – RPS in discussions on progression of this Change. | TBC | Low | N/A
This Change has been raised to review how appropriate the current ONAGE SLAs and lead times are following the changes that were introduced as part of the Faster Switching program. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 7
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0116 | TPI access to the Meter Asset Manager data via the GES | - | Ginger Energy | GES | Initial Assessment | 13/12/23 – IA response date | TBC | Low | N/A
This Change was raised to allow TPIs access to the Meter Asset Manager (MAM) via GES so that they are able to identify and contact the relevant MAM to arrange direct agreements for our clients on their behalf. |  |  |  |  |  |  |  |  | 
R0118 | Review of Schedule 12 and processes to manage access to data | N/A | REC | - | Approved – Awaiting Delivery | 06/12/23 - Implementation | TBC | Med | 
This Change was raised in order to review the data items that can currently be viewed by Supplier in the Gas Enquiry Service. Scottish Power have come across some issues internally as they don’t currently have access to some items in the Shipper portfolio. We have been assessing the data items that have been requested in the DAM and are working towards the DIA stage of the process. |  |  |  |  |  |  |  |  | 
R0120 | Search GES API using Meter Serial Number | N/A | GBG | GES | Initial Assessment | w/c 04/12 – IIA expected | TBC | Low | N/A
This Change was raised to enable searches of GES API by Meter Serial Number, which is enough information to enable the return of all meter-point data associated with the MPRN. We have had internal discussions around how we plan to progress this Change and have spoken to the Code Manager about taking and initial IA at the start of December. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 8
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0142 | Amendment to Multiplication Factor Enumerations to Support Hydrogen Trials |  | Xoserve | - | Service Provider Impact Assessment | 11/01/24 – DIA response date | TBC | Medium | N/A
The H100 hydrogen gas trial involves the supply of hydrogen gas to households in place of natural gas. The quantity of gas supplies needs to be billed in a way that is comparable to standard gas supply. To facilitate the trial, a multiplication factor enumeration value must be established within the Data Specification that can replicate hydrogen’s calorific value, therefore allowing accurate billing. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 9
REC Related XRN Changes
Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority
Resolution of Address Interactions between DCC and CDSP | XRN 5546 | Xoserve | GRDS | Under development | Ongoing discussion with DNs, analysis taking place on DCC data | TBC | Medium
Early Provision of Meter Reading for the ‘CSS Registration Effective Date’ (including the ‘Original Intended CSS Registration Effective Date’). Detailed Design | XRN 5675 | David Addison (on back of the P1 issue) | Shipper funded | Update in slide pack | Ongoing delivery discussions, governance activities ongoing | TBC | High
Currently working on
Key:
Upcoming
Monitoring
Early Engagement