## List of work activities
Draft Proposed Work Plan - First 12 months
| Work Activity | Description | Relevant Reference | Prioritisation | Possible timeframes | Add column for formulas | dates and time frames
Set up Activities
| Procurement and appoint PAFA | Procurement and put in place admin and expert adviser to the PAC | Framework document -Document 1, 6 Responsibilities PAFA | High | 2017-06-01
| Review of UNC performance assurance reporting and develop list of required reports | Review reporting under UNC and consider any consolidation and changes. Consider regular reporting required- the format and level of information Pac members require | Framework document - Document 1, 3.3 objectives; to determine the appropriate reporting and analysis to measure energy settlement performance and risks to it | High | 2017-01-01 | PAC could consider before PAFA is in place
| Development of risk methodology | Assess risk methodology options, models, and supporting analysis. This will be undertaken with input from PAFA | Framework document - Document 1, 3.3 objectives; to create a risk register and supporting analysis to assess risks and determine mitigation |  |  | Dependent on input from PAFA
| Create risk register and mitigations | Finalise list of risks, controls/actions, and risk progress report format | Framework document - Document 1, 3.3 objectives; to create a risk register and supporting analysis to assess risks and determine mitigation |  |  | Dependent on input from PAFA
| Performance Indicators | Development of performance indices that will be reported against | Framework document - Document 1, 3.4 Application and Operation - The provision of training and awareness services to existing users |  |  | PAC could prepare briefing/consider steer to give to PAFA ?
| Escalation, resolution and sanctions (penalties) | Decide arrangements for follow up if there are issues of under performance and what are the range of resolutions, escalation routes or sanctions. | TOR para 2.5 |  |  | PAC could prepare briefing/consider steer to give to PAFA ?
| Develop incentives regime | How to incentivise -performance and link with the performance indicators | Framework document -Document 1, 3.3 objectives; To create a regime incentivising the required performance if necessary by proposing modifications to the UNC | Medium |  | PAC could prepare briefing/consider steer to give to PAFA ?
| PAC Reporting (pre-Nexus) | Develop reporting formats - PARR schedules | Framework document -Document 1, 3.3 objectives; To report as necessary |  |  | PAC could prepare briefing/consider steer to give to PAFA ?
| PAC Reporting (post-Nexus) | Review reporting formats - changes to PARR and other reporting/when they should be introduced once Nexus is live | Framework document -Document 1, 3.3 objectives; To report as necessary |  |  | PAC could prepare briefing/consider steer to give to PAFA ?
| Agree stakeholder engagement/communication strategy | Communication of reporting requirements and awareness of PAC's role | Framework document -Document 1, 3.3 objectives; To report as necessary |  |  | PAC could consider this prior to PAFA being appointed
| Role in Advocating good practice | Consider the value of training and awareness of good practice | Framework document -Document 1, 3.4 Application and Operation - The provision of training and awareness services to existing users |  |  | PAC could consider this prior to PAFA being appointed
| Horizon scanning work on assurance issues/scope changes | Are there any new issues that could come within scope of the PAC. Are there changes that mean the risk methodology should be reviewed/reports might need to changed or redundant Useful to have this ongoing piece so PAFA can work into work plans and when coming to new procurement any new activities can be included into a scope of work. The format needs to be considered (there are synergies with the strategy document PAB produce etc) | Framework document - Document 1, 3.4 Application and Operation - Other activities Also, in order to update risk model and other issues |  |  | PAC could consider this prior to PAFA being appointed