## Risk Log
|  |  | Name | Nexus Workgroup
|  |  | Last Updated | 2014-02-25
Category | Risk ID | Title/Area | Area | Description of Risk | Cause \ Factors | Impact | Risk Proximity Start Date | Risk Proximity End Date | Impact Date | Date Identified | Identified By | Gross Risk Value (£) | Probability (P) | Impact (I) | Score (P*I) | Risk Owner | Mitigation Actions | Mitigation Action Date (s) \ Target Resolution | Mitigating Action Owner | Residual Risk Value (£) | Probability (P) | Impact (I) | Score (P*I) | Issue Ref No. | Status | Status Date | Date Closed
|  |  |  | There is a risk that......... | because of.......... | leading to.....
| RIS001 | EU Reform | Settlement | There is a risk that the EU changes may impact the implementation date of the Nexus changes | because of the extent & complexity of the changes required to industry systems, including Gemini | leading to a delay in the delivery of the new Settlement arrangements and Nexus requirements | 2013-10-01 | 2015-10-01 | 2015-10-01 | 2013-09-30 | NGT |  | 3 | 5 | 15 | NGT | Impact assessment on changes required to gemini for both UU changes and Nexus | 2014-06-01 | NGT |  |  |  |  | ISS001 | Awaiting Approval
| RIS002 | Industry Change programme during 2015 | Settlement | There is a risk that the objectives or implementation date of the Nexus changes may be at risk due to the congested industry change programme during late 2015 | because there are a number of industry changes In addition to Nexus changes, other changes scheduled to take place during late 2015 include: convergence with EU Network Codes, DCC go-live for smart metering and change of supplier reforms. | leading to a delay in the delivery of the new Settlement arrangements and Nexus requirements | 2015-06-01 | 2015-12-01 | 2015-10-01 | 2013-12-01 | PN UNC |  | 4 | 5 | 20

## Assumptions Log
| Name | Nexus Workgroup
Last Updated
Assumption Reference | Cross Topics Y/N | Assumption Description | Comments | Proximity Start Date | Proximity End Date | Raised by | Date Raised | To be Agreed by | Date Agreed | Review Date | Status | Status Date
ASS | [10 empty] | Open

## Issue Log
|  | Name | Nexus Workgroup
Last Updated
Issue Ref | Title | Area | Description of Issue and its Impact | Date Identified | Identified By | Priority (MoSCoW) | Impact (Severity) Rating | Owner | Issue Resolution Actions | Responsible for Action | Target Resolution Date | Resolution Date | Cost of Action (£) | Status | Status Date | Open Days
ISS001 | EU Reform | Settlement | EU are making changes to the Daily Settlement processes effective from 1st October 2015 which will also require changes to Gemini. | 2013-09-01 | PN UNC | Must | 4 | NGT | 1. Xoserve to carry out impact assessment | Xoserve | 2014-03-03 |  |  | Raised
ISS002 | Industry Change programme | Settlement | There are a number of industry changes In addition to Nexus changes which may impact the implementation date. Other changes scheduled to take place during late 2015 include: convergence with EU Network Codes, DCC go-live for smart metering and change of supplier reforms. | 2013-12-01 | PN UNC | Must | 5 | PN Unc

## Dependency Log
Name | Nexus Workgroup
Last Updated
Dependency Reference | Title | Description (to include who dependency is on Internal / External) | Date Required | Owner | Forecast Completion Date | Actual Completion Date | Impact of missed completion date | Comments | Status | Status Date
DEP001

## Info
Information relating to RAID proforma
Proximity | A start and end date should be documented which details the period of time over which the risk may be experienced
Risk Probability Scoring Matrix: | Score | Probability of Occurrence | Description
| 1 | <= 10% | Remote
| 2 | >10% <= 40% | Less Likely
| 3 | >40% <= 60% | Equally as likely as unlikely
| 4 | >60% <= 90% | More likely
| 5 | >90% | Almost certain
Risk Impact Scoring Methodology | Impact | Very Low (1) | Low (2) | Medium (3) | High (4) | Very High (5)
| Financial | x < £100,000 | £100,000 < x < £500k | £500k < x < £1 million | £1 million < x < £2 million | X > £2 million
| Reputation | Minor impact on Project | Major impact on Project | Minor impact on Project & 1 Stakeholder | Major impact on Project & a Stakeholder group | Major impact on Project & all stakeholders
MoSCoW: | M | Must
| S | Should
| C | Could
| W | Won't

## Governance
Definition: Risk: | An uncertain event or set of events that, should it occur, will have an effect on the achievement of objectives
A Risk is something that may happen in the future
Definition: Issue: | A relevant event that has happened, was not planned, and which requires action.
Issues can be problems, benefits or situations
An Issue is something that is happening now
Process: | 1. The Risk / Issue/ Assumption / Dependency raised by an individual or at PN UNC
2. If raised outside of PN UNC, the relevant proforma is submitted to the Joint Office for publishing for discussion at the following meeting
3. The item is discussed & agreed in the Workgroup:
a) Agree information & scoring
b) Assign ownership
c) Agree any actions
4. Monitor each item at the Workgroups
a)Updates where appropriate Any further actions agreed
b) Closed by approval of PN UNC
Responsibilities: | Joint Office: | Maintaining the RAID Log
| Nexus Workgroup: | Record Risks, Issues, Assumptions & Dependencies
| Nexus Workgroup: | Review & manage
| Nexus Workgroup: | Agree ownership & actions
| Anyone: | Review Risks, Issues, Assumptions & Dependencies
| Owners: | Take appropriate & agreed actions

## Requirements
ID | Date Raised | Status | Heading | BRD / Topic | Area | Options | Actions/Resolution | Agreed Date
REQ1 | 2013-10-30 | Closed | Read Validation | Settlement | Following a transfer of ownership the new Shipper will be unable to validate the first read received from a consumer as the new Shipper will have no history. | Send new Shipper the latest read before the transfer effective date. | The latest read at D-7 will be sent to the Proposing Shipper. Not included in Mod 0432. Needs to be added to BRD & a Modification | 2013-10-30
REQ2 | 2013-11-19 | Closed | Winter Consumption | AQ | WAR Bands are derived annually for Monthly Read sites (AQ greater 293,000kWh) using the consumption derived from reads loaded during the preceding years winter consumption. Currently there is an appeal process where Shippers can challenge the WAR band | Propose to follow the same principle as the AQ review process: No appeals process, the winter consumption is based on the validated reads loaded & WAR band applied based on the consumption. | 08/01/2014: Agreed a WAR Band can be challenged via the AQ Correction process. | 2014-01-08
REQ3 | 2013-11-22 | Open | Duplicates | SPR | Process improvement for notifying & processing a duplicate MPRN | Following submission & validation of a query for a Duplicate Meter Point, the MPRN will be end dated from the date specified and the adjustment processed, no need for a Withdrawal notification from the Shipper.
REQ4 | 2014-01-21 | Open | Change of Class | Settlement | For a change in Class, no change in Shipper, the request requires a minimum of 5 days notice. However, for Supply Points moving to Class 1 or 2, if the current AQ & SOQ is not accepted, a Referral would be required. | Shipper requests change in Class with the SOQ currently registered for the Supply Point. If a change in SOQ is required the Shipper would need to go through the Capacity Revision process. Note: The 'soft landing' rules for a Ratchet applies to Supply Points moving from Class 3/4 to 1/2 (Ratchet will not be levied in in the first 12 months where the NDM SOQ is taken)
REQ5 | 2014-01-21 | Open | Updates to Asset or Address Data | SPR | Asset updates for greenfield/brownfield sites that are un-registered. | Allow a Shipper to update asset details or address details where the Supply Meter Point is not registered to a Shipper. This will support Mod 410a & UNC G7.3.7
REQ6 | 2014-01-21 | Open | Ratchets | SPR | Ratchets on DM CSEPs | Apply ratchet charges Instead of 'Overruns' to DM CSEPs, as Overruns can not be applied if there are any NDM CSEPs within the 'CSEP' .
REQ7 | 2014-01-21 | Open | Withdrawal | SPR | Withdrawal status made visible to Shippers | When a Supply Point Withdrawal has been lodged by the Registered User, the Withdrawal status will be recorded & so visible on data Enquiry
REQ8 | 2014-01-21 | Open | Isolated & Withdrawn | SPR | Commodity charges on a Supply Meter Point that has been isolated & Withdrawn and subsequently Confirmed | For Classes 3 & 4 the deeming of Commodity from Registration Date rather than meter installation date (if later). Reconciliation would reconcile Commodity once a valid read is received.
REQ9 | 2014-01-21 | Open | Correction Factor | SPR | Ability to update a Correction factor | Ability for the Shipper to update the Correction Factor for a Supply Meter Point via a 'Supply Point Amendment'. Currently the CF can only be updated via RGMA flows.
REQ10 | 2014-01-21 | Open | Isolated & Withdrawn | SPR | Following a GSR visit by the GT's it is established that gas is capable of flowing, the Supply Meter Point must be registered back into the ownership of the last Shipper (Mod 424). | The Supply Meter Point is automatically registered to the last Shipper and the asset re-installed without the need for a Confirmation or RGMA flows from the Shipper.
REQ11 | 2011-01-21 | Open | Meter Inspect | SPR | Ability to submit the read taken during a Meter Inspection visit | The read taken & submitted to be used for downstream processes, e.g. AQ review & reconciliation, if valid.
REQ12 | 2014-01-21 | Open | Isolation | SPR | The deeming of gas following an Isolation | Following an Isolation notification the deeming of Commodity will cease on D+1 (currently D+7) and reconciliation processes will reconcile Commodity back to the Isolation read. If already Withdrawn, the Withdrawal will become effective from the day after the date the isolation was submitted. | Note: The date of the effective withdrawal is: a) the day following acceptance of a Supply Point Withdrawal if already isolated, b) the day following acceptance of an isolation notification (if Withdrawal already accepted), c) the day on which both the Withdrawal and Isolation is accepted or, d) the Registration date on an Incoming Shipper where this occurs before the Supply Meter point is isolated.
REQ13 | 2014-01-20 | Open | Asset Data | SPR | Current quality of asset data held is poor particularly around meter models. | Shippers submit only the data needed for Xoserve to derive the remaining values based on the meter model, e.g. Product ID.