## Sheet1
[10 empty] | Open | In Progress | Closed
Proposed Release 2 Scope - Query Log
Transition ID | Date Raised | Contact Name | Contact Organisation | Your Question | Xoserve Updates & Final Answer (Green) | Additional Comments | Response Provided | Status | Date Closed
Q001 | 2017-08-29 | Beverley.Viney@nationalgrid.com | NGT | At the prioritisation meeting in July it was agreed that XRN4290/COR4010 was going to be moved to high prioritisation as it has a requirement date for this report. I notice from the attached presentation that this is not included in release 2 and doesn’t have an explanation for exclusion. Can you please advise when this report/COR will be carried out. For clarification; there is a requirement for this to be run each year with financial year data from 1 April to 31 March, we have requested that the data be provided in each May for the previous financial year. Priority is to have the 1st report run which will cover the 1 April 2017 to 31 March 2018 available in May 2018. The reports are only for National Grid Transmission. | The change you mention below is part of the proposed Release 2 scope under Change Reference UKLP194 (see extract from Change Demand Backlog). Within the presentation on slides 7, 8, 9 & 14 you will see this referenced as well. | Lee Sent the email to Beverly on 29/8/17 | Email | Closed | 2017-08-29
Q002 | 2017-09-08 | Nicky.Rozier@bu-uk.co.uk | BUUK | Good afternoon, Ahead of the release 2 scope discussion next week at ChMC meeting I wanted to highlight a concern iGTs had with regards to UKLP270. IGTs do not require any amendments to the process so are not in support of picking up any associated costs or impacts. We require clarity into whether all changes raised by GTs pre-Nexus are only impacting GT’s as a restricted class. Kind regards Nicky |  |  |  | Open
Q003 | 2017-09-12 | alison.neild@gazprom-energy.com | Gazprom | Hi Emma, My comments/feedback on the Release 2 scope are below. (1) UKLP202: As we don’t have a firm solution for this yet, what are the chances of this one being in the release? (2) There is a proportionally high number of Low priority changes that have been put in scope of release 2 but the looks of it due to the common code element. However when looking at the missing high priority ones I see this is largely due to missing sponsors. (3) Comments on the other high priority fixes not in release 2 a. UKLP112 – this is currently in change pack and a desirable option is low impact. Will it be if the low impact solution is agreed this month b. UKLP109 – this is a current issue due to the data we have taken into the new UKLink systems. If the change is complex can any different changes/workarounds be considered that will alleviate the issues here. The concern is that by the time it makes it to a release, it will lose its benefit. c. UKLP071 – If this had a sponsor – would it be in Release 2? Apologies for the delay Regards Alison |  |  |  | Open
Q004 | 2017-09-12 | Chris.Warner@cadentgas.com | Cadent Gas | Hi Emma, I think that for Cadent, the enduring invoicing solution is definitely a priority and we’d like this to be prioritised for Release 2. The Siteworks CP is less clear as to the extent of its priority (given that it was raised by SGN in 2013)! Dave, Hilary, do you have a view? Chris Warner |  |  |  | Open
Q005 | 2017-09-12 | david.mitchell@sgn.co.uk | SGN | Hi Emma, As discussed at the constituency meeting last week GDN’s provide Xoserve with the Site Works Reference number when we create a new MPRN, therefore it makes sense to capture the Site works reference number as a data item on your systems and to provide it back to the GDN’s on reports such as the Plot Address report and the Shipperless and Unregistered sites reports. If GDN’s have the siteworks reference number on both the Plot to Postal reports and the Shipperless and Unregistered reports then we would be able to go back and find the project that the MPRN was raised against. Having this information will speed up the process of resolving data issues as we will be able to find the original enquiry which will contain developer contact details etc. I believe that the siteworks reference number was removed from the reports @ 5 years ago, the decision to remove this data item was an Xoserve decision at the time and was always something that the GDN’s challenged. Regards David Mitchell |  |  |  | Open
Q006 | 2017-09-12 | darren.lond@nationalgrid.com | NGT | Hi emma The current invoicing rebilling solution is causing concern for our customers, I have had direct feedback from some that it is causing additional processing and additional invoices, also I’m aware our invoicing team have had a number of questions and concerns raised about the current solution. The enduring solution was always the preference however had to be delayed due to Nexus implementation and therefore I believe the implementation of the enduring invoicing solution should be a priority for Release 2. I am concerned following discussions last week at the constituency meeting that if it is not implemented in release 2 then it may also be at risk for release 3 should RAASP need to be implemented following 0624R . Thanks Darren |  |  |  | Open
Q007
Q008
Q009
Q010
Q011
Q012
Q013
Q014
Q015
Q016
Q017
Q018
Q019
Q020
Q021
Q022
Q023
Q024
Q025
Q026
Q027
Q028
Q029
Q030
Q031
Q032
Q033
Q034
Q035
Q036
Q037
Q038
Q039
Q040
Q041

## Sheet2
Status | Response Provided
Open | Email
In Progress | Phone
Closed