## Risk Summary
PAC Risk | Risk Title | Current Throughput (1-5) | Current Probability (1-5) | Control (Not Effective, Partially Effective, Effective) | Gross Risk Score | Net Risk Score | Allocation (£) | Reconciliation (£) | Allocation (GWh) | Reconciliation (GWh) | Associated Risk
PACR0001 | Theft of Gas | 5 | 5 | Not Effective (x1) | 25 | 25 | 42218000 | 43046000 | 2483 | 2532 | -
PACR0002 | Use of the AQ Correction Process | 5 | 5 | Not Effective (x1) | 25 | 25 | 32218000 | 32286000 | 1895 | 1899 | -
PACR0003 | Estimated reads used for daily metered sites (Product Classes 1 and 2) | 5 | 4 | Not Effective (x1) | 20 | 20 | 23555000 | 47000 | 1386 | 3 | -
PACR0004 | Identified LDZ Offtake Measurement Errors | 5 | 3 | Partially Effective (x0.8) | 15 | 12 | 21152000 | - | 1244 | - | PACR0007
PACR0005 | Incorrect asset data on the Supply Point Register | 4 | 4 | Not Effective (x1) | 16 | 16 | 13987000 | 14073000 | 823 | 828 | -
PACR0006 | Use of Winter Annual Ratio (WAR) for End User Category (EUC) 03-08 | 4 | 4 | Not Effective (x1) | 16 | 16 | 8908000 | - | 524 | - | -
PACR0007 | Undetected LDZ Offtake Measurement Errors | 3 | 2 | Not Effective (x1) | 6 | 6 | 7051000 | 7051000 | 415 | 415 | PACR0004
PACR0008 | Shipperless Sites | 2 | 3 | Not Effective (x1) | 6 | 6 | 2481000 | 621000 | 146 | 37 | -
PACR0009 | Unregistered Sites | 2 | 4 | Not Effective (x1) | 8 | 8 | 2326000 | - | 137 | - | -
PACR0010 | Meter readings fail validation | 2 | 4 | Not Effective (x1) | 8 | 8 | 1439000 | - | 85 | - | -
PACR0011 | Late check reads on meters that derive a read | 2 | 4 | Not Effective (x1) | 8 | 8 | 1437000 | 467000 | 85 | 27 | -
PACR0012 | Meter read submission frequency for Product Class 4 meter points | 2 | 4 | Not Effective (x1) | 8 | 8 | 1350000 | - | 79 | - | -
PACR0013 | Estimated reads at Change of Shipper | 1 | 3 | Not Effective (x1) | 3 | 3 | 408000 | 410000 | 24 | 24 | -
PACR0014 | Failure to obtain a meter reading within the settlement window | 1 | 3 | Not Effective (x1) | 3 | 3 | 79000 | 79000 | 5 | 5 | -
PACR0015 | Consistent approach to retrospective updates | 1 | 3 | Not Effective (x1) | 3 | 3 | - | 5000 | - | 0 | -
Cost at average SAP 1.7p for higher threshold (Oct 2012 – Nov 2016)

## Risk Scores
Rating | Energy Throughput | Cost (£) | Likelihood
1 | 0 – 49 GWh | 850000 | Description – Remote Probability – <10% chance
2 | 50 – 249 GWH | 4250000 | Description – Less Likely Probability – >=10% and < 40% chance
3 | 250 – 499 GWh | 8500000 | Description – Equally unlikely as likely Probability – >=40% and < 60% chance
4 | 500 – 999 GWh | 17000000 | Description – More likely Probability – >=60% and < 90% chance
5 | > 1,000 GWh | 42,500,000 (no upper limit) | Description – Almost certain Probability – >=90% chance
Cost at average SAP 1.7p for higher threshold (Oct 2012 – Nov 2016)

## 001-Theft of Gas
Risk Number | PACR0001 | Risk Description / Title: | Theft of Gas
|  | There is a risk that… | The energy consumed at a Shipper's site will not be accounted for and be incorporated into unidentified gas
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £85.26 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 5 | Not Effective (x1) | 25 | 25 | Further discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 4 | 5 | Partially Effective (x0.8) | 20 | 16
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Failure to identify consumers and customers who conduct theft of gas. |  | The sites and quantity of gas stolen cannot be identified, gas cannot be allocated and reconciled correctly |  | Detective: Shipper performance report to be produced in the future. Preventative: The TRAS framework. Above controls that have been put in place (obligations, TRAS etc.) have yet to be considered or reviewed by PAC, and until they are reviewed, an assumption that the controls are not effective has been made. | Action 0801: Scottish Power (AL) to chase ElectraLink to gain clarity on the quantities of energy identified through TRAS which would have an impact on allocation and settlement process. Investigate data from AUGE as this takes a view on ToG. Action 0807: Members to agree on comments made on Risk Register |  | To be agreed at PAC meeting on 04/10/2017

## 002 - Use of the AQ Corrections
Risk Number | PACR0002 | Risk Description / Title: | Use of the AQ Correction Process
|  | There is a risk that… | Inaccurately calculated AQs will cause a misallocation of energy and the AQ correction process will not be used in a fair and consistent way.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £64.5 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 5 | Not Effective (x1) | 25 | 25 | Further discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 3 | 5 | Partially Effective (x0.8) | 15 | 12
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Misunderstanding as well as misuse of how and when to use the AQ correction process. Also Erroneous reads, significant changes in consumption and sites with AQ incorrectly calculated of 1. The misuse and misunderstanding (not actioning) can lead to deflated AQs as a result, e.g. lowered erroneous consumption due to tampered reads means AQs should potentially be increased once theft is discovered. |  | The AQ allocated does not provide an accurate reflection of gas consumption; impacts allocation to the shipper and unidentified gas. The misallocation will not be corrected until Meter Point Reconciliation takes place. |  | To be Agreed. Reporting to monitor use of the corrections process and provide assurance that corrections are submitted in a fair and consistent manner. Production of shipper performance report 2A.8 and 2B.8 | Monitoring of Report 2A 8 to help show the use of the AQ correction process. Action 0807: Members to agree on comments made on Risk Register |  | To be agreed at PAC meeting on 04/10/2017

## 003 - Estimated readings
Risk Number | PACR0003 | Risk Description / Title: | Estimated reads used for daily metered sites (Product Classes 1 and 2)
|  | There is a risk that… | Where estimated reads are used in Product Classes 1 and 2 after D+5, gas is allocated and reconciled incorrectly.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £23.6 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 4 | Not Effective (x1) | 20 | 20 | Further discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 5 | 3 | Partially Effective (x0.8) | 15 | 12
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
The current cause of this risk is thought to be that the estimated read issue causes incorrect reconciliation at D+5. This risk should be considered as a risk to allocation, rather than a risk to reconciliation. |  | Estimated daily readings being used rather than actuals; allocation and reconciliation will be impacted. Use of estimated reads for these meters can affect unidentified gas volumes. Ultimately the meter point reconciliation corrects the position, though settlement remains unaccurate until then. |  | To be Agreed. Manage and monitor the number of estimates used for MPRNs in PC2. Transporter incentives in TPD M7.2 are reviewed to ensure they are proportionate and mitigate the settlement risk for MPRNs in PC1. Incentive targets are implemented to ensure check reads obligations are met. Production of shipper performance report 2A.1 and 2B.1 | Action 0804: PAFA to define specific time periods for risk PACR003 for Product Classes 1 and 2. Action 0807: Members to agree on comments made on Risk Register Xoserve currently working with Shippers, the DMSP (Daily Metered Service Provider) and the GTs to resolve sites with this issue |  | To be agreed at PAC meeting on 04/10/2017

## 004 - LDZ Offtake measure error
Risk Number | PACR0004 | Risk Description / Title: | Identified LDZ Offtake Measurement Errors
|  | There is a risk that… | Offtake meters develop errors and produces inaccurate readings.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £21.15 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 3 | Partially Effective (x0.8) | 15 | 12 | Further discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 4 | 4 | Partially Effective (x0.8) | 16 | 12.8
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | PACR0007 |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Inadequate management and monitoring of offtake meters. Meter inaccuracies and equipment faults. |  | Gas incorrectly allocated to meter points within the LDZ. No back-up or check meters in place. Also misallocation of NTS shrinkage leading to increased unidentified gas allocation |  | Manage and monitor LDZ Offtake meters to mitigate risk and implement a set of Transporter principles to provide assurance that the UNC Offtake arrangements are being followed. Performance report to be produced in the future. | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to agree on comments made on Risk Register Action 0806: GTs to present on why they believe that this risk is now lower probability than when Engage carried out the initial study. 3 Transporters have now published their quarterly Offtake Meter Performance reports outlining maintenance regime, meter error reports and copy of RRP report |  | To be agreed at PAC meeting on 04/10/2017

## 005 - Incorrect asset data
Risk Number | PACR0005 | Risk Description / Title: | Incorrect asset data on the Supply Point Register
|  | There is a risk that… | The billing attributes of a meter and gas consumption are incorrectly recorded or missing
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £28.06 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 4 | 4 | Not Effective (x1) | 16 | 16 | Further discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 4 | 4 | Partially Effective (x0.8) | 16 | 12.8
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Insufficient validation and/or assurance of information provided by Shippers (ultimately provided by Suppliers and MAMs) |  | Meter reads failing validation resulting in delays and/or missing reconciliation. For Class 1 & 2 (DM) the impact is at the point of allocation and persists in reconciliation unless spotted and corrected. For Class 3 & 4, allocation will be correct but the asset error will cause incorrect (or missing) reconciliation. |  | To be Agreed. A principle of good behaviour to be introduced where Shippers are measured for updating incorrect asset data. Production of Shipper performance report for the following: 1A.1, 1B.1, 2A.9, 2B.9, 1A.2, 1B.2, 2A.2, 2B.2, 2A.3, 2A.3. PAC to investigate, attaining MDD data and information from Electralink. | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to agree on comments made on Risk Register |  | To be agreed at PAC meeting on 04/10/2017

## 006 - Site WAR for EUC 3-8
Risk Number | PACR0006 | Risk Description / Title: | Use of Winter Annual Ratio (WAR) for End User Category (EUC) 03-08
|  | There is a risk that… | Accurate daily settlement of meter points that do not have a site specific WAR; it will not reflect accurate consumption.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £8.9 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 4 | 4 | Not Effective (x1) | 16 | 16 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 4 | 4 | Partially Effective (x0.8) | 16 | 12.8
|  | Inherent | 4 | 4 | Not Effective (x1) | 16 | 16
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Lack of meter read history means the WAR has not been populated or an estimated profile has been applied. |  | Allocated energy is not reflective of accurate consumption if timing for WAR bands are missed and thus daily allocations could be impacted and incorrect AQ values derived. However, reconciliation might be impacted as it might put energy into the wrong times of year. |  | To be Agreed: Shippers to manage and monitor, on a monthly basis, the percentage of their MPRNs with a site specific WAR. Production of shipper performance report 2A.5 and 2B.5 | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to agree on comments made on Risk Register. |  | To be agreed at PAC meeting on 04/10/2017

## 007 - Undetected LDZ errors
Risk Number | PACR0007 | Risk Description / Title: | Undetected LDZ Offtake Measurement Errors
|  | There is a risk that… | LDZ offtake meters develop an error and remains undetected, which causes the readings to be inaccurate.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £14.1 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 3 | 2 | Not Effective (x1) | 6 | 6 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 3 | 2 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 4 | 4 | Not Effective (x1) | 16 | 16
Associated Risk | PACR0004 |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Offtake errors from LDZ's are occurring but are not being identified and corrected. Inadequate management and monitoring of LDZ offtake meters. Also there are no back-up or check meters in place. Meter inaccuracies and equipment faults remain undectected until reconciliation takes place |  | The incorrect LDZ offtake measurements leads to gas being wrongly allocated. Misallocation of NTS shrinkage leading to increased Unidentified Gas allocation. |  | To be agreed: Transporters manage and monitor LDZ offtake meters in mitigating risk. Frequent auditing and investigation into LDZ offtake measurement errors. Use the Transporter performance to provide industry assurance that UNC Offtake Arrangements are met. Performance report to be produced in the future | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to agree regarding the Risk Register direct to PAFA. To investigate the use of reports around unregistered sites; PAC to consider use and monitoring of these. Action 0806: GTs to present on why they believe that this risk is now lower probability than when Engage carried out the initial study. 3 Transporters have now published their quarterly Offtake Meter Performance reports outlining maintenance regime, meter error reports and copy of RRP report |  | To be agreed at PAC meeting on 04/10/2017

## 008 - Shipperless Sites
Risk Number | PACR0009 | Risk Description / Title: | Shipperless Sites
|  | There is a risk that… | The accuracy of settlement where a Shipperless site is either still consuming gas, or begins to consume at a future date without the Supply Point being reregistered.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £3.1 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 3 | Not Effective (x1) | 6 | 6 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 2 | 2 | Partially Effective (x0.8) | 4 | 3.2
|  | Inherent | 2 | 3 | Not Effective (x1) | 6 | 6
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers are withdrawing from sites that still have meters attached. The site then starts and/or continues to consume gas |  | The gas consumed is not measured and falls into unidentified gas. This also impacts accuracy of settlement |  | To be Agreed. Shippers to manage and monitor that UNC MODs 0424 and 0425 are met. MOD 0469S details Transporter performance. Also monitoring Shippers follow the correct withdrawal process and Transporters to ensure that GSR visits are completed on time. Monitor site re-registrations to ensure energy allocation is corrected. Production of shipper performance report 1A.2, 1B.2, | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. PAC members to understand issues in the performance reports, should there be any once reports are received. PAC to ensure there is a clear demarcation between Shipperless sites and Unregistered sites. |  | To be agreed at PAC meeting on 04/10/2017

## 009 - Unregistered Sites
Risk Number | PACR0008 | Risk Description / Title: | Unregistered Sites
|  | There is a risk that… | An unregistered meter begins consuming gas and adversely impacts the accuracy to Settlement
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £2.33 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 3 | 4 | Not Effective (x1) | 12 | 12
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Following a new connection, meters are fitted and gas is allowed to flow without a valid supply contract being in place (where they have an MPRN) Also incorrectly identifying customer owned meters as primary meters. |  | Shipper fails to register a site. The consumption at those sites is not measured and falls in to unidentified gas. |  | To be Agreed. Manage and monitor the performance and ensure that the intentions of UNC MOD 410A are achieved. | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. Obtain reports around unregistered sites for PAC consideration PAC to ensure there is a clear demarcation between Shipperless sites and Unregistered sites. |  | To be agreed at PAC meeting on 04/10/2017

## 010 - Readings fail validation
Risk Number | PACR0010 | Risk Description / Title: | Meter readings fail validation
|  | There is a risk that… | Meter readings are submitted and fail validation, and subsequent reads fail validation; the AQ will become less accurate impacting the timeliness of reconciliation.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £1.44 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 2 | 3 | Effective (x0.6) | 6 | 3.6
|  | Inherent | 2 | 4 | Not Effective (x1) | 8 | 8
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers are not managing the validation errors identified and therefore not remedying the issue. Also causes for rejected reads not investigated which reflects in inaccurate consumption. |  | Because of a poor and/or diminishing meter reading history, reconciliation will not be possible and the derived AQ is more likely to be inaccurate. |  | To be agreed: Manage and monitor the use of data set tolerance readings and focus on where there are persistent read fail validations. Production of shipper performance report 2A.6, 2B.6 | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. |  | To be agreed at PAC meeting on 04/10/2017

## 011 - Late Check Reads
Risk Number | PACR0011 | Risk Description / Title: | Late check reads on meters that derive a read
|  | There is a risk that… | Where check reads are not completed, there is a risk that meters are under or over reading for an extended period of time which will impact allocation accuracy
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £1.9 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 2 | 4 | Not Effective (x1) | 8 | 8
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers failing to provide timely check reads and providing late reads. Shippers not checking converters at the same time as the main meters. |  | Late check readings impact accurate allocation and extend drift periods. Derived readings cannot be verified as being accurate leading to potential consumption inaccuracies. |  | To be agreed: Ensure obligation for shippers to check converters at the same time as the main meter is met. Production of shipper performance report 2A.1, 2B.1 | To be agreed at PAC meeting on 04/10/2017. Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. |  | To be agreed at PAC meeting on 04/10/2017

## 012 - Meter read submission PC4
Risk Number | PACR0012 | Risk Description / Title: | Meter read submission frequency for Product Class 4 meter points
|  | There is a risk that… | The frequency of submission of meter readings for Product Class 4 meter points could adversely impact the accuracy of the derived AQ and consumption
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £1.35 million
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 2 | 4 | Not Effective (x1) | 8 | 8
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers submitting meter readings infrequently |  | Timing differences in submission will create a risk of misallocation among shippers. The AQ will not be recalculated frequently from a good meter reading history leading to potential inaccuracies. |  | Obligations recently introduced following CMA order (annual read submission obligation and monthly read submission for smart). Manage and monitor frequency of read submissions. Production of shipper performance report 2A.5, 2B.5 Individual meter point reconciliation should correct this miscalculation. | To be agreed at PAC meeting on 04/10/2017. Define read submission targets. Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. |  | To be agreed at PAC meeting on 04/10/2017

## 013 - Est. Reads Change Shipper
Risk Number | PACR0013 | Risk Description / Title: | Estimated reads at Change of Shipper
|  | There is a risk that… | Estimated readings provided by the Transporter are used and not replaced with an actual reading are inaccurate and will create incorrect periods of reconciliation.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £818k
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 1 | 3 | Not Effective (x1) | 3 | 3 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6
|  | Inherent | 3 | 3 | Not Effective (x1) | 9 | 9
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
No reading obtained within the change of transfer window and/or rejected by initial validation due to incorrect AQ. Shippers do not have an actual reading to replace the estimate following transfer |  | Estimated opening meter read used during the reconciliation between the two shippers will be inaccurate. This will result in an incorrect final allocation for the transferring parties; accuracy of the whole market will not be accurate. |  | UNC, SPAA and supply license rules and regulations. SARs process to correct change of supplier reads. Production of shipper performance report 1A.3, 1B.3, 2A.4, 2B.4 | To be agreed at PAC meeting on 04/10/2017: Investigate how is this estimated read used in settlement Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. PAC to review Shipper agreed reads process to see if there are any issues. |  | To be agreed at PAC meeting on 04/10/2017

## 014 - Failure to obtain read
Risk Number | PACR0014 | Risk Description / Title: | Failure to obtain a meter reading within the settlement window
|  | There is a risk that… | Some meter points do not obtain a read within the settlement window and reconciliation periods will crystallise not reflecting true consumption
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £158k
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 1 | 3 | Not Effective (x1) | 3 | 3 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6
|  | Inherent | 2 | 3 | Not Effective (x1) | 6 | 6
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Meter readings are not being obtained within the settlements window. Also read validation errors not being corrected by shippers. |  | Incorrect consumption being crystallised due to lack of meter reads |  | To be agreed: Principle of logic checks to approve consumption adjustments. Production of shipper performance report 1A.4, 1B.4, 2A.7, 2B.7 | To be agreed at PAC meeting on 04/10/2017: Investigate the issue where the meter is read but reads are not loaded within the agreed window. Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. |  | To be agreed at PAC meeting on 04/10/2017

## 015 - Retrospective updates
Risk Number | PACR0015 | Risk Description / Title: | Consistent approach to retrospective updates
|  | There is a risk that… | The approach taken by shippers to retrospective updates increases the risk of inaccurate reconciliation periods.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Status (Active / Inactive) | Active | Risk Financial Estimate | £5k
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 1 | 3 | Not Effective (x1) | 3 | 3 | Discussion with PAC on 04/10/2017 to agree on scores.
|  | Target | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6
|  | Inherent | 1 | 3 | Not Effective (x1) | 3 | 3
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Commercial drivers and incentives on shippers do not promote a fair and balanced approach to use retrospective updates. |  | An unfair and unbalanced approach to retrospective updates, allocation could be skewed and distorted overall towards greater unidentified gas. |  | To be agreed: Monitoring the use of the retrospective updates process, by measuring update requests. Full set of retrospective adjustment update requirements not fully delivered at initial Nexus implementation, work is being done to refine requirements and agree future delivery Shipper performance report to be produced in the future | To be agreed at PAC meeting on 04/10/2017: Shipper performance monitoring of use of retrospective process. Action 0807: Members to supply feedback and views regarding the Risk Register direct to PAFA. |  | To be agreed at PAC meeting on 04/10/2017