## CMC Summary
Totals by Budget Area (£,000's) | [11 empty] | Current Year Value of Work Done Split By Customer Class
|  |  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) |  | Expenditure Type | Approved Budget Value 17/18 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget 17-18 | MKT_1718_01 | External | 1255.041 | 273.995 | 114.238 | 80.291 | 33.947 | 0 | 0 | G | G | 0 | 4.467 | 29.48 | 0 | 0
|  | Internal | NA | 178.437 | 107.913 | 76.864 | 31.049 | 0 | 0 | NA | G | 0 | 31.049 | 0 | 0 | 0
|  | Total | NA | 452.432 | 222.151 | 157.155 | 64.996 | 0 | 0 | NA | G | 0 | 35.516 | 29.48 | 0 | 0
Note that project expenditure & budget values shown do not include margin | [9 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [9 empty] | Red - Above target
Details of Changes
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining
4340 UK Link Future Release 1.1 (DSC Change Budget) - External | 127 | -82.5 | 0 | 11.5 | -94 | 0
4340 UK Link Future Release 1.1 (DSC Change Budget) - Internal | 51.1 | 0 | 0 | 0 | 0 | 0
Grand Total | 178.1 | -82.5 | 0 | 11.5 | -94 | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## CMC Detail
[7 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [6 empty] | Formulas do not delete |  | 5 | 6 | 7 | 9 | 10 | 12 | 13 | 14 | 15 | 16
Budget Pot Reference | Project Ref No | Project Title | High Level Process Stage | Next Contractual Step | Next Step Date | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | Matcher | Project Line | High Level Process Stage | Next Contractual Step | Next Step Date | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | Delivery Stage | On Hold | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4160External | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - External | DIFF | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | Delivery Stage | On Hold | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4160Internal | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - Internal | DIFF | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | Delivery Stage | On Hold | N/A | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4160Total | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - Total | DIFF | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Change Proposal Receipt | [XOS] Send EQR Initial Response | TBC | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4248External | 4248 Quarterly smart metering reporting for HS&E and GDNs - External | DIFF | DIFF | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Change Proposal Receipt | [XOS] Send EQR Initial Response | TBC | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4248Internal | 4248 Quarterly smart metering reporting for HS&E and GDNs - Internal | DIFF | DIFF | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Change Proposal Receipt | [XOS] Send EQR Initial Response | TBC | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4248Total | 4248 Quarterly smart metering reporting for HS&E and GDNs - Total | DIFF | DIFF | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER Stage | [XOS] Send BER Initial Response | TBC | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4361External | 4361 UK Link Future Release 2 (DSC Change Budget) - External | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER Stage | [XOS] Send BER Initial Response | TBC | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4361Internal | 4361 UK Link Future Release 2 (DSC Change Budget) - Internal | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER Stage | [XOS] Send BER Initial Response | TBC | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4361Total | 4361 UK Link Future Release 2 (DSC Change Budget) - Total | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Delivery Stage | [XOS] Implement Change | TBC | External | 127.006 | 29.48 | 97.526 | 0 | 29.48 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 29.48 | 0 |  |  | 4340External | 4340 UK Link Future Release 1.1 (DSC Change Budget) - External | DIFF | DIFF | DIFF | 127 | -82.5 | 0 | 11.5 | -94 | 0 | DIFF | YES | -82.5 | TRUE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Delivery Stage | [XOS] Implement Change | TBC | Internal | 51.13 | 0 | 51.13 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4340Internal | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Internal | DIFF | DIFF | DIFF | 51.1 | 0 | 0 | 0 | 0 | 0 | DIFF | YES | 0 | TRUE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Delivery Stage | [XOS] Implement Change | TBC | Total | 178.136 | 29.48 | 148.656 | 0 | 29.48 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 29.48 | 0 |  |  | 4340Total | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Total | DIFF | DIFF | DIFF | 178.1 | -82.5 | 0 | 11.5 | -94 | 0 | DIFF | YES | -82.5 | TRUE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCR | 2017-11-08 | External | 33.273 | 11.23 | 22.043 | 9.032 | 2.198 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.198 | 0 | 0 |  |  | 2949External | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - External | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCR | 2017-11-08 | Internal | 25.714 | 22.721 | 2.993 | 22.684 | 0.037 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0.037 | 0 | 0 |  |  | 2949Internal | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Internal | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCR | 2017-11-08 | Total | 58.987 | 33.951 | 25.036 | 31.716 | 2.235 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.235 | 0 | 0 |  |  | 2949Total | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Total | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCR | 2017-11-24 | External | 15.016 | 3.016 | 12 | 2.016 | 1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1 | 0 | 0 |  |  | 3991External | 3991 Pafa Administrator Role [Usr Pys] - External | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCR | 2017-11-24 | Internal | 57.5 | 43.1 | 14.4 | 22.7 | 20.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 20.4 | 0 | 0 |  |  | 3991Internal | 3991 Pafa Administrator Role [Usr Pys] - Internal | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCR | 2017-11-24 | Total | 72.516 | 46.116 | 26.4 | 24.716 | 21.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 21.4 | 0 | 0 |  |  | 3991Total | 3991 Pafa Administrator Role [Usr Pys] - Total | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCR | 2017-11-08 | External | 89 | 60.288 | 28.712 | 60.288 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4110External | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - External | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCR | 2017-11-08 | Internal | 31.05 | 36.444 | -5.394 | 24.18 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 12.264 | 0 | 0 |  |  | 4110Internal | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - Internal | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCR | 2017-11-08 | Total | 120.05 | 96.732 | 23.318 | 84.468 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 12.264 | 0 | 0 |  |  | 4110Total | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - Total | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCR | N/A | External | 9.7 | 10.224 | -0.524 | 8.955 | 1.269 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.269 | 0 | 0 | Sent | CMC to approve CCR | 3995External | 3995 TRAS Tip-off Hotline Data Provision - External | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCR | N/A | Internal | 3.12 | 2.267 | 0.853 | 2.3 | -0.033 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -0.033 | 0 | 0 | Sent |  | 3995Internal | 3995 TRAS Tip-off Hotline Data Provision - Internal | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCR | N/A | Total | 12.82 | 12.491 | 0.329 | 11.255 | 1.236 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.236 | 0 | 0 | Sent |  | 3995Total | 3995 TRAS Tip-off Hotline Data Provision - Total | SAME | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Approved |  | 4161External | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - External | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | Internal | 9.923 | 3.381 | 6.542 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.619 | 0 | 0 | Approved |  | 4161Internal | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - Internal | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | Total | 9.923 | 3.381 | 6.542 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.619 | 0 | 0 | Approved |  | 4161Total | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - Total | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | Closed - Delivered as a BAU activity | 4242External | 4242 Monthly provision of national S&U statistics - External | DIFF | DIFF | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4242Internal | 4242 Monthly provision of national S&U statistics - Internal | DIFF | DIFF | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | N/A | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 4242Total | 4242 Monthly provision of national S&U statistics - Total | DIFF | DIFF | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
Note on AY2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual