## Slide 1: Change Management Committee – Retail & Networks Update
November 2017

## Slide 2: Regular DSC update
As we begin to stabilise the change portfolio post-R1, we wanted to agree communications this committee wish to receive:
Portfolio Overview: a 2-year view of the release structure, and ‘best view’ release scoping and planning for that period. During review, we would expect ChMC to provide direction of scoping and timing.
Scoping Progress: R2 undertook a review of known scope and, in accordance with the release principles agreed with ChMC, completed a prioritisation to determine scope; whilst a similar process may be needed for Release 3, it is our intention to undertake impact assessments on an ongoing basis, such that we can inform this committee with the latest priority position at each ChMC to support timely prioritisation and change delivery
Delivery Progress: for those releases/changes that are in an active stage, we will share progress such that the committee can track and discuss development, e.g. plan progress, risk, customer experiences, etc.
Does the above meet your needs?

## Slide 3: Platform Portfolio Overview - Current

## Slide 4: Platform Portfolio Overview – Proposed

## Slide 5: 4340 – UK Link Future Release 1.1
RAG Key – Milestones are end dates:
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed
30th October 2017 | Overall Project RAG Status |  |  |  |  |  |  |  |  |  |  | G |  | 
 | Time |  |  | Risks and Issues |  |  |  | Cost |  |  |  | Resources |  | 
RAG Status | G |  |  | G |  |  |  | G |  |  |  | A |  | 
Status Explanation |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Objective | Release delivery is for a scope of 4 CRs to meet business process ‘need dates’ |  |  |  |  |  |  |  |  |  |  |  |  | 
Time | Ofgem decision delayed for CP370B and CR249 and ChMC agreed to descope this CR from R1.1 Detailed Design (DD) completed on 16/10 for all 5 CRs in the original scope (as notified at the 11/10 ChMC we completed DD for CR249) Build has commenced and is tracking to plan The implementation date will be communicated in a ChMC Change Pack, Imp Date proposed for 08th December 17 Testing plan, scenarios & test cases defined in full, regression testing packs to be provided to DRG to report on progress versus plan PIS period agreed internally within Xoserve considering the Christmas holiday period |  |  |  |  |  |  |  |  |  |  |  |  | 
Risks and Issues | Risks are considered to be low scale and mitigated. Monitoring production defects and deployments for any potential impact to R1.1 deployment |  |  |  |  |  |  |  |  |  |  |  |  | 
Cost | On track – Descope of CR249, revision of R1.1 project costs being defined |  |  |  |  |  |  |  |  |  |  |  |  | 
Resources | Weekly monitoring of SME resources supporting Release 1 stabilisation and multiple demands (Future Releases, UIG etc) |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Scoping |  |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding |  | Initiation | Analysis and HLD | Detailed Design |  | Build | Test | Imp. |  |  | PIS
Baseline Plan | 07/06/17 | 07/06/17 | 11/08/17 |  | Early July | Early July | 01/09/17 |  | Oct 17 | Nov 17 | Nov 17 |  |  | Dec 17
Current Plan | 07/06/17 | 24/07/17 | 24/07/17 |  | 15/07/17 | 15/07/17 | 16/10/17 |  | 03/11/17 | 01/12/17 | 08/12/17 |  |  | 04/01/18

## Slide 6: 4340 – UK Link Future Release 2
30th October 2017 | Overall Project RAG Status |  |  |  |  |  |  |  |  |  |  | A |  | 
 | Time |  |  | Risks and Issues |  |  |  | Cost |  |  |  | Resources |  | 
RAG Status | A |  |  | A |  |  |  | G |  |  |  | A |  | 
Status Explanation |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Objective | Full project delivery of UK Link Future Release 2 Scope |  |  |  |  |  |  |  |  |  |  |  |  | 
Time | The R2 Scope was agreed at the11/10 ChMC, following receipt of CR individual costs a business benefit/case review has been conducted for all CRs Following this review it has been identified that 8 CRs do not have a viable business case The EQR to request funding approval for 10 CRs to commence Detailed Design is being provided to ChMC for review, seeking approval from the DSC Market Change Budget Detailed delivery plan definition is being defined considering the scope review following business case/benefit review. Delivery Sub committee to be engaged on plans, RAID and agreeing the high level testing strategy |  |  |  |  |  |  |  |  |  |  |  |  | 
Risks and Issues | Approval of funding for Detailed Design (EQR - 08/11) and R2 full project delivery (BER -13/12) not being achieved would impact the June 17 target implementation date |  |  |  |  |  |  |  |  |  |  |  |  | 
Cost | Full project delivery costs are expected to be within the 2017/18 & 18/19 values in BP17 and anticipated to align with BP18 forecast costs |  |  |  |  |  |  |  |  |  |  |  |  | 
Resources | Weekly monitoring of SME resources supporting Release 1 stabilisation and multiple demands (Future Releases, UIG etc) |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Scoping |  |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding |  | Initiation | Analysis and HLD | Detailed Design |  | Build | Test | Imp. |  |  | PIS
Baseline Plan | 7/6/17 | 25/7/17 | 9/8/17 |  | Aug 17 | Aug 17 | 20/11/17 |  | TBC | TBC | Jun 2018 |  |  | TBC
Current Plan | 7/6/17 | 11/10/17 | 8/11/17 |  | 8/11/17 | 8/11/17 | 20/11/17 |  | TBC | TBC | TBC |  |  | TBC
RAG Key – Milestones are end dates:
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed

## Slide 7: UK Link Future Release 3
30th October 2017 | Overall Project RAG Status |  |  |  |  |  |  |  |  |  |  | G |  | 
 | Time |  |  | Risks and Issues |  |  |  | Cost |  |  |  | Resources |  | 
RAG Status | G |  |  | A |  |  |  | G |  |  |  | A |  | 
Status Explanation |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Objective | Set up of UK Link Future Release 3 Project |  |  |  |  |  |  |  |  |  |  |  |  | 
Time | Collation and categorisation of open / deferred Change Items is in progress – this is dependent on R2 scope lockdown These Change Items include those relating to RAASP, Cadent Billing and Meter Read Sequencing which are perceived as being a priority Prioritisation of Change Items will be sought through ChMC and SDG UIG impacts to other delivery work streams is being assessed |  |  |  |  |  |  |  |  |  |  |  |  | 
Risks and Issues | There is a risk that the review and prioritisation of Change Demand Backlog will take longer than planned to agree the R3 scope |  |  |  |  |  |  |  |  |  |  |  |  | 
Cost | It is assumed that scope will be managed such that full project delivery costs would be within BP18 values |  |  |  |  |  |  |  |  |  |  |  |  | 
Resources | Weekly monitoring of SME resources supporting Release 1 stabilisation and multiple demands (Future Releases, UIG etc) |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Scoping |  |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding |  | Initiation | Analysis and HLD | Detailed Design |  | Build | Test | Imp. |  |  | PIS
Baseline Plan | 13/12/17 | 10/01/18 | Feb 18 |  | TBC | TBC | TBC |  | TBC | TBC | TBC |  |  | TBC
Current Plan | 13/12/17 | 10/01/18 | Feb 18 |  | TBC | TBC | TBC |  | TBC | TBC | TBC |  |  | TBC
RAG Key – Milestones are end dates:
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed

## Slide 8: Future Committee Content
Committee Date | Topic | Objective | Required Outcome | Decision / Action / Information | Comments
08/11/17 | Release 2 Funding Agreement for Detailed Design (EQR) | ChMC agreement for R2 DSC Market Change Budget funding to commence Detailed Design | Approve EQR | Decision | 
13/12/17 | Release 2 Funding Agreement (BER) | ChMC agreement for R2 DSC Market Change Budget funding for full project delivery | Approve BER | Decision | 
13/12/17 | Release 3 Scope | Prioritisation of Change Items for Release 3 inclusion | Agreed scope proposal | Decision | To be ratified by SDG