## CMC_Summary
Totals by Budget Area (£,000's) | [11 empty] | Current Year Value of Work Done Split By Customer Class
|  |  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) |  | Expenditure Type | Approved Budget Value 17/18 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget 17-18 | MKT_1718_01 | External | 1255.041 | 1579.5836 | 1182.334 | 80.291 | 102.1341 | 559.0687 | 440.8402 | G | G | 0 | 67.2261 | 29.48 | 0 | 5.428
|  | Internal |  | 508.1376 | 409.187 | 76.864 | 56.7339 | 157.4795 | 118.1096 | NA | G | 0 | 50.7339 | 6 | 0 | 0
|  | Total |  | 2082.8362 | 1591.521 | 157.155 | 158.868 | 716.5482 | 558.9498 | NA | G | 0 | 117.96 | 35.48 | 0 | 5.428
PAC Subset DSC Change Budget 17-18 |  | External | 50 | 50 | 50 | 0 | 0 | 50 | 0 | NA | G
*This has already been included in above DSC figures,and this sub table is for visibility only |  | Internal | [7 empty] | NA | G
|  | Total |  | 50 | 50 | 0 | 0 | 50 | 0 | NA | G
Note that project expenditure & budget values shown do not include margin | [9 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [9 empty] | Red - Above target | [7 empty] | PIE VALUES
[18 empty] | Budget | 1255.041
[18 empty] | Budget Remaining | 473.8382
Details of Changes | [17 empty] | Xoserve's estimate of Potential Spend | 679.0687
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year | [14 empty] | VOWD Transmission | 0
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining | [11 empty] | VOWD DNs | 67.2261
No Changes | [17 empty] | VOWD IGTs | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease. | [17 empty] | VOWD DNs & IGTs | 29.48
[18 empty] | VOWD Shippers | 5.428
[17 empty] | LABEL > | Total VOWD £102.1

## CMC_Current
[5 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [6 empty] | SORT FIELD 2 | [5 empty] | SORT FIELD 1 | Formulas do not delete |  | 5 | 7 | 8 | 10 | 11 | 12 | 13 | 14
Budget Pot Reference | Project Ref No | Project Title | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | Line Sequence Sort (THEN BY THIS) | PM | Line Check NOT FOR FILTER | Show Approved Money? | Show Reported Money? | Auto Assess of CMC Friendly? | Progress Sort (SORT BY THIS) | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | External | 50 | 50 | 0 | 0 | 0 | 50 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 422 | Emma Smith / Rachel Hinsley | #N/A | SHOW | SHOW | Y | 6 | xxxx.A.PACExternal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - External | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 423 | Emma Smith / Rachel Hinsley | #N/A | SHOW | SHOW | Y | 6 | xxxx.A.PACInternal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - Internal | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | Total | 50 | 50 | 0 | 0 | 0 | 50 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 424 | Emma Smith / Rachel Hinsley | #N/A | SHOW | ShOW | Y | 6 | xxxx.A.PACTotal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - Total | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | BER/Bus Case | External | 9.7 | 10.224 | -0.524 | 8.955 | 1.269 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.269 | 0 | 0 | Sent |  | 95 | Mark Pollard | TRUE | SHOW | SHOW | Y | 7 | 3995External | 3995 TRAS Tip-off Hotline Data Provision - External | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | BER/Bus Case | Internal | 3.12 | 2.267 | 0.853 | 2.3 | -0.033 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -0.033 | 0 | 0 | Sent |  | 96 | Mark Pollard | TRUE | SHOW | SHOW | Y | 7 | 3995Internal | 3995 TRAS Tip-off Hotline Data Provision - Internal | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | BER/Bus Case | Total | 12.82 | 12.491 | 0.329 | 11.255 | 1.236 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.236 | 0 | 0 | Sent |  | 97 | Mark Pollard | TRUE | SHOW | SHOW | Y | 7 | 3995Total | 3995 TRAS Tip-off Hotline Data Provision - Total | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER/Bus Case | External [C] | 1107.0172 | 941.3863 | 165.6309 | 0 | 62.7591 | 502.0727 | 376.5545 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 62.7591 | 0 | 0 |  |  | 212 | Christina Francis | FALSE | SHOW | SHOW | Y | 7 | 4361External [C] | 4361 UK Link Future Release 2 (DSC Change Budget) - External [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER/Bus Case | Internal [C] | 329.7006 | 295.274 | 34.4266 | 0 | 19.6849 | 157.4795 | 118.1096 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 19.6849 | 0 | 0 |  |  | 213 | Christina Francis | FALSE | SHOW | SHOW | Y | 7 | 4361Internal [C] | 4361 UK Link Future Release 2 (DSC Change Budget) - Internal [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER/Bus Case | External [O] | 128.5714 | 64.2857 | 64.2857 | 0 | 0 | 0 | 64.2857 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 214 | Christina Francis | FALSE | SHOW | SHOW | Y | 7 | 4361External [O] | 4361 UK Link Future Release 2 (DSC Change Budget) - External [O] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER/Bus Case | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 215 | Christina Francis | FALSE | SHOW | SHOW | Y | 7 | 4361Internal [O] | 4361 UK Link Future Release 2 (DSC Change Budget) - Internal [O] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | BER/Bus Case | Total | 1565.2892 | 1300.946 | 264.3432 | 0 | 82.444 | 659.5522 | 558.9498 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 82.444 | 0 | 0 |  |  | 216 | Christina Francis | FALSE | SHOW | SHOW | Y | 7 | 4361Total | 4361 UK Link Future Release 2 (DSC Change Budget) - Total | DIFF | 1565.3 | 1300.9 | 0 | 82.4 | 659.6 | 558.9 | DIFF | YES | 742 | TRUE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Delivery | External | 127.006 | 29.48 | 92.641 | 0 | 29.48 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 29.48 | 0 |  |  | 203 | Matt Rider | FALSE | SHOW | SHOW | Y | 11 | 4340External | 4340 UK Link Future Release 1.1 (DSC Change Budget) - External | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Delivery | Internal | 51.13 | 6 | 45.13 | 0 | 6 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 6 | 0 |  |  | 204 | Matt Rider | FALSE | SHOW | SHOW | Y | 11 | 4340Internal | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Internal | DIFF | 0 | 6 | 0 | 6 | 0 | 0 | DIFF | YES | 6 | TRUE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Delivery | Total | 173.251 | 35.48 | 137.771 | 0 | 35.48 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 35.48 | 0 |  |  | 205 | Matt Rider | FALSE | SHOW | SHOW | Y | 11 | 4340Total | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Total | DIFF | -4.9 | 6 | 0 | 6 | 0 | 0 | DIFF | YES | 6 | TRUE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Delivery | External [C] | 20 | 12.424 | 7.576 | 0 | 5.428 | 6.996 | 0 | 100% | 0% | 0% | 0% | 0% | 5.428 | 0 | 0 | 0 | 0 |  |  | 375 | Debbie Jones | FALSE | SHOW | SHOW | Y | 11 | 4510External [C] | 4510 Negative Consumption Period For Rolling AQ - External [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Delivery | External [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 376 | Debbie Jones | FALSE | SHOW | SHOW | Y | 11 | 4510External [O] | 4510 Negative Consumption Period For Rolling AQ - External [O] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Delivery | Internal [C] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 377 | Debbie Jones | FALSE | SHOW | SHOW | Y | 11 | 4510Internal [C] | 4510 Negative Consumption Period For Rolling AQ - Internal [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Delivery | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 |  | 0 | 0 | 0 |  |  | 378 | Debbie Jones | FALSE | SHOW | SHOW | Y | 11 | 4510Internal [O] | 4510 Negative Consumption Period For Rolling AQ - Internal [O] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Delivery | Total | 20 | 12.424 | 7.576 | 0 | 5.428 | 6.996 | 0 | 100% | 0% | 0% | 0% | 0% | 5.428 | 0 | 0 | 0 | 0 |  |  | 379 | Debbie Jones | FALSE | SHOW | SHOW | Y | 11 | 4510Total | 4510 Negative Consumption Period For Rolling AQ - Total | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closedown | External | 33.273 | 11.23 | 22.043 | 9.032 | 2.198 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.198 | 0 | 0 |  |  | 56 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 2949External | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - External | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closedown | Internal | 25.714 | 22.721 | 2.993 | 22.684 | 0.037 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0.037 | 0 | 0 |  |  | 57 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 2949Internal | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Internal | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closedown | Total | 58.987 | 33.951 | 25.036 | 31.716 | 2.235 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.235 | 0 | 0 |  |  | 58 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 2949Total | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Total | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closedown | External | 15.016 | 3.016 | 12 | 2.016 | 1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1 | 0 | 0 |  |  | 104 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 3991External | 3991 Pafa Administrator Role [Usr Pys] - External | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closedown | Internal | 57.5 | 43.1 | 14.4 | 22.7 | 20.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 20.4 | 0 | 0 |  |  | 105 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 3991Internal | 3991 Pafa Administrator Role [Usr Pys] - Internal | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closedown | Total | 72.516 | 46.116 | 26.4 | 24.716 | 21.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 21.4 | 0 | 0 |  |  | 106 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 3991Total | 3991 Pafa Administrator Role [Usr Pys] - Total | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | External | 89 | 60.288 | 28.712 | 60.288 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 140 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 4110External | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - External | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | Internal | 31.05 | 36.444 | -5.394 | 24.18 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 12.264 | 0 | 0 |  |  | 141 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 4110Internal | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - Internal | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | Total | 120.05 | 96.732 | 23.318 | 84.468 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 12.264 | 0 | 0 |  |  | 142 | Mark Pollard | FALSE | SHOW | SHOW | Y | 12 | 4110Total | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - Total | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Approved |  | 155 | Lorraine Cave | TRUE | SHOW | SHOW | Y | 100 | 4161External | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | Internal | 9.923 | 3.381 | 6.542 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.619 | 0 | 0 | Approved |  | 156 | Lorraine Cave | TRUE | SHOW | SHOW | Y | 100 | 4161Internal | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | Total | 9.923 | 3.381 | 6.542 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.619 | 0 | 0 | Approved |  | 157 | Lorraine Cave | TRUE | SHOW | SHOW | Y | 100 | 4161Total | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
Note on AQ2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual