## Slide 1: XRN4361 – UK Link Future Release 2
10th January 2018 | Overall Project RAG Status |  |  | A
 | Time | Risks and Issues | Cost | Resources
RAG Status | G | A | G | A
Status Explanation |  |  |  | 
Objective | Full project delivery of UK Link Future Release 2 Scope |  |  | 
Time | The Detailed Design for the initial 14 changes is in progress; all Design workshops completed The plan for issues of Change Packs has been shared with Customers at SDG on 18/12/17, all planned dates are being achieved The Detailed Design for the Secondary Scope began on 02/01/18 The Release 2 testing and training requirements discussion was conducted with SDG on 18/12/17 and it has been agreed to conduct evidenced based testing. Training requirements will be confirmed following Change Pack approvals National Grid and Cadent Enduring Invoicing Arrangements recommendation for R3 was provided verbally at the 13/12/17 ChMC, material posted on JO website for review and vote at 10/01/18 ChMC |  |  | 
Risks and Issues | Risk that scope of R2 may change that could result in impacts to the project plan and increased costs Risk that approval of funding for R2 full project delivery (14 CRs via BER) is not agreed at ChMC on 10/01/18 that could impact the June 17 target implementation date |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting Release 1 stabilisation and multiple demands (Future Releases, UIG etc) |  |  | 

## Slide 2: Release 2 - Plan
Primary Scope | Scoping |  |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding |  | Initiation | Analysis and HLD | Detailed Design |  | Build | Test | Imp. |  |  | PIS
Baseline Plan | 7/6/17 | 25/7/17 | 9/8/17 |  | Aug 17 | Aug 17 | 20/11/17 |  | 29/01/18 | 28/06/18 | 29/06/18 (TBC) |  |  | 30/07/18
Current Plan | 07/6/17 | 11/10/17 | 10/01/18 |  | 13/12/17 | 12/01/18 | 29/01/18 |  | 29/01/2018 | 28/06/18 | 29/06/18 (TBC) |  |  | 08/07/18
Secondary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build | Test | Imp. |  | PIS
Baseline Plan | 7/6/17 | 25/7/17 | 07/02/18 | NA | NA | 09/02/18 | 09/03/18 | 28/06/18 | 29/06/18 (TBC) |  | 30/07/18
Current Plan | 07/6/17 | 27/11/2017 | 07/02/18 | NA | NA | 09/02/18 | 09/03/18 | 28/06/18 | 29/06/18 (TBC) |  | 08/07/18
RAG Key – Milestones are end dates:
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed