## Summary Stats
| ITI&SD Change Lifecycle Status | ICAF (New this week) |  | R & N (Lee Foster) |  | Data Office (Crispin Wibberley) |  | T & SC (Jane Rocky) |  | TU (Dave Payne) |  | Other |  | Sub Total | Grand Total
|  | CP | CR | CP | CR | CP | CR | CP | CR | CP | CR | CP | CR
1. Start-Up (Progressing through change governance) | 0. ROM In-Progress | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 90
| 0.5 Change Proposal awaiting MOD approval (ROM complete) | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
| 1. Awaiting ICAF Assignment | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 1.5 Change Proposal out for Shipper Consultation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.1. Start-Up Approach In Progress | 0 | 0 | 0 | 13 | 2 | 5 | 1 | 3 | 0 | 0 | 1 | 3 | 28
| 2.2. Awaiting ME/BICC HLE Quote | 0 | 1 | 2 | 6 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 7 | 23
| 3.1. Start-Up Approach Awaiting Platform Director Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2. ASR Awaiting Customer Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4. EQR In-Progress | 0 | 0 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 20
| 6. EQR Awaiting ChMC Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7. BER/Business Case In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 5
| 9. Business Case awaiting IRC/XEC/Board approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10. BER Awaiting ChMC Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Change sanctioned/approved and in project delivery | 11. Change In Delivery | 0 | 0 | 10 | 18 | 0 | 7 | 5 | 3 | 0 | 5 | 0 | 3 | 51 | 51
3. Change delivered, awaiting closure approval/sign-off | 12. CCR/Closedown document in progress | 0 | 0 | 5 | 0 | 1 | 4 | 18 | 4 | 0 | 0 | 1 | 4 | 37 | 43
| 13.1. CCR Awaiting ChMC Approval | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 13.2 Closedown document awaiting approval | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2
| 14. Awaiting ECF Sign-Off | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3
4. Change proposed to be rejected by Xoserve (awaiting closure approval) | 97. Xoserve require ChMC sponsorship | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7
| 98. Xoserve Propose Change Not Required | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Platform Totals | 8 |  | 87 |  | 27 |  | 44 |  | 5 |  | 20
[12 empty] | Grand Total |  | 191

## Change Register
XRN Ref | High-Level Status | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritsation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Current Delivery Implementation Forecast Date | Customer Requested Implementation Date | Primary Application Impacted | Workaround Available? | Workaround Accountability | Workaround Frequency | Estimated No. of FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? (Xoserve perceived) | Customer Testing Likely Required? (Xoserve perceived) | Customer Training Required? (Xoserve perceived) | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk?
4555 | 1. Start-Up (Progressing through change governance) | Provision of a web portal to enable GDNs to access customer contact details | CP | LIVE | 0. ROM In-Progress | 21.02% |  |  | Data Office | 2017-12-06 | Richard Pomroy | Murray Thomson | 0 |  | 2018-02-23 | 2018-02-13 | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4586 | 1. Start-Up (Progressing through change governance) | Amendments to Gas Transmission Charging Regime (0621B) | CP | LIVE | 0. ROM In-Progress | 9.009% |  |  | ICAF | 2018-01-19 | Jeff Chandler (SSE) | No Project Manager | 0 |  | 2018-01-26 | No Date | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4597 | 1. Start-Up (Progressing through change governance) | Changes to settlement regime to address Unidentified Gas issues (MOD642) | CP | LIVE | 0. ROM In-Progress | 21.02% |  |  | ICAF | 2018-01-25 | Justine Price (Corona Energy) | No Project Manager | 0 |  | 2018-02-07 | 2018-02-07 | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4598 | 1. Start-Up (Progressing through change governance) | Changes to settlement regime to address Unidentified Gas issues issues including retrospective correction(MOD 643) | CP | LIVE | 0. ROM In-Progress | 21.02% |  |  | ICAF | 2018-01-25 | Lorna Lewin (Orsted) Lorna Lewin (Orsted) Lorna Lewin ( Orsted ) | No Project Manager | 0 |  | 2018-02-07 | 2018-02-07 | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4599 | 1. Start-Up (Progressing through change governance) | Changes to settlement regime to address Unidentified Gas issues (642A) | CP | LIVE | 0. ROM In-Progress | 21.02% |  |  | ICAF | 2018-01-25 | Kirsty Dudley (Eon) | No Project Manager | 0 |  | 2018-02-07 | 2018-02-07 | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4347 | 1. Start-Up (Progressing through change governance) | UNC Modification 0619 - Application of proportionate ratchet charges to daily read sites | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 42.64% |  |  | R & N | 2017-08-17 | Murray Thomson on behalf of JO | Murray Thomson | 0 |  | 2017-09-07 | 2018-10-01 | No Application | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4529 | 1. Start-Up (Progressing through change governance) | UNC Modification 0619A Protection from ratchet charges for daily read customers with AQ of 73,200kWh and below MOD0619A | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 42.64% |  |  | R & N | 2017-11-09 | Steve Ganney | Padmini Duvvuri | 0 |  | 2017-12-13 | 2018-10-01 | ISU | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4585 | 1. Start-Up (Progressing through change governance) | Amendments to Gas Transmission Charging Regime (0621A) | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 9.009% |  |  | ICAF | 2018-01-19 | Benoit Enault (Storengy) | No Project Manager | 0 |  | 2018-01-26 | No Date | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4587 | 1. Start-Up (Progressing through change governance) | Test of the Bulk upload facility | CR | LIVE | 1. Awaiting ICAF Assignment | 69.97% |  |  | ICAF | 2018-01-22 | Dawn Gallacher | No Project Manager | 0 |  | No Date | 2018-02-01 | ISU | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE
4601 | 1. Start-Up (Progressing through change governance) | US01 Exception Remove Dummy Meter Occurrences | CR | LIVE | 1. Awaiting ICAF Assignment | 15.02% |  |  | ICAF | 2018-01-30 | Jo Duncan/Dean Johnson | No Project Manager | 0 |  | No Date | 2018-03-09 | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3143 | 2. Change sanction/approved and in project delivery | COR3143 - Decommission XFTM & Server Farm & re-direct NG files Phase 1 | CP | LIVE | 11. Change In Delivery | 21.02% |  |  | T & SC | 2013-08-06 | Khawar Ahmed | Mark Pollard | 0 |  | 2018-02-28 | 2015-10-27 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3447 | 2. Change sanction/approved and in project delivery | COR3447 - XP1 Decommissioning | CP | LIVE | 11. Change In Delivery | 21.02% |  |  | T & SC | 2014-07-08 | Chris Fears | Mark Pollard | 0 |  | 2018-02-28 | 2000-02-02 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4112 | 2. Change sanction/approved and in project delivery | Microsoft Project Online Plus (MPOP) – Implementation of new PPM solution | CR | LIVE | 11. Change In Delivery | 19.22% |  |  | Other | 2016-10-03 | Steve Muffett | Catrin Morgan | 0 |  | 2018-02-01 | 2017-01-31 | Other | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | No Workaround Intensity | 2018-02-01 | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4117 | 2. Change sanction/approved and in project delivery | Transform Us | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | TU | 2016-10-05 | Steve Muffett | Helen Pardoe | 0 |  | 2018-09-20 | 2018-04-03 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4117.1 | 2. Change sanction/approved and in project delivery | TransformUs ERP | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | TU | 2016-10-05 | Steve Muffett | John Follows | 0 |  | 2018-08-31 | 2018-04-03 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4117.2 | 2. Change sanction/approved and in project delivery | TransformUs Desktop | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | TU | 2016-10-05 | Steve Muffett | Stewart McDermott | 0 |  | 2018-08-30 | 2018-04-03 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4117.3 | 2. Change sanction/approved and in project delivery | TransformUs Network | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | TU | 2016-10-05 | Steve Muffett | Stewart McDermott | 0 |  | 2018-10-05 | 2018-04-03 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4117.4 | 2. Change sanction/approved and in project delivery | TransformUs Auxiliary (Payroll/Flex Bens) | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | TU | 2016-10-05 | Steve Muffett | Julie Smart / Donna Hadley | 0 |  | 2018-05-15 | 2018-04-03 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4149 | 2. Change sanction/approved and in project delivery | NG Gateway Migration | CP | LIVE | 11. Change In Delivery | 15.02% |  |  | T & SC | 2016-11-28 | Beverley Viney | Nicola Patmore | 0 |  | 2018-05-09 | 2018-03-31 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4216 | 2. Change sanction/approved and in project delivery | API Platform Implementation | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | T & SC | 2017-02-03 | Gareth Hepworth | Mark Pollard | 0 |  | 2018-03-14 | 2017-12-10 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE
4368 | 2. Change sanction/approved and in project delivery | EU Gas Capacity Conversion Interim Optimal Solution | CP | LIVE | 11. Change In Delivery | 21.02% |  |  | T & SC | 2017-09-15 | Darren Lond/Beverley Viney | Rachel Addison | 0 |  | 2018-02-11 | 2018-01-01 | Gemini | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4376 | 2. Change sanction/approved and in project delivery | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | CP | LIVE | 11. Change In Delivery | 27.63% |  |  | T & SC | 2017-09-22 | Chris Gumbley/Darren Lond | Nicola Patmore | 0 |  | 2019-01-23 | 2019-01-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4378 | 2. Change sanction/approved and in project delivery | Solution Manager Upgrade | CR | LIVE | 11. Change In Delivery | 18.02% |  |  | R & N | 2017-10-02 | Smitha Pichrikat | Smitha Pichrikat | 0 |  | 2018-03-23 | 2018-04-03 | ISU | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4379 | 2. Change sanction/approved and in project delivery | Entry Scheduling (Entry and Exit Scheduling Summary Report & Detailed ESC Report) Bio Methane Exclusion | CR | LIVE | 11. Change In Delivery | 18.02% |  |  | Data Office | 2017-10-11 | Matthew Newman | Steve Concannon | 0 |  | 2018-02-23 | 2018-08-31 | BW | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | FALSE | TRUE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4440 | 2. Change sanction/approved and in project delivery | Npower MPRN Information report | CR | LIVE | 11. Change In Delivery | 34.23% |  |  | Data Office | 2016-08-04 | Emma Partlett | Steve Concannon | 0 | UKLP IADBI246 | 2018-02-23 | 2018-01-31 | BW | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4446 | 2. Change sanction/approved and in project delivery | CNG Monthly Shipper Pack | CR | LIVE | 11. Change In Delivery | 31.23% |  |  | Data Office | 2016-10-19 | Emma Marnell | Steve Concannon | 0 | UKLP IADBI268 | 2018-01-31 | 2018-01-31 | BW | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4468 | 2. Change sanction/approved and in project delivery | Proposal for the process improvement for SI files | CR | LIVE | 11. Change In Delivery | 21.02% | TBP | Medium | R & N | 2017-03-14 | Linda Whitcroft | Padmini Duvvuri | 0 | UKLP IADBI307 | 2018-02-19 | 2017-12-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4470 | 2. Change sanction/approved and in project delivery | MI & KPI Dashboard for Business Operations | CR | LIVE | 11. Change In Delivery | 13.81% |  |  | Data Office | 2017-03-31 | Michele Downes | Steve Concannon | 0 | UKLP IADBI312v2 | 2018-02-23 | 2018-11-01 | Other | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4515 | 2. Change sanction/approved and in project delivery | Inclusion of SAP ISU rejection information into SAP BW | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | Data Office | 2017-10-25 | Steve Concannon | Steve Concannon | 0 |  | 2018-02-23 | 2017-11-30 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4551 | 2. Change sanction/approved and in project delivery | Amendment to TOG reporting | CR | LIVE | 11. Change In Delivery | 34.83% |  |  | Data Office | 2017-12-06 | Kieran McNulty/Dave Acker/Sat Salsi | Steve Concannon | 0 |  | 2018-02-23 | 2017-10-01 | CMS | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4574 | 2. Change sanction/approved and in project delivery | Provision of a New Project Track UK Link Environment | CR | LIVE | 11. Change In Delivery | 9.009% |  |  | R & N | 2018-01-08 | Lee Chambers | Lee Chambers | 0 |  | No Date | No Date | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4575 | 2. Change sanction/approved and in project delivery | Introduction of a R&N Minor Release Delivery Mechanism | CR | LIVE | 11. Change In Delivery | 9.009% |  |  | R & N | 2018-01-09 | Lee Chambers | Lee Chambers | 0 |  | No Date | No Date | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2831.1 | 3. Change delivered, awaiting closure approval/sign-off | DCC Day 1 Delivery | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2012-11-21 | Joanna Ferguson | Helen Pardoe | 0 |  | 2014-06-29 | 2014-06-27 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2831.2 | 3. Change delivered, awaiting closure approval/sign-off | DSP Gateway Mechanism Analysis & Design | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2012-11-21 | Joanna Ferguson | Helen Pardoe | 0 |  | 2014-04-16 | 2000-02-02 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2831.4 | 3. Change delivered, awaiting closure approval/sign-off | Smart Metering UNC MOD 430: DCC User Gateway Network | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2014-03-13 | Jo Ferguson | Helen Pardoe | 0 |  | 2016-09-22 | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2831.5a | 3. Change delivered, awaiting closure approval/sign-off | Smart Metering UNC MOD 430 DCC Testing and Trialling Pre Nexus | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2015-12-22 | Jo Feguson | Helen Pardoe | 0 |  | 2017-03-31 | 2017-03-31 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2949 | 3. Change delivered, awaiting closure approval/sign-off | UNC Mod 458 Seasonal LDZ Capacity Rights | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2014-06-12 | Colin Thomson | Lorraine Cave | 0 |  | 2017-06-01 | 2014-10-31 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3151 | 3. Change delivered, awaiting closure approval/sign-off | Communications Link Solution for Provision of Smart Meter Data from iGT's to Xoserve | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2013-08-15 | Lee Chambers | Helen Pardoe | 0 |  | 2014-09-01 | 2014-04-30 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3151.1 | 3. Change delivered, awaiting closure approval/sign-off | Business to Xoserve to Business File Transfer Capability | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2014-01-16 | Lee Chambers | Helen Pardoe | 0 |  | 2014-09-29 | 2014-04-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3390 | 3. Change delivered, awaiting closure approval/sign-off | Billing History by all NTS capacity / commodity related charges (2003 - 2013) | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2014-05-16 | Sean McGoldrick | Mark Pollard | 0 |  | 2014-10-08 | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3457 | 3. Change delivered, awaiting closure approval/sign-off | Solution to meet the obligations of UNC MOD 425V & UNC MOD455 | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2014-08-28 | Joanna Ferguson | Jon Follows | 0 |  | 2015-07-09 | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3600 | 3. Change delivered, awaiting closure approval/sign-off | Xoserve Office Relocation | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | Other | 2015-03-20 | Jane Rocky | Julian Childs | 0 |  | 2016-07-29 | 2016-05-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3704 | 3. Change delivered, awaiting closure approval/sign-off | Creation of a Learning Management System | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | Other | 2015-05-18 | Ann Breen | Karen Anthony | 0 |  | 2016-09-06 | 2015-05-18 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3706 | 3. Change delivered, awaiting closure approval/sign-off | Updating Contact Centre telephone system | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2015-05-19 | Christina Francis | Mark Pollard | 0 |  | 2015-06-23 | 2015-08-31 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3720 | 3. Change delivered, awaiting closure approval/sign-off | Document Management System for Legal & Compliance | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | Other | 2015-05-22 | Joe Majoros | Gareth Hepworth | 0 |  | 2017-01-20 | 2016-10-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3907 | 3. Change delivered, awaiting closure approval/sign-off | Server Migration Support Project | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2015-12-03 | Emma Rose | Emma Rose | 0 |  | 2017-01-13 | 2015-12-08 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4009 | 3. Change delivered, awaiting closure approval/sign-off | Billing History by all NTS capacity / commodity related charges (applicable dates in 2014 to Nexus implementation) | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-04-12 | Beverley Viney | Mark Pollard | 0 |  | 2017-07-19 | 2016-06-30 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4043 | 3. Change delivered, awaiting closure approval/sign-off | DN Sales Outbound Services | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-26 | Chris Warner | Mark Pollard | 0 |  | 2017-06-01 | 2016-10-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4043.1 | 3. Change delivered, awaiting closure approval/sign-off | DN Sales (Outbound Services) | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-24 |  | Jon Follows | 0 |  | 2017-06-01 | 2016-10-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4043.2 | 3. Change delivered, awaiting closure approval/sign-off | DN Sales Outbound Services – DBI for current UK Link | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-26 |  | Jon Follows | 0 |  | 2017-06-01 | 2016-10-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4043.3 | 3. Change delivered, awaiting closure approval/sign-off | DN Sales Outbound Services – Operating costs for current UK Link | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-24 |  | Jon Follows | 0 |  | 2017-06-01 | 2016-10-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4043.4 | 3. Change delivered, awaiting closure approval/sign-off | DN Sales Outbound Services – Analysis on new UK Link | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-24 |  | Jon Follows | 0 |  | 2017-06-01 | 2017-01-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4043.5 | 3. Change delivered, awaiting closure approval/sign-off | DN Sales Outbound Services – DBI for new UK Link | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-24 |  | Jon Follows | 0 |  | 2017-06-01 | 2017-01-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4043.6 | 3. Change delivered, awaiting closure approval/sign-off | DN Sales Outbound Services – Operating costs for new UK Link | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-24 |  | Jon Follows | 0 |  | 2017-06-01 | 2017-01-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4082 | 3. Change delivered, awaiting closure approval/sign-off | Upgrade of Shared Components, Management Services and Network Switches | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | Other | 2016-08-05 | Chris Fears | Parminder Dhir | 0 |  | 2017-05-12 | 2017-05-30 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4110 | 3. Change delivered, awaiting closure approval/sign-off | Creation of a Service to Release Domestic Consumer Data to W’s & TPI’s | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-10-12 | Jo Ferguson | Mark Pollard | 0 |  | 2000-02-02 | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4242 | 3. Change delivered, awaiting closure approval/sign-off | Monthly provision of national S&U statistics | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2016-05-16 | Joanna Ferguson | Lorraine Cave | 0 |  | 2017-04-26 | 2016-09-30 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4380 | 3. Change delivered, awaiting closure approval/sign-off | Monthly Nomination Referral Report | CP | LIVE | 12. CCR/Closedown document in progress | 39.04% |  |  | Data Office | 2017-10-25 | Matt Smith | Tom Lineham | 0 | UKLP IADBI337 | 2018-01-19 | 2018-01-19 | BW | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | Service Area 21: Data Flows and Services to Network Operators | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4382 | 3. Change delivered, awaiting closure approval/sign-off | Charge Type creation to support CP4368 EU Gas Capacity Conversion change | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | T & SC | 2017-10-18 | Rachel Addison | Jessica Harris | 0 |  | 2018-01-19 | 2017-12-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4462 | 3. Change delivered, awaiting closure approval/sign-off | BEIS_Consumption Data | CR | LIVE | 12. CCR/Closedown document in progress | 24.92% | TBP | High | Data Office | 2017-02-08 | Fiona Cottam | Steve Concannon | 0 | UKLP IADBI294 | 2018-01-19 | 2018-09-01 | BW | FALSE | [5 empty] | BEIS | One Market Group | FALSE | FALSE | FALSE | Service Area 19: Network Operator and User Relationship Management | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4511 | 3. Change delivered, awaiting closure approval/sign-off | Monthly AQ performance statistics | CR | LIVE | 12. CCR/Closedown document in progress | 13.21% |  |  | Data Office | 2017-10-25 | Sue Prosser | Steve Concannon | 0 |  | 2018-01-19 | 2018-06-01 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4520 | 3. Change delivered, awaiting closure approval/sign-off | UIG Monthly Reporting | CR | LIVE | 12. CCR/Closedown document in progress | 21.62% |  |  | Data Office | 2017-10-30 | Linda Whitcroft | Steve Concannon | 0 |  | 2018-01-19 | 2017-11-30 | BW | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4559 | 3. Change delivered, awaiting closure approval/sign-off | Amending the reporting requirements to release data to Meter Asset Provider organisations. Modification 0637. | CR | LIVE | 12. CCR/Closedown document in progress | 27.03% |  |  | Data Office | 2017-12-12 | Ellie Rogers | Steve Concannon | 0 |  | 2018-01-31 | 2018-01-31 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3991 | 3. Change delivered, awaiting closure approval/sign-off | Procurement for the PAF Administrator Role | CP | LIVE | 13.2 Closedown document awaiting approval | 21.02% |  |  | T & SC | 2016-03-11 | Robert Wigginton | Mark Pollard | 0 |  | 2017-06-26 | 2017-06-26 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4073 | 3. Change delivered, awaiting closure approval/sign-off | EU Phase 4A | CP | LIVE | 13.2 Closedown document awaiting approval | 21.02% |  |  | T & SC | 2016-07-25 | Beverley Viney | Rachel Addison | 0 |  | 2017-09-22 | 2017-10-01 | Gemini | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3428 | 3. Change delivered, awaiting closure approval/sign-off | Correction of CWV data on the National Grid Operational website as a result of incorrect weather flows for NE LDZ | CP | LIVE | 14. Awaiting ECF Sign-Off | 21.02% |  |  | T & SC | 2014-06-18 | Joanna Ferguson | Mark Pollard | 0 |  | 2000-02-02 | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3842 | 3. Change delivered, awaiting closure approval/sign-off | Modification Proposal 466AV - Changes to DM Read Services (with improved within day data provision) | CP | LIVE | 14. Awaiting ECF Sign-Off | 21.02% |  |  | T & SC | 2015-10-14 | Chris Warner | Mark Pollard | 0 |  | 2016-03-01 | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4079 | 3. Change delivered, awaiting closure approval/sign-off | Reports required under UNC TPD V16.1 in legacy systems (reports required by Mod 520A) | CP | LIVE | 14. Awaiting ECF Sign-Off | 21.02% |  |  | T & SC | 2016-08-05 | Richard Pomroy | Mark Pollard | 0 |  | 2017-04-01 | 2000-02-02 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4160 | 1. Start-Up (Progressing through change governance) | Provision of data for TRAS relating to permission provided in UNC0574 | CP | LIVE | 2.1. Start-Up Approach In Progress | 21.02% |  |  | T & SC | 2016-12-09 | Joanna Ferguson | Lorraine Cave | 0 |  | No Date | 2000-02-02 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4353 | 1. Start-Up (Progressing through change governance) | General Data Protection Regulation and Data Protection Bill | CR | LIVE | 2.1. Start-Up Approach In Progress | 15.02% |  |  | Other | 2017-08-24 | Emma Mascall | Sally Hall | 0 |  | 2018-05-25 | 2018-04-03 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4489 | 1. Start-Up (Progressing through change governance) | FOF environment for GDE Lookup tables in SAP BW | CR | LIVE | 2.1. Start-Up Approach In Progress | 10.21% |  |  | T & SC | 2017-06-19 | Darran Dredge | Mark Pollard | 0 | UKLP IADBI343 | No Date | 2018-11-01 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4527 | 1. Start-Up (Progressing through change governance) | New Service Line for Reporting Services to Performance Assurance Committee (PAC) | CP | LIVE | 2.1. Start-Up Approach In Progress | 21.02% |  |  | Other | 2017-11-01 | John Welsh/Rachel Hinsley | Andy Miller | 0 |  | No Date | 2017-12-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4542 | 1. Start-Up (Progressing through change governance) | Changes to the PSR Report (new fields and removal of fields no longer applicable) | CP | LIVE | 2.1. Start-Up Approach In Progress | 22.22% |  |  | Data Office | 2017-11-24 | Emma Smith | Steve Concannon | 0 |  | 2018-03-23 | 2018-11-01 | BW | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4549 | 1. Start-Up (Progressing through change governance) | Future Solution for Hosting and Support of www.xoserve.com | CR | LIVE | 2.1. Start-Up Approach In Progress | 21.02% |  |  | Other | 2017-12-05 | Mohamed Abdel-Gadir | Sarah Bridge | 0 |  | No Date | 2017-12-20 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4552 | 1. Start-Up (Progressing through change governance) | ‘Front end’ development of new Company Intranet | CR | LIVE | 2.1. Start-Up Approach In Progress | 21.02% |  |  | Other | 2017-12-05 | Sarah Bridge | Sarah Bridge | 0 |  | No Date | 2017-06-30 | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4571 | 1. Start-Up (Progressing through change governance) | MAM and MAP asset data analysis and reporting | CR | LIVE | 2.1. Start-Up Approach In Progress | 18.02% |  |  | Data Office | 2018-01-03 | Andy Miller Andy Miller | Steve Concannon | 0 |  | No Date | 2018-02-15 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4576 | 1. Start-Up (Progressing through change governance) | Class 4 Transfer Reads not visible to shippers in DES | CP | LIVE | 2.1. Start-Up Approach In Progress | 9.009% |  |  | Data Office | 2018-01-09 | Alison Cross | Steve Concannon | 0 |  | No Date | No Date | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4577 | 1. Start-Up (Progressing through change governance) | Delivery assessment for introduction of new Demand Estimation system/tools | CR | LIVE | 2.1. Start-Up Approach In Progress | 31.53% |  |  | T & SC | 2018-01-10 | Linda Whitcroft | Emma Rose | 0 |  | No Date | 2018-01-31 | Other | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4579 | 1. Start-Up (Progressing through change governance) | Monthly EUC1 and 2 Report | CR | LIVE | 2.1. Start-Up Approach In Progress | 36.94% |  |  | Data Office | 2018-01-16 | Ryan Larner | Steve Concannon | 0 |  | 2018-02-23 | 2018-01-31 | Other | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4580 | 1. Start-Up (Progressing through change governance) | Shipper Performance Birst Dashboard (by Data Cleansing Topic) | CR | LIVE | 2.1. Start-Up Approach In Progress | 24.62% |  |  | Data Office | 2018-01-16 | James Verdon | Steve Concannon | 0 |  | No Date | 2018-02-28 | ISU | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4584 | 1. Start-Up (Progressing through change governance) | Central Switching Services | CR | LIVE | 2.1. Start-Up Approach In Progress | 9.009% |  |  | R & N | 2018-01-17 | Andy Earnshaw | Smitha Pichrikat | 0 |  | No Date | No Date | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4592 | 1. Start-Up (Progressing through change governance) | BIRST work item inclusion & multiple daily updates | CR | LIVE | 2.1. Start-Up Approach In Progress | 27.33% |  |  | Data Office | 2018-01-23 | Jo Duncan | Steve Concannon | 0 |  | No Date | No Date | ISU | TRUE | Xoserve | Daily | One | Medium | 2018-02-28 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4594 | 1. Start-Up (Progressing through change governance) | Customer Inclusion for BIRST Exceptions | CR | LIVE | 2.1. Start-Up Approach In Progress | 32.43% |  |  | Data Office | 2018-01-23 | Jo Duncan/Thomas Elce | Steve Concannon | 0 |  | No Date | 2018-02-01 | ISU | TRUE | Xoserve | Monthly | One | Medium | 2018-02-28 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4354 | 1. Start-Up (Progressing through change governance) | Request for New DNO Report Nested CSEPs Hierarchy Report | CP | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 34.23% |  |  | Data Office | 2017-09-01 | Cadent Gas /Emma Smith | Steve Concannon | 0 |  | No Date | 2018-02-01 | BW | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4426 | 1. Start-Up (Progressing through change governance) | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of Ofgem RFI | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 47.45% | TBP | High | Data Office | 2016-04-28 | Paul Orsler | Steve Concannon | 0 | UKLP IADBI192 | No Date | 2018-01-31 | BW | FALSE | [5 empty] | CMA Order | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4556 | 1. Start-Up (Progressing through change governance) | Process to provide a report when Gas Safety Regulations requests return no MPRN’s | CP | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 21.02% |  |  | R & N | 2017-12-06 | Andy Clasper | Padmini Duvvuri | 0 |  | No Date | 2017-12-19 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4563 | 1. Start-Up (Progressing through change governance) | Assurance of the Annual AQ activities | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 33.03% |  |  | Data Office | 2017-12-18 | Sue Prosser | Steve Concannon | 0 |  | 2018-03-31 | 2018-02-01 | BW | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4567 | 1. Start-Up (Progressing through change governance) | Amendment to plot to postal report | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 22.82% |  |  | Data Office | 2018-01-02 | Tahera Choudhury | Steve Concannon | 0 |  | 2018-02-23 | 2018-02-28 | BW | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4570 | 1. Start-Up (Progressing through change governance) | BW Reports - RA/ RANTS Reporting Logic | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 27.63% |  |  | Data Office | 2017-01-03 | Michael Maguire | Steve Concannon | 0 |  | No Date | 2018-01-31 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4573 | 1. Start-Up (Progressing through change governance) | AQ Market Breaker Tolerance validation values Error | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 28.53% |  |  | R & N | 2018-01-03 | Sue Pross | Padmini Duvvuri | 0 |  | No Date | 2018-01-31 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4578 | 1. Start-Up (Progressing through change governance) | Monthly AQ Calculations for Class 4 sites with AMR fitted | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 39.64% |  |  | Other | 2018-01-10 | Rachel martin/Emma Lyndon | Donna Johnson | 0 |  | No Date | 2018-01-31 | ISU | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4581 | 1. Start-Up (Progressing through change governance) | MD05 – Automatic Exception resolver Batch Job change | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 28.83% |  |  | Other | 2018-01-16 | Jo Duncan | Donna Johnson | 0 |  | No Date | No Date | ISU | TRUE | Xoserve | Daily | One | Medium | 2018-02-28 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | No DSC Service Area | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4582 | 1. Start-Up (Progressing through change governance) | Amendment Invoice Reporting Automation | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 66.97% |  |  | Data Office | 2018-01-16 | Dean Johnson | Steve Concannon | 0 |  | No Date | 2018-01-31 | ISU | TRUE | Xoserve | Weekly | Two to Five | High | 2018-03-31 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4588 | 1. Start-Up (Progressing through change governance) | Network Templates (New Shipper) | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 41.14% |  |  | Other | 2018-01-22 | Nicola Dowding | Donna Johnson | 0 |  | No Date | 2019-01-02 | Other | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 23: Internal | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4589 | 1. Start-Up (Progressing through change governance) | Network Templates (Name Change) | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 38.44% |  |  | Other | 2018-01-22 | Nicola Dowling | Donna Johnson | 0 |  | No Date | 2018-02-02 | AMT | TRUE | Xoserve | Daily | One | Medium | 2018-02-28 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | TRUE | TRUE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4590 | 1. Start-Up (Progressing through change governance) | SLSP - Incorrect Seasonal Large Supply Point charging | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 46.25% |  |  | ICAF | 2018-01-12 | Carole Elwell | Steve Concannon | 0 |  | No Date | 2018-03-31 | BW | TRUE | Xoserve | Monthly | One | Medium | 2018-03-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4591 | 1. Start-Up (Progressing through change governance) | FOF environment for GDE Lookup tables in SAP BW | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 31.53% |  |  | Other | 2018-01-23 | Julie Bretherton | Donna Johnson | 0 |  | No Date | 2017-02-06 | BW | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4595 | 1. Start-Up (Progressing through change governance) | SAP T-Code Access – Modification to ISU & BW Permissions for Data Office Aligned Resources | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 27.63% |  |  | Other | 2018-01-23 | Steve Concannon | Donna Johnson | 0 |  | No Date | 2018-01-31 | AMT | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4596 | 1. Start-Up (Progressing through change governance) | Setup of File Transfer mechanism from BO to IX | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 24.62% |  |  | Other | 2018-01-23 | Steve Concannon | Donna Johnson | 0 |  | No Date | 2018-02-28 | IX | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4568 | 1. Start-Up (Progressing through change governance) | DSC Service Description Table cosmetic changes to Service Lines | CP | LIVE | 4. EQR In-Progress | 25.23% |  |  | Other | 2018-01-02 | Andy Miller | Andy Miller | 0 |  | 2018-03-30 | 2018-03-30 | Other | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4324 | 1. Start-Up (Progressing through change governance) | Checkpoint Hardware Upgrade | CR | LIVE | 7. BER/Business Case In Progress | 21.02% |  |  | T & SC | 2017-06-29 | Chris Fears | Tony Long | 0 |  | 2018-03-01 | 2017-12-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4325 | 1. Start-Up (Progressing through change governance) | Cisco Security Upgrade | CR | LIVE | 7. BER/Business Case In Progress | 21.02% |  |  | T & SC | 2017-06-29 | Chris Fears | Tony Long | 0 |  | 2018-03-01 | 2018-02-02 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4349 | 1. Start-Up (Progressing through change governance) | Control-M/EM, Server and agent upgrade for Gemini and CMS | CR | LIVE | 7. BER/Business Case In Progress | 11.41% |  |  | T & SC | 2017-08-18 | Annie Griffith | Emma Rose | 0 |  | 2018-07-31 | 2018-07-31 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4550 | 1. Start-Up (Progressing through change governance) | Gemini Re-platform | CP | LIVE | 7. BER/Business Case In Progress | 19.22% |  |  | T & SC | 2017-12-04 | Phil Hobbins | Hannah Reddy | 0 |  | No Date | 2020-01-01 | Gemini | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4562 | 1. Start-Up (Progressing through change governance) | Business Excellence | CR | LIVE | 7. BER/Business Case In Progress | 15.02% |  |  | T & SC | 2017-12-18 | Andy Simpson | Debi Jones | 0 |  | No Date | 2018-03-31 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1154 | 2. Change sanction/approved and in project delivery | UK Link Programme | CP | LIVE | 11. Change In Delivery | 22.22% |  |  | R & N | 2008-03-03 | Chris Smith | Paul Toolan | 1 |  | 2017-06-01 | 2017-06-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 23: Internal | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3747 | 3. Change delivered, awaiting closure approval/sign-off | Notification of Formula Year AQ & SOQ | CP | LIVE | 12. CCR/Closedown document in progress | 13.21% | High | High | R & N | 2015-07-07 | Emma Smith / Susan Prosser | Matt Rider | 1.1 | UKLP IADBI113 | 2017-12-08 | 2018-05-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4340 | 3. Change delivered, awaiting closure approval/sign-off | UK Link Future Release 1.1 | CP | LIVE | 12. CCR/Closedown document in progress | 13.21% |  |  | R & N | 2017-08-03 | Matt Rider/Dave Turpin | Matt Rider | 1.1 |  | 2017-12-08 | 2018-05-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4448 | 3. Change delivered, awaiting closure approval/sign-off | Capacity referral raised in error following Nomination | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% | High | High | R & N | 2016-11-09 | Dean Johnson | Matt Rider | 1.1 | UKLP IADBI272 | 2017-12-08 | 2017-12-08 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4452 | 3. Change delivered, awaiting closure approval/sign-off | Pending capacity amendment with Ratchet | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% | Medium | Medium | R & N | 2016-12-06 | Dean Johnson | Matt Rider | 1.1 | UKLP IADBI279 | 2017-12-08 | 2017-12-08 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4466 | 3. Change delivered, awaiting closure approval/sign-off | Mod431 – Validations against file header and data within records | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% | High | High | R & N | 2017-02-27 | Steve Nunnington | Matt Rider | 1.1 | UKLP IADBI305 | 2017-12-08 | 2017-12-08 | AMT | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4510 | 3. Change delivered, awaiting closure approval/sign-off | Negative Consumption Period For Rolling AQ20171023 | CP | LIVE | 13.1. CCR Awaiting ChMC Approval | 21.02% |  |  | R & N | 2017-10-25 | Linda Whitcroft | Debi ¦Jones | 1.1 |  | 2017-12-08 | 2017-12-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4463 | 2. Change sanction/approved and in project delivery | CSEP MAX AQ SOQ Rate Application | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | R & N | 2017-02-20 | Emma Smith | Padmini Duvvuri | 1.15 | UKLP IADBI298 | 2018-02-02 | 2018-04-03 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2831.5b | 2. Change sanction/approved and in project delivery | Changes to the upper parameter of the XDO partial refresh file. Post Nexus (R2) | CR | LIVE | 11. Change In Delivery | 21.02% | TBP | High | R & N | 2017-02-07 | Jon Follows | Christina Francis | 2 | UKLP292 | 2018-06-29 | 2017-04-07 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3283 | 2. Change sanction/approved and in project delivery | Recording of DN Siteworks’ / New Network Connection Reference in Central systems (ON HOLD PENDING NEW CO) | CP | LIVE | 11. Change In Delivery | 21.02% | Low | Low | R & N | 2013-12-16 | Joel Martin | Christina Francis | 2 | n/a | 2018-06-29 | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3386 | 2. Change sanction/approved and in project delivery | Create new “role” for CMS to cover all activities undertaken within a Distribution Network (ON HOLD PENDING NEW CO) | CP | LIVE | 11. Change In Delivery | 21.02% | Low | Low | R & N | 2014-05-08 | Jo Ferguson | Christina Francis | 2 | n/a | 2018-06-29 | 2000-02-02 | CMS | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3477 | 2. Change sanction/approved and in project delivery | Missing Key Data Item from iGT’s to Shippers (Plot Number) | CP | LIVE | 11. Change In Delivery | 21.02% | High | High | R & N | 2015-07-07 | Lee Chambers | Christina Francis | 2 | UKLP IADBI112 | 2018-06-29 | 2000-02-02 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3995a | 2. Change sanction/approved and in project delivery | Energy Theft Tip-off Service Data Provision | CP | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2016-03-15 | Alex Ross-Shaw | Christina Francis | 2 | UKLP222 | 2018-06-29 | 2016-08-01 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4248 | 2. Change sanction/approved and in project delivery | Quarterly smart metering reporting for HS&E and GDNs (post Nexus R2) | CP | LIVE | 11. Change In Delivery | 21.02% | High | High | R & N | 2017-03-22 | Joanna Ferguson | Christina Francis | 2 | n/a | 2018-06-29 | 2017-06-29 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4249 | 2. Change sanction/approved and in project delivery | Address Maintenance Solution | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-03-22 | Steve Ganney | Christina Francis | 2 |  | 2018-06-29 | 2017-11-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4288 | 2. Change sanction/approved and in project delivery | DDS/DDU file amendment | CP | LIVE | 11. Change In Delivery | 21.02% | Low | High pending discussions with all Networks | R & N | 2015-10-14 |  | Christina Francis | 2 | UKLP IADBI147 | 2018-06-29 | 2017-11-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4299 | 2. Change sanction/approved and in project delivery | Reports required under UNC TPD V16.1 in Nexus (reports required by Mod 520A) | CP | LIVE | 11. Change In Delivery | 13.21% | High | High | R & N | 2016-08-12 |  | Christina Francis | 2 | UKLP251 | 2018-06-29 | 2018-05-01 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4303 | 2. Change sanction/approved and in project delivery | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | CR | LIVE | 11. Change In Delivery | 13.21% | TBP | Low | R & N | 2016-10-18 | Dean Johnson | Christina Francis | 2 | UKLP267 | 2018-06-29 | 2018-05-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4304 | 2. Change sanction/approved and in project delivery | Amend referral rules for class 2 smaller LSP’s | CR | LIVE | 11. Change In Delivery | 13.21% | TBP | Medium | R & N | 2016-11-03 | Dean Johnson | Christina Francis | 2 | UKLP270 | 2018-06-29 | 2018-05-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4309 | 2. Change sanction/approved and in project delivery | Back billing for domestic (SSP) sites needs to be reflect thecorrect adjustment start date | CR | LIVE | 11. Change In Delivery | 13.21% | TBP | Low | R & N | 2016-01-19 | Dean Johnson | Christina Francis | 2 | UKLP287 | 2018-06-29 | 2018-05-01 | CMS | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4316 | 2. Change sanction/approved and in project delivery | Meter Point Details Report & Sector Breakdown Report | CR | LIVE | 11. Change In Delivery | 13.21% | TBP | Low | R & N | 2017-04-07 | Mark Cockayne | Christina Francis | 2 | UKLP315 | 2018-06-29 | 2018-05-01 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4361 | 2. Change sanction/approved and in project delivery | Release 2 Delivery | CP | LIVE | 11. Change In Delivery | 13.21% |  |  | R & N | 2017-10-11 | Christina Francis | Christina Francis | 2 |  | 2018-06-29 | 2018-05-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4449 | 2. Change sanction/approved and in project delivery | PSR requirements – Vulnerable Customer data requirements | CP | LIVE | 11. Change In Delivery | 21.02% | High | High | R & N | 2016-11-11 | Steve Nunnington | Christina Francis | 2 | UKLP273 | 2018-06-29 | 2017-06-29 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4513 | 2. Change sanction/approved and in project delivery | Change to validation of address fields | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI359 | 2018-06-29 | 2017-11-01 | CMS | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4514 | 2. Change sanction/approved and in project delivery | MIV File Changes for MUR Invoice - CMS | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI367 | 2018-06-29 | 2017-12-01 | CMS | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3656 | 1. Start-Up (Progressing through change governance) | Read Validation Tolerances | CR | LIVE | 4. EQR In-Progress | 13.21% | TBP | Low | R & N | 2014-12-24 | Michelle Downes | Padmini Duvvuri | 3 | UKLP IADBI060 | No Date | 2018-05-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3667 | 1. Start-Up (Progressing through change governance) | Provision of Formula Year AQ | CR | LIVE | 4. EQR In-Progress | 10.21% | High | High | R & N | 2015-02-06 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI071 | No Date | 2018-12-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
4273 | 1. Start-Up (Progressing through change governance) | Introducing IHD (In-Home Display) Installed Status of Failed MOD614 | CP | LIVE | 4. EQR In-Progress | 25.23% |  |  | R & N | 2017-05-10 | Alex Cebo | Padmini Duvvuri | 3 |  | No Date | 2018-06-01 | ISU | FALSE | [5 empty] | SPAA Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4337 | 1. Start-Up (Progressing through change governance) | To change the optionality of the Supply Point confirmation reference for the T51 file | CR | LIVE | 4. EQR In-Progress | 30.63% |  |  | R & N | 2017-07-24 | Sue prosse/Emma Lyndon | Padmini Duvvuri | 3 |  | 2017-07-31 | 2018-04-01 | AMT | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | One | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4381 | 1. Start-Up (Progressing through change governance) | The updating of the ZDT_AQ_OPER table | CR | LIVE | 4. EQR In-Progress | 36.04% |  |  | R & N | 2017-10-06 | Sue Prosser/Emma Lyndon | Tom Lineham | 3 |  | No Date | 2018-02-19 | ISU | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4431 | 1. Start-Up (Progressing through change governance) | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | CR | LIVE | 4. EQR In-Progress | 33.03% | TBP | High | R & N | 2016-05-04 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI202 | No Date | 2018-10-01 | ISU | TRUE | External Customer | Daily | No Xoserve FTEs | Low | 2018-12-31 | MOD/Ofgem | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
4432 | 1. Start-Up (Progressing through change governance) | Amendment to U82 record to include the revised NTS optional tariff rate | CR | LIVE | 4. EQR In-Progress | 21.62% | TBP | Low | R & N | 2016-05-04 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI203 | No Date | 2018-06-01 | ISU | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4436 | 1. Start-Up (Progressing through change governance) | Change number of occurances for K13 record for SSMP’s | CR | LIVE | 4. EQR In-Progress | 22.82% | TBP | Low | R & N | 2016-06-21 | Dean Johnson | Padmini Duvvuri | 3 | UKLP IADBI225 | No Date | 2018-06-01 | ISU | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4443 | 1. Start-Up (Progressing through change governance) | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | CR | LIVE | 4. EQR In-Progress | 24.62% | TBP | Low | R & N | 2016-09-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI258 | No Date | 2018-06-01 | ISU | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE
4453 | 1. Start-Up (Progressing through change governance) | File Format Should Have Changes | CR | LIVE | 4. EQR In-Progress | 33.63% | TBP | Low | R & N | 2016-12-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI280v3 | No Date | 2018-06-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE
4454 | 1. Start-Up (Progressing through change governance) | Cadent Billing - DN Sales (Outbound Services) | CP | LIVE | 4. EQR In-Progress | 51.95% | TBP | High | R & N | 2016-12-16 | Linda Whitcroft | Padmini Duvvuri | 3 | UKLP IADBI281 | 2018-06-29 | 2018-06-01 | ISU | TRUE | Both Xoserve & Customer | Daily | 2-5 | High | 2018-06-01 | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | High | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
4458 | 1. Start-Up (Progressing through change governance) | Class 4 CSEPS Reconciliation Variance Identification | CR | LIVE | 4. EQR In-Progress | 22.22% | TBP | Medium | R & N | 2017-01-26 | Karen Marklew | Padmini Duvvuri | 3 | UKLP IADBI289 | No Date | 2018-12-31 | ISU | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4481 | 1. Start-Up (Progressing through change governance) | Resolution of penny mismatches within invoice supporting information for Core invoices. | CR | LIVE | 4. EQR In-Progress | 31.83% |  |  | R & N | 2017-05-30 | Kiran Kumar | Padmini Duvvuri | 3 | UKLP IADBI332 | 2018-03-01 | 2018-06-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4486 | 1. Start-Up (Progressing through change governance) | Meter Type O = Oriffice to be an acceptable value in file formats and reports | CR | LIVE | 4. EQR In-Progress | 21.62% |  |  | R & N | 2017-06-05 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI338 | No Date | 2018-06-01 | ISU | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
4495 | 1. Start-Up (Progressing through change governance) | Energy Tolerance Rejection code | CR | LIVE | 4. EQR In-Progress | 26.43% |  |  | R & N | 2017-06-28 | Nick Timm | Padmini Duvvuri | 3 | UKLP IADBI356 | No Date | 2018-11-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
4534 | 1. Start-Up (Progressing through change governance) | Amendment to RGMA Validation Rules for Meter Asset Installation Date | CP | LIVE | 4. EQR In-Progress | 52.85% |  |  | R & N | 2017-11-20 | Andrew Margan | Padmini Duvvuri | 3 |  | No Date | 2018-06-01 | No Application | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | One | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4538 | 1. Start-Up (Progressing through change governance) | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File. | CR | LIVE | 4. EQR In-Progress | 9.009% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | 2000-02-02 | No Date | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4539 | 1. Start-Up (Progressing through change governance) | New File Level Rejection | CR | LIVE | 4. EQR In-Progress | 26.43% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | 2000-02-02 | 2018-11-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4572 | 1. Start-Up (Progressing through change governance) | Retail & Network Release 3 | CP | LIVE | 4. EQR In-Progress | 9.009% |  |  | R & N | 2018-01-03 | Padmini Duvvuri | Padmini Duvvuri | 3 |  | No Date | No Date | No Application | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4525 | 1. Start-Up (Progressing through change governance) | Transparency of the Rolling AQ Process | CP | LIVE | 0. ROM In-Progress | 29.43% |  |  | R & N | 2017-10-31 | Shane Preston/Rachel Hinsley | Padmini Duvvuri | 50 |  | 2018-01-25 | 2018-11-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4543 | 1. Start-Up (Progressing through change governance) | UNC Modification 0636 - - Updating the parameters for the NTS Optional Commodity Charge | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 44.44% |  |  | R & N | 2017-11-28 | Debra Hawkin | Padmini Duvvuri | 50 |  | 2017-12-11 | 2018-06-01 | ISU | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4545 | 1. Start-Up (Progressing through change governance) | UNC Modification 0619B - Application of proportionate ratchet charges to daily read sites | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 42.64% |  |  | R & N | 2017-11-29 |  | Murray Thomson | 50 |  | 2017-12-13 | 2018-10-01 | ISU | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3676 | 2. Change sanction/approved and in project delivery | Amendment to the AQ &SOQ File and Field Length | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | T & SC | 2015-03-24 | Jo Tedd/ Dan Donovan | Donna Johnson | 50 | UKLP IADBI080 | 2018-02-28 | 2015-10-01 | Gemini | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4169 | 2. Change sanction/approved and in project delivery | To update functionality in Gemini to ensure that all Cash Call Notices and Templates reflect UNC Section X and Energy Balancing Credit Rules. To review the possibility of Gemini producing automatic Further Security Notices and associated Fax Headers with | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | T & SC | 2017-01-09 | Loraine O’Shaughnessy | Donna Johnson | 50 |  | 2018-04-29 | 2018-04-29 | Gemini | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4357 | 2. Change sanction/approved and in project delivery | Offline Systems Database D096 Phase 3 | CR | LIVE | 11. Change In Delivery | 18.02% |  |  | other | 2017-09-04 | Sandra Dworkin | Donna Johnson | 50 |  | 2018-02-28 | 2018-02-28 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4358 | 2. Change sanction/approved and in project delivery | Offline Systems Database D096 Phase 2 | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-09-04 | Dan Donovan/Sandra Simpson | Donna Johnson | 50 |  | 2018-02-28 | 2017-10-28 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4364 | 2. Change sanction/approved and in project delivery | Offline Systems Database D361 FGO Indebtedness Database | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | other | 2017-09-13 | Michelle Kearney / Sandra Dworkin | Donna Johnson | 50 |  | 2018-02-23 | 2017-09-30 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4493 | 2. Change sanction/approved and in project delivery | BIRST Connect integration | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | Data Office | 2017-06-26 | Steve Concannon | Emma Rose | 50 | UKLP IADBI353 | 2018-01-31 | 2017-11-30 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4508 | 2. Change sanction/approved and in project delivery | USM File Occurrence Limit Change | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-10-25 | Dean Johnson/Sandra Simpson | Padmini Duvvuri | 50 |  | 2018-02-02 | 2017-11-03 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4521 | 2. Change sanction/approved and in project delivery | NTS Datalogged Site not being loaded into Gemini | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-10-31 | Liz Ryan/Emma Lyndon | Padmini Duvvuri | 50 |  | 2018-04-29 | 2000-02-02 | Gemini | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4528 | 2. Change sanction/approved and in project delivery | The word ‘PLOT’ as a prefix | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-11-07 | Mike Orsler/Emma Smith | Padmini Duvvuri | 50 |  | 2018-03-02 | 2017-11-11 | CMS | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4536 | 2. Change sanction/approved and in project delivery | NTS Shorthaul – UK-Link composite role | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-11-15 | Pete Hailstone/Mark Cockayne | Padmini Duvvuri | 50 |  | 2018-02-02 | 2017-12-04 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4348 | 3. Change delivered, awaiting closure approval/sign-off | D346 Enhancement | CR | LIVE | 12. CCR/Closedown document in progress | 21.02% |  |  | Other | 2017-08-21 | Carole Elwell | Donna Johnson | 50 |  | 2018-01-05 | 2017-08-31 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4044 | 1. Start-Up (Progressing through change governance) | Extension of ‘Must Read’ process to include Annual Read sites | CP | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 21.02% |  |  | R & N | 2017-12-05 | Andy Clasper | Donna Johnson | 50 |  | No Date | 2016-09-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4328 | 1. Start-Up (Progressing through change governance) | Report of iGT Meter Points where the confirming shipper is not the elected shipper | CP | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 42.04% |  |  | Data Office | 2017-07-05 | Emma Smith | Steve Concannon | 50 |  | No Date | 2018-02-01 | BW | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | TRUE | Service Area 18: Provision of User Reports and Information | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4554 | 1. Start-Up (Progressing through change governance) | Amendment Invoice validation Reports | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 21.02% |  |  | R & N | 2017-12-05 | Vicky Spiller | Padmini Duvvuri | 50 |  | 2018-06-30 | 2018-01-31 | BW | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4561 | 1. Start-Up (Progressing through change governance) | US01 Exception Automation | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 56.46% |  |  | R & N | 2017-12-18 | Jo Duncan | Padmini Duvvuri | 50 |  | No Date | 2018-02-28 | ISU | TRUE | Xoserve | Daily | Five to Ten | Medium | 2018-02-28 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | No DSC Service Area | No Number of impacted DSC Service Areas | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4593 | 1. Start-Up (Progressing through change governance) | Removal of Backbiling Exceptions (BB02, BB04, BB05) | CR | LIVE | 1. Awaiting ICAF Assignment | 33.33% |  |  | R & N | 2018-01-23 | Jo Duncan | Matt Rider | 99 |  | No Date | 2018-03-30 | ISU | TRUE | Xoserve | Daily | One | Medium | 2018-02-28 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3732 | 1. Start-Up (Progressing through change governance) | Capability to replace a sequence of readings | CR | LIVE | 2.1. Start-Up Approach In Progress | 43.24% | High | Medium | R & N | 2015-06-17 | Emma Smith | Matt Rider | 99 | UKLP IADBI109 | No Date | 2018-11-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4421 | 1. Start-Up (Progressing through change governance) | Addition of Daily LDZ Unidentified Gas (UG) to National Grid Operational Data Services | CR | LIVE | 2.1. Start-Up Approach In Progress | 36.04% | TBP | Medium | R & N | 2015-12-17 | Fiona Cottam | Matt Rider | 99 | UKLP IADBI162 | No Date | 2017-06-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | Service Area 15: Demand Estimation | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4461 | 1. Start-Up (Progressing through change governance) | Splitting of the DXI inbound and DXR outbound file from the DCC. | CR | LIVE | 2.1. Start-Up Approach In Progress | 20.42% | TBP | Consensus is Medium, One DN had a recommendation of high | R & N | 2017-02-07 | Jon Follows | Matt Rider | 99 | UKLP IADBI293 | No Date | 2018-12-31 | ISU | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4469 | 1. Start-Up (Progressing through change governance) | UMR Hierarchy Amendment in AMT | CR | LIVE | 2.1. Start-Up Approach In Progress | 27.63% | TBP | Low | R & N | 2017-03-27 | Karen Marklew | Matt Rider | 99 | UKLP IADBI309 | No Date | 2018-10-01 | AMT | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4473 | 1. Start-Up (Progressing through change governance) | Sybase NLS Solution Design Gap | CR | LIVE | 2.1. Start-Up Approach In Progress | 16.82% | TBP | Low | R & N | 2017-04-11 | Lee Chambers | Matt Rider | 99 | UKLP IADBI317 | No Date | 2018-06-01 | Other | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4474 | 1. Start-Up (Progressing through change governance) | Delivery of Retro | CR | LIVE | 2.1. Start-Up Approach In Progress | 36.04% | TBP | High | R & N | 2017-04-21 | Lee Chambers | Matt Rider | 99 | UKLP IADBI319 | No Date | 2019-02-01 | ISU | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Five to Twenty | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4480 | 1. Start-Up (Progressing through change governance) | Capacity reconciliation charge (MOD445) calculation functionality | CR | LIVE | 2.1. Start-Up Approach In Progress | 48.65% |  |  | R & N | 2017-05-30 | Kiran Kumar | Matt Rider | 99 | UKLP IADBI331 | No Date | 2018-10-01 | ISU | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4484 | 1. Start-Up (Progressing through change governance) | Remove restriction on nominated SOQ (as per MOD 445 | CR | LIVE | 2.1. Start-Up Approach In Progress | 36.64% |  |  | R & N | 2017-06-06 | Bhupinder Basra | Matt Rider | 99 | UKLP IADBI336 | No Date | 2018-10-01 | ISU | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4488 | 1. Start-Up (Progressing through change governance) | API Management Platform Implementation (Including Price Comparison Website Data Provision) | CR | LIVE | 2.1. Start-Up Approach In Progress | 21.02% |  |  | T & SC | 2017-06-13 | Gareth Hepworth | Mark Pollard | 99 | UKLP IADBI342 | No Date | 2017-12-12 | Other | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4496 | 1. Start-Up (Progressing through change governance) | iGT Address Amendments - SAP | CR | LIVE | 2.1. Start-Up Approach In Progress | 34.83% |  |  | R & N | 2017-06-30 | Richard Cresswell | Matt Rider | 99 | UKLP IADBI358 | No Date | 2018-12-31 | ISU | TRUE | Xoserve | Daily | No Xoserve FTEs | High | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4498 | 1. Start-Up (Progressing through change governance) | ZSMP IGT Amendment prevention | CR | LIVE | 2.1. Start-Up Approach In Progress | 22.22% |  |  | R & N | 2017-07-11 | Richard Cresswell | Matt Rider | 99 | UKLP IADBI360 | No Date | 2018-12-31 | ISU | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | High | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4503 | 1. Start-Up (Progressing through change governance) | Late Meter Attached resolution | CR | LIVE | 2.1. Start-Up Approach In Progress | 49.85% |  |  | R & N | 2017-08-08 | Sarah Hadley | Matt Rider | 99 | UKLP IADBI370 | No Date | 2018-02-01 | Other | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4541 | 1. Start-Up (Progressing through change governance) | Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | CR | LIVE | 2.1. Start-Up Approach In Progress | 28.23% | Low | Low - to be reviewed in 3 months time | R & N | 2015-02-10 | Emma Smith | Matt Rider | 99 | UKLP IADBI073 | No Date | 2018-11-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4438 | 1. Start-Up (Progressing through change governance) | Contact Titles – Nullified data – functional change | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 37.24% | TBP | Low | R & N | 2016-07-19 | Tahera Choudhury | Padmini Duvvuri | 99 | UKLP IADBI233 | No Date | 2017-12-01 | ISU | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4465 | 1. Start-Up (Progressing through change governance) | Annual Production and notification of LIS-3years read | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 44.74% | TBP | Low | R & N | 2017-02-21 | Emma Smith | Padmini Duvvuri | 99 | UKLP IADBI301 | 2018-03-31 | 2018-03-01 | ISU | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
4482 | 1. Start-Up (Progressing through change governance) | SAP Meter Read Entry Screen | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 12.61% |  |  | R & N | 2017-05-30 | Emma Smith | Padmini Duvvuri | 99 | UKLP IADBI333 | No Date | 2018-03-01 | ISU | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4345 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | File format changes to the CGI file | CR | LIVE | 97. Xoserve require ChMC sponsorship | 21.02% |  |  | R & N | 2017-09-12 | Emma Lyndon | Padmini Duvvuri | 99 | UKLP IADBI379 | No Date | 2017-12-31 | AMT | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4451 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Treatment of values in the CDR | CR | LIVE | 97. Xoserve require ChMC sponsorship | 11.41% | TBP | Low | R & N | 2016-12-05 | David Addison | Padmini Duvvuri | 99 | UKLP IADBI277 | No Date | 2018-10-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE
4499 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | CDN/CDR File record Occurence Change | CR | LIVE | 97. Xoserve require ChMC sponsorship | 21.02% |  |  | R & N | 2017-07-11 | Emma Lyndon | Padmini Duvvuri | 99 | UKLP IADBI365 | No Date | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
3699 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | IA for strategic solution options for the GDE Offline database | CR | LIVE | 98. Xoserve Propose Change Not Required | 21.02% | Low | Low | R & N | 2015-05-15 |  | Padmini Duvvuri | 99 | UKLP IADBI096 | No Date | 2000-02-02 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4439 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | CR | LIVE | 98. Xoserve Propose Change Not Required | 21.02% | Low | Low | R & N | 2016-08-04 | Lorraine Cave | Padmini Duvvuri | 99 | UKLP IADBI244 | No Date | 2000-02-02 | Gemini | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4477 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Response file for (AIR) the request to bill (RTB) submission from Networks are not getting gerenbrated for the originator. | CR | LIVE | 98. Xoserve Propose Change Not Required | 25.23% |  |  | R & N | 2017-05-11 | Emma Smith | Padmini Duvvuri | 99 | UKLP IADBI326 | No Date | 2018-04-01 | ISU | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
4492 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Ability to replace Code cut off reads | CR | LIVE | 98. Xoserve Propose Change Not Required | 21.02% |  |  | R & N | 2017-06-20 | Emma Smith | Padmini Duvvuri | 99 | UKLP IADBI348 | No Date | 2018-02-01 | ISU | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE