## CMC_Summary
Totals by Budget Area (Values shown £0,000's) | [11 empty] | Current Year Value of Work Done Split By Customer Class
|  |  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) |  | Expenditure Type | Approved Budget Value 17/18 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget 17-18 | MKT_1718_01 | External | 1255.041 | 1579.5836 | 1065.2488 | 80.291 | 288.0813 | 256.0363 | 440.8402 | G | G | 0 | 246.1773 | 29.48 | 0 | 12.424
|  | Internal |  | 508.1376 | 295.1738 | 76.864 | 118.3098 | 40 | 60 | NA | G | 0 | 112.3098 | 6 | 0 | 0
|  | Total |  | 2082.8362 | 1360.4226 | 157.155 | 406.3911 | 296.0363 | 500.8402 | NA | G | 0 | 358.4871 | 35.48 | 0 | 12.424
PAC Subset DSC Change Budget 17-18 |  | External | 50 | 50 | 5 | 0 | 0 | 5 | 0 | NA | G
*This has already been included in above DSC figures,and this sub table is for visibility only |  | Internal | [7 empty] | NA | G
|  | Total |  | 50 | 5 | 0 | 0 | 5 | 0 | NA | G
Note that project expenditure & budget values shown do not include margin | [9 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [9 empty] | Red - Above target | [7 empty] | PIE VALUES
[18 empty] | Budget | 1255.041
[18 empty] | Budget Remaining | 657.6484
Details of Changes (Values shown £0,000's) | [17 empty] | Potential Additional Spend | 53.275
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year | [14 empty] | VOWR for Approved Projects | 256.0363
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining | [11 empty] | VOWD Transmission | 0
3991 Pafa Administrator Role [Usr Pys] - Internal | 0 | 2.2 | 0 | 2.2 | 0 | 0 | [11 empty] | VOWD DNs | 246.1773
4361 UK Link Future Release 2 (DSC Change Budget) - External [C] | 0 | -72.1 | 0 | 53.4 | -125.5 | 0 | [11 empty] | VOWD Shippers | 12.424
4361 UK Link Future Release 2 (DSC Change Budget) - Internal [C] | 0 | -116.2 | 0 | 20 | -78.1 | -58.1 | [11 empty] | VOWD DNs & IGTs | 29.48
xxxx.A PAC Change Budget Placeholder (subset of DSC Change Budget) - External | 0 | -45 | 0 | 0 | -45 | 0 | [10 empty] | LABEL > | VOWD iGTs | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease. | [17 empty] | Total VOWD 288.1

## CMC_Current
Values in £ 0,000s unless marked otherwise |  |  |  |  | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [6 empty] | SORT FIELD 2 |  | SORT FIELD 1 |  |  |  |  | Formulas do not delete |  | 5 | 7 | 8 | 10 | 11 | 12 | 13 | 14
Budget Pot Reference | Project Ref No | Project Title | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | Line Sequence Sort (THEN BY THIS) | PM | StageNum for Show or No Show(SORT BY THIS) | Show Approved Money? | Show Reported Money? | Auto Assess of CMC Friendly? | Progress Sort | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | External | 50 | 5 | 45 | 0 | 0 | 5 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 419 | Emma Smith / Rachel Hinsley | 0 | Show | Show | Y | N/A | xxxx.A.PACExternal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - External | SAME | 0 | -45 | 0 | 0 | -45 | 0 | DIFF | YES | -45 | TRUE |  | 0
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 420 | Emma Smith / Rachel Hinsley | 0 | Show | Show | Y | N/A | xxxx.A.PACInternal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | Total | 50 | 5 | 45 | 0 | 0 | 5 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 421 | Emma Smith / Rachel Hinsley | 0 | Show | Show | Y | N/A | xxxx.A.PACTotal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - Total | SAME | 0 | -45 | 0 | 0 | -45 | 0 | DIFF | YES | -45 | TRUE |  | 0
MKT_1718_01 | 4572 | Retail & Network Release 3 (DSC Change Budget) | EQR | External [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 449 | Padmini D | 4 | No | Show | Y | 4 | 4572External [O] | 4572 Retail & Network Release 3 (DSC Change Budget) - External [O] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4572 | Retail & Network Release 3 (DSC Change Budget) | EQR | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 450 | Padmini D | 4 | No | Show | Y | 4 | 4572Internal [O] | 4572 Retail & Network Release 3 (DSC Change Budget) - Internal [O] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4572 | Retail & Network Release 3 (DSC Change Budget) | EQR | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 451 | Padmini D | 4 | No | Show | Y | 4 | 4572Total | 4572 Retail & Network Release 3 (DSC Change Budget) - Total | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Delivery | External | 9.7 | 10.2 | -0.52 | 9 | 1.3 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.3 | 0 | 0 |  |  | 95 | Mark Pollard | 11.0 | Show | Show | Y | 11 | 3995External | 3995 TRAS Tip-off Hotline Data Provision - External | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Delivery | Internal | 3.1 | 2.3 | 0.85 | 2.3 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 96 | Mark Pollard | 11.0 | Show | Show | Y | 11 | 3995Internal | 3995 TRAS Tip-off Hotline Data Provision - Internal | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Delivery | Total | 12.8 | 12.5 | 0.33 | 11.3 | 1.2 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.2 | 0 | 0 |  |  | 97 | Mark Pollard | 11.0 | Show | Show | Y | 11 | 3995Total | 3995 TRAS Tip-off Hotline Data Provision - Total | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | External [C] | 1107 | 869.3 | 237.72 | 0 | 241.7 | 251 | 376.6 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 241.7 | 0 | 0 |  |  | 212 | Christina Francis | 11 | Show | Show | Y | 11 | 4361External [C] | 4361 UK Link Future Release 2 (DSC Change Budget) - External [C] | DIFF | 0 | -72.1 | 0 | 53.4 | -125.5 | 0 | DIFF | YES | -72.1 | TRUE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | Internal [C] | 329.7 | 179.1 | 150.65 | 0 | 79.1 | 40 | 60 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 79.1 | 0 | 0 |  |  | 213 | Christina Francis | 11 | Show | Show | Y | 11 | 4361Internal [C] | 4361 UK Link Future Release 2 (DSC Change Budget) - Internal [C] | DIFF | 0 | -116.2 | 0 | 20 | -78.1 | -58.1 | DIFF | YES | -58.1 | TRUE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | External [O] | 128.6 | 64.3 | 64.29 | 0 | 0 | 0 | 64.3 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 214 | Christina Francis | 11 | Show | Show | Y | 11 | 4361External [O] | 4361 UK Link Future Release 2 (DSC Change Budget) - External [O] | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 215 | Christina Francis | 11 | Show | Show | Y | 11 | 4361Internal [O] | 4361 UK Link Future Release 2 (DSC Change Budget) - Internal [O] | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | Total | 1565.3 | 1112.6 | 452.65 | 0 | 320.8 | 291 | 500.8 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 320.8 | 0 | 0 |  |  | 216 | Christina Francis | 11 | Show | Show | Y | 11 | 4361Total | 4361 UK Link Future Release 2 (DSC Change Budget) - Total | DIFF | 0 | -188.3 | 0 | 73.4 | -203.6 | -58.1 | DIFF | YES | -130.2 | TRUE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closedown | External | 33.3 | 11.2 | 22.04 | 9 | 2.2 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.2 | 0 | 0 |  |  | 56 | Mark Pollard | 12 | Show | Show | Y | 12 | 2949External | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closedown | Internal | 25.7 | 22.7 | 2.99 | 22.7 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 57 | Mark Pollard | 12 | Show | Show | Y | 12 | 2949Internal | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closedown | Total | 59 | 34 | 25.04 | 31.7 | 2.2 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.2 | 0 | 0 |  |  | 58 | Mark Pollard | 12 | Show | Show | Y | 12 | 2949Total | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | External | 89 | 60.3 | 28.71 | 60.3 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 140 | Mark Pollard | 12 | Show | Show | Y | 12 | 4110External | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | Internal | 31.1 | 36.4 | -5.39 | 24.2 | 12.3 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 12.3 | 0 | 0 |  |  | 141 | Mark Pollard | 12 | Show | Show | Y | 12 | 4110Internal | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | Total | 120.1 | 96.7 | 23.32 | 84.5 | 12.3 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 12.3 | 0 | 0 |  |  | 142 | Mark Pollard | 12 | Show | Show | Y | 12 | 4110Total | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Closedown | External [O] | 127 | 29.5 | 97.53 | 0 | 29.5 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 29.5 | 0 |  |  | 203 | Matt Rider | 12 | Show | Show | Y | 12 | 4340External [O] | 4340 UK Link Future Release 1.1 (DSC Change Budget) - External [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Closedown | Internal [O] | 51.1 | 6 | 45.13 | 0 | 6 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 6 | 0 |  |  | 204 | Matt Rider | 12 | Show | Show | Y | 12 | 4340Internal [O] | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Internal [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Closedown | Total | 173.3 | 35.5 | 137.77 | 0 | 35.5 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 35.5 | 0 |  |  | 205 | Matt Rider | 12 | Show | Show | Y | 12 | 4340Total | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | External [C] | 20 | 12.4 | 7.58 | 0 | 12.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 12.4 | 0 | 0 | 0 | 0 |  |  | 372 | Debi Jones | 13.1 | Show | Show | Y | 13.1 | 4510External [C] | 4510 Negative Consumption Period For Rolling AQ - External [C] | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | External [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 373 | Debi Jones | 13.1 | Show | Show | Y | 13.1 | 4510External [O] | 4510 Negative Consumption Period For Rolling AQ - External [O] | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | Internal [C] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 374 | Debi Jones | 13.1 | Show | Show | Y | 13.1 | 4510Internal [C] | 4510 Negative Consumption Period For Rolling AQ - Internal [C] | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 375 | Debi Jones | 13.1 | Show | Show | Y | 13.1 | 4510Internal [O] | 4510 Negative Consumption Period For Rolling AQ - Internal [O] | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | Total | 20 | 12.4 | 7.58 | 0 | 12.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 12.4 | 0 | 0 | 0 | 0 |  |  | 376 | Debi Jones | 13.1 | Show | Show | Y | 13.1 | 4510Total | 4510 Negative Consumption Period For Rolling AQ - Total | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closedown | External | 15 | 3 | 12 | 2 | 1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1 | 0 | 0 |  |  | 104 | Mark Pollard | 13.2 | Show | Show | Y | 13 | 3991External | 3991 Pafa Administrator Role [Usr Pys] - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closedown | Internal | 57.5 | 45.3 | 12.19 | 22.7 | 22.6 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 22.6 | 0 | 0 |  |  | 105 | Mark Pollard | 13.2 | Show | Show | Y | 13 | 3991Internal | 3991 Pafa Administrator Role [Usr Pys] - Internal | SAME | 0 | 2.2 | 0 | 2.2 | 0 | 0 | DIFF | YES | 2.2 | TRUE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closedown | Total | 72.5 | 48.3 | 24.19 | 24.7 | 23.6 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 23.6 | 0 | 0 |  |  | 106 | Mark Pollard | 13.2 | Show | Show | Y | 13 | 3991Total | 3991 Pafa Administrator Role [Usr Pys] - Total | SAME | 0 | 2.2 | 0 | 2.2 | 0 | 0 | DIFF | YES | 2.2 | TRUE |  | 0
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Approved |  | 155 | Lorraine Cave | 100 | Show | Show | Y | 100 | 4161External | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | Internal | 9.9 | 3.4 | 6.54 | 5 | -1.6 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.6 | 0 | 0 | Approved |  | 156 | Lorraine Cave | 100 | Show | Show | Y | 100 | 4161Internal | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | Total | 9.9 | 3.4 | 6.54 | 5 | -1.6 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.6 | 0 | 0 | Approved |  | 157 | Lorraine Cave | 100 | Show | Show | Y | 100 | 4161Total | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
Note on AQ2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual