## Slide 1: Release 3 Update
07th March 2018

## Slide 2: Summary
Design Planning work for Release 3 has been completed with Design commencing on 5th of March
There are a number of scope considerations to be finalised at this ChMC.
What we are seeking Scope agreement on :
  2 outstanding scope items (XRN 4431 & 4453) have recommendations due from DSG (due 05th of March) – Decision on inclusion or otherwise in R3
  A number of ‘In scope’ changes have high level ROM costs presented to this group as requested in February ChMC – decision on inclusion or otherwise into R3
Scope approval has close linkage to Design – some sunk costs may be incurred if scope decisions are deferred to later stages of Release 3.
Design plan overview is also provided for information to the Change Management Committee on Industry Design Engagement and CP issuance (refer to slides 3 & 4)
Project team continue to track green to previously committed funding milestone date of full BER submission to ChMC for approval by 11th April 2018

## Slide 3: Release 3 Change Update
XRN | Change Title | Comments
4432 | Amendment to U82 record to include the revised NTS optional tariff rate | Recommended by DSG to de-scope
4436 | Change number the of occurrences for K13 record for SSMP’s | Recommended by DSG to de-scope
4539 | New File Level Rejection | Awaiting final agreement from DSG
3667 | Provision of Formula Year AQ | Awaiting industry sponsor
4431 | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | Change solution / scope needs to be finalised with DSG
4453 | File Format Should Have Changes | Scope of file format changes needs to be finalised with DSG

## Slide 4: Release 3 High Level Delivery timelines
2018 |  |  |  |  |  |  |  |  |  |  | 
January | February | March | April | May | June | July | August | September | October | November | December
Scope
Prioritisation
Scope
Defined
Funding
Design
Build
Imp.
PIS
Scoping
Initiation
Delivery
Realisation
Baselined
Scope
Locked
Scope*
Analysis, IA & HL Design
System Test
UAT
Market Trials
CP representation & Finalisation
*Locked scope at this stage enters Design phase; BER finalisation and/or Design Phase may result in some R3 scope being reviewed by ChMC

## Slide 5: Design Plan – Change Pack Issuance
Design Plan commenced on 5th of March and planned to complete on 27/04/2018
Expected to be a tight plan due to nature/complexity of Release 3 changes e.g. Cadent Billing, RGMA validation
CP Drops planned in accordance with internal Design workshops; some flex may be experienced depending on complexity encountered during design
External facing changes being prioritised for early CP drops
Industry Design engagement sessions planned (via DSG) to ensure early visibility of R3 design is provided to representatives at DSG
Detailed Design
02/05/18
Change Pack 1
Change Pack Drop
21/03/18
Change Pack Approval
11/04/18
Change Pack Drop
04/04/18
Change Pack Approval
23/04/18
Change Pack 2
HL Design
Build
Change Pack Drop
16/04/18
Change Pack Approval
30/04/18
Change Pack 3
05/03/18
30/04/18
6 month Notification
Design Engagement Session
Design Engagement Session