## Modification Proposals Register
UNC Modification Register | [9 empty] | *Key Dates are normally an end-date, where shown red this is date sent to Ofgem
Modification Reference Suffix: A - Alternate, S - Self Governance, FT - Fast Track Self Governance, V - Varied
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Live/ Closed | Category | Workgroup | Current Status | Next Stage | Key date* | SME |  | Legal Text Provider | Text Rotation | Text Requested | Text Due | Text Delivered | Std Met | ACS
0663 |  | Extending the data comprised under the definition of Supply Point Premises Data (TPD V5.18.1) | Scottish Power | 2018-07-06 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2019-04-18 |  |  | Scotia Gas Networks | 5
0662 |  | Revenue Recovery at Combined ASEPs | National Grid NTS | 2018-06-12 | Live | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2019-04-18 |  |  | National Grid
0661 | R | Reconciliation and Imbalance Cash Out Prices | Winchester Gas | 2018-06-11 | Live | Request | Other | New Proposal | Panel Consideration | 2018-07-18 |  |  | n/a
0660 | S | Amendment to PARR permissions to allow PAC to update with UNCC approval | Centrica | 2018-06-08 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2018-09-20 |  |  | Cadent | 4
0659 | S | Improvements to the Composite Weather Variable | E.ON UK | 2018-05-29 | Live | Self-Governance | UIG | Allocated to Workgroup | Report to Panel | 2018-11-15 |  |  | Northern Gas Networks | 3
0658 |  | CDSP to identify and develop improvements to LDZ settlement processes | Total Gas and Power | 2018-05-25 | Live | Urgent | None | Panel recommended implementation | Ofgem decision | 2018-06-21 |  |  | Cadent | 2
0657 | S | Adding AQ reporting to the PARR Schedule reporting suite | Npower | 2018-04-30 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2018-08-16 |  |  | SGN | 1
0656 |  | Changes to Modification Panel arrangements | Gazprom | 2018-04-30 | Live | Modification | Governance | Allocated to Workgroup | Report to Panel | 2018-07-19 |  |  | Cadent | 8
0655 | S | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone. | Gazprom | 2018-04-06 | Closed | Self-Governance | Distribution | Withdrawn | End of process | 2018-07-16 |  |  | Wales & West Utilities | 7
0654 |  | Mandating the provision of NDM sample data | E.ON UK | 2018-03-28 | Live | Modification | UIG | Allocated to Workgroup | Report to Panel | 2018-08-16 | National Grid NTS |  | Scotia Gas Networks | 5
0653 |  | Updating the parameters for the NTS Optional Commodity Charge – Introducing the NTS Optional Capacity Charge | Centrica | 2018-03-15 | Live | Modification | NTS CMF | Allocated to Workgroup | Report to Panel | 2018-07-18 | National Grid NTS | n/a | National Grid NTS | n/a
0652 |  | Obligation to submit reads and data for winter consumption caclulation (meters in EUC bands 3 - 8) | Npower | 2018-03-07 | Live | Modification | UIG | Allocated to Workgroup | Report to Panel | 2018-08-16 | n/a | n/a | Northern Gas Networks | 3
0651 |  | Changes to the Retrospective Data Update provisions | Cadent | 2018-03-05 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2018-08-16 |  |  | n/a | n/a
0650 | FT | Minor Typographical Correction to UNC0638V Legal Text | Northern Gas Networks | 2018-02-28 | Closed | Fast Track | Distribution | Implemented | Effective date | 2018-04-10 |  |  | n/a
0649 | S | Update to UNC to formalise the Data Enquiry Service Permissions Matrix | Gazprom | 2018-02-26 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2018-09-20 |  |  | Cadent | 2
0648 | S | End dating the revised DM Read estimation process introduced by Modification 0634 | Gazprom | 2018-02-06 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2018-06-11 |  |  | Scotia Gas Networks | 1 | Panel Requested Text 15/02/18 | 2018-03-08 | 2018-02-26 | Y
0647 |  | Opening Class 1 reads to Competition | Wales & West Utilities | 2018-01-18 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2018-09-20 | SGN |  | n/a
0646 | R | Review of the Offtake Arrangements Document | Cadent | 2018-01-10 | Live | Request | Oftake | Allocated to Workgroup | Report to Panel | 2018-12-20 |  |  | n/a
0645 | S | Amending the oxygen content limit in the Network Entry Agreement at South Hook LNG | South Hook Gas Ltd | 2018-01-02 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2018-06-11 | n/a | n/a | National Grid NTS |  | Panel Requested Text 15/02/18 | 2018-03-08 | 2018-02-16 | Y
0644 |  | Improvements to nomination and reconciliation through the introduction of new EUC bands and improvements for the ALP and DAF | E.ON UK | 2017-12-15 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2018-08-16 |  |  | Cadent | 2 (6)
0643 |  | (Urgent) - Changes to settlement regime to address Unidentified Gas issues including retrospective correction | Orsted Sales | 2017-12-15 | Live | Urgent | Distribution | Panel did not recommend implementation | Ofgem decision | 2018-02-15 |  |  | Cadent | 2 (4)
0642 | A | (Urgent) - Changes to settlement regime to address Unidentified Gas issues | E.ON UK | 2017-12-22 | Live | Urgent | UIG | Panel did not recommend implementation | Ofgem decision | 2018-02-15 |  |  | Cadent | 2 | Panel Requested 18/01/18 | 2018-02-08 | 2018-02-01 | Y
0642 |  | (Urgent) - Changes to settlement regime to address Unidentified Gas issues | Corona Energy | 2017-12-15 | Live | Urgent | Distribution | Panel did not recommend implementation | Ofgem decision | 2018-02-15 |  |  | Cadent | 2
0641 | S | Amendments to Modification 0431 - Shipper/Transporter - Meter Point Portfolio Reconciliation rules and obligations | Centrica | 2017-12-08 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2018-06-11 |  |  | Cadent | 8 | Panel Requested 18/01/18 | 2018-02-08 | 2018-03-07 | N
0640 | S | Provision of access to Domestic Consumer data for Suppliers | Centrica | 2017-12-08 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2018-04-10 |  |  | Wales & West Utilities | 7 | Panel Requested Text 21/12/17 | 2018-01-17
0639 | R | Review of AUGE Framework and Arrangements | Gazprom | 2017-12-07 | Closed | Request | Individual | Request Closed | End of process | 2018-06-21 |  |  | n/a | n/a
0638 | V | Mandate monthly read submission for Smart and AMR sites from 01 April 2018 | Centrica Energy | 2017-12-21 | Closed | Modification | Distribution | Implemented | Effective date | 2018-04-01 | Northern Gas Networks | 3 | Northern Gas Networks | 3 | Panel Requested Text 21/12/17 | 2018-01-16 | 2018-01-08 | Y
0638 |  | Mandate monthly read submission for Smart and AMR sites from 01 April 2018 | Centrica Energy | 2017-10-30 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-12-21 |  |  | Northern Gas Networks | 3 | Panel Requested Text 19/10/17 | 2017-11-09 | 2017-11-07 | Y
0637 | S | Amending the permissions to release data to Meter Asset Provider organisations | E.ON UK | 2017-10-11 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-12-08 |  |  | Cadent | 6 | Panel Requested Text 19/10/17 | 2017-10-19 | 2017-10-19 | Y
0636 | D | Updating the parameters for the NTS Optional Commodity Charge while complying with the EU Tariff Code | Gazprom | 2018-04-06 | Live | Modification | NTS CMF | Panel did not recommend implementation | Ofgem decision | 2018-06-21 |  |  | National Grid NTS | n/a
0636 | C* | Updating the parameters for the NTS Optional Commodity Charge – Introducing the NTS Optional Capacity Charge (Renumbered to 0653) | Centrica | 2018-02-20 | Live | Modification | NTS CMF | Allocated to Workgroup | Report to Panel | 2018-07-18 | National Grid NTS |  | National Grid NTS | n/a
0636 | C | Updating the parameters for the NTS Optional Commodity Charge | Aughinish Alumina | 2018-03-02 | Live | Modification | NTS CMF | Panel did not recommend implementation | Ofgem decision | 2018-06-21 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 15/03/18 | 2018-04-09
0636 | B | Updating the parameters for the NTS Optional Commodity Charge | SSE | 2018-02-01 | Live | Modification | NTS CMF | Panel did not recommend implementation | Ofgem decision | 2018-06-21 | National Grid NTS |  | National Grid NTS | n/a | Panel Requested Text 15/02/18 | 2018-03-08
0636 | A | Updating the parameters for the NTS Optional Commodity Charge | Vitol S.A. Geneva | 2018-01-05 | Live | Modification | NTS CMF | Panel did not recommend implementation | Ofgem decision | 2018-06-21 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested 18/01/18 | 2018-02-08
0636 |  | Updating the parameters for the NTS Optional Commodity Charge | Vermilion Energy Ireland Ltd | 2017-10-10 | Live | Modification | NTS CMF | Panel did not recommend implementation | Ofgem decision | 2018-06-21 |  |  | National Grid NTS | n/a | Panel Requested Text 21/12/17 | 2018-01-16 | 2018-01-16 | Y
0635 | A | Reforms to incentivise accurate and timely DM reads and to remove the Transporter Class 1 read obligation | Wales & West Utilities | 2018-01-10 | Closed | Modification | Distribution | Renumbered | End of process | 2018-01-18 | SGN | 5 | SGN | 5
0635 |  | Reforms to incentivise accurate and timely DM reads for Class 2 Meter Points to improve the accuracy of Unidentified Gas allocation | first:utility | 2017-10-09 | Closed | Modification | Distribution | Withdrawn | End of process | 2018-02-20 |  |  | SGN | 5
0634 |  | (Urgent) - Revised estimation process for DM sites with D-7 zero consumption | first:utility | 2017-10-09 | Closed | Urgent | Distribution | Implemented | Effective date | 2017-11-20 |  |  | Cadent | 4 | Panel Requested Text 19/10/17 | 2017-11-09 | 2017-11-07 | Y
0633 | V | Mandate monthly read submission for Smart and AMR sites from 01 February 2018 | Corona Energy | 2017-12-21 | Closed | Modification | Distribution | Rejected | End of process | 2018-01-31 | Northern Gas Networks | 3 | Northern Gas Networks | 3 | Panel Requested Text 21/12/17 | 2018-01-16 | 2018-01-08 | Y
0633 |  | Mandate monthly read submission for Smart and AMR sites from 01 December 2017 | Corona Energy | 2017-10-09 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-12-21 |  |  | Northern Gas Networks | 3 | Panel Requested Text 19/10/17 | 2017-11-09 | 2017-11-07 | Y
0632 | S | Shipper asset details reconcilation | Corona Energy | 2017-10-09 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2018-04-10 |  |  | Cadent | 2 | Panel Requested 18/01/18 | 2018-02-08 | 2018-01-24 | Y
0631 | R | Review of NDM algorithm post-Nexus | Corona Energy | 2017-10-06 | Closed | Request | Distribution | Request Closed | End of process | 2018-04-19 |  |  | n/a | n/a
0630 | R | Review of the consequential changes required in UNC as a result of the Ofgem Switching Programme | Cadent | 2017-10-06 | Live | Request | Distribution | Allocated to Workgroup | Report to Panel | 2018-08-16 |  |  | n/a | n/a
0629 | S | Standard Design Connections: A2O connection process modification | National Grid NTS | 2017-10-04 | Live | Self-Governance | Transmission | Representations invited | Consultation end | 2018-07-12 |  |  | National Grid NTS | n/a | Text provided with mod |  | 2018-03-26 | Y
0628 | S | Standard Design Connections: PARCA process | National Grid NTS | 2017-10-04 | Live | Self-Governance | Transmission | Representations invited | Consultation end | 2018-07-12 |  |  | National Grid NTS | n/a | Text provided with mod |  | 2018-03-26 | Y
0627 | S | Removal of the absolute requirement to include a Remotely Operable Valve (ROV) Installation for all new NTS Exit Connections | National Grid NTS | 2017-09-08 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2018-01-17 |  |  | National Grid NTS | n/a | Panel Requested Text 16/11/17 | 2017-11-16 | 2017-11-16 | Y
0626 | FT | Updating UNC Section B to correct a number of references to the timing of processes associated with the start of a Gas Day | National Grid NTS | 2017-09-08 | Closed | Fast Track | Transmission | Implemented | Effective date | 2017-10-13 |  |  | National Grid NTS | n/a
0625 |  | Extension of 4 months to 10 months to transfer non-mandatory sites from Class 1 | Gazprom | 2017-08-01 | Closed | Modification | Distribution | Implemented | Effective date | 2017-11-28 |  |  | SGN | 1 | Panel Requested Text 19/10/17 | 2017-10-19 | 2017-10-19 | Y
0624 | R | Review of arrangements for Retrospective Adjustment of Meter Information, Meter Point/Supply Point and Address data | Cadent | 2017-07-07 | Closed | Request | Other | Request Closed | End of process | 2018-02-15 |  |  | n/a | n/a | No Text req'd - Request
0623 |  | Governance Arrangements for Alternatives to Self-Governance Modification Proposals | Wales & West Utilities | 2017-07-03 | Closed | Modification | Governance | Implemented | Effective date | 2018-04-20 |  |  | Wales & West Utilities | n/a | Panel Requested Text 16/11/17 | 2017-12-07 | 2017-11-30 | Y
0622 |  | Correct allocation of Shrinkage Error as identified by the AUGE | Gazprom | 2017-06-13 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-07-03 |  |  | Cadent | 8
0621 | L | Amendments to Gas Transmission Charging Regime | Shell | 2018-04-26 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | K | Amendments to Gas Transmission Charging Regime | George Grant, Gateway LNG Company Ltd | 2018-04-24 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | J | Amendments to Gas Transmission Charging Regime | RWE | 2018-03-08 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | H | Amendments to Gas Transmission Charging Regime | E.ON UK | 2018-03-02 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | G | Amendments to Gas Transmission Charging Regime | Vitol S.A. Geneva | 2018-03-02 | Closed | Modification | NTS CMF | Withdrawn | End of process | 2018-04-20 |  |  | National Grid NTS | n/a
0621 | F | Amendments to Gas Transmission Charging Regime | Interconnector | 2018-02-02 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | E | Amendments to Gas Transmission Charging Regime | Uniper Energy | 2018-02-02 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | D | Amendments to Gas Transmission Charging Regime | Wales & West Utilities | 2018-02-01 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | C | Amendments to Gas Transmission Charging Regime | Centrica | 2018-02-01 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | B | Amendments to Gas Transmission Charging Regime | SSE | 2017-12-12 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 | A | Amendments to Gas Transmission Charging Regime | Storengy | 2017-12-12 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | National Grid NTS | n/a
0621 |  | Amendments to Gas Transmission Charging Regime | National Grid NTS | 2017-06-05 | Live | Modification | NTS CMF | Representations invited | Consultation end | 2018-06-22 |  |  | n/a | n/a
0620 | S | Deferral of the UK Link Manual delivery date (further revision) | Cadent | 2017-06-02 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-07-31 |  |  | n/a | n/a | Text provided with mod | 2017-06-05 | 2017-06-05 | Y
0619 | B | Application of proportionate ratchet charges to daily read sites | Centrica Energy | 2017-10-31 | Live | Modification | Distribution | Panel did not recommend implementation | Ofgem decision | 2018-03-15 |  |  | Wales & West Utilities | 7 | Panel Requested Text 21/12/17 | 2018-01-16 | 2018-01-16 | Y
0619 | A | Protection from ratchet charges for daily read customers with an AQ of 732,00kWh and below | Scotia Gas Networks | 2017-09-08 | Live | Modification | Distribution | Panel recommended implementation | Ofgem decision | 2018-03-15 |  |  | Wales & West Utilities | 7 | Panel Requested Text 21/12/17 | 2018-01-16 | 2017-10-27 | Y
0619 |  | Application of proportionate ratchet charges to daily read sites | Gazprom | 2017-05-10 | Live | Modification | Distribution | Panel did not recommend implementation | Ofgem decision | 2018-03-15 |  |  | Wales & West Utilities | 7 | Panel Requested Text 21/09/17 | 2017-10-12 | 2017-09-20 | Y
0618 |  | Extension of Invoicing Contingency Arrangements in case of Project Nexus defect | Wales & West Utilities | 2017-05-03 | Closed | Urgent | Distribution | Implemented | Effective date | 2017-06-01 |  |  | Wales & West Utilities | n/a | Text provided with mod | 2017-05-05 | 2017-05-05 | Y
0617 | S | Revised UK Link Manual delivery date | Cadent | 2017-04-07 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-06-01 |  |  | Cadent | n/a | Text provided with mod | 2017-04-20 | 2017-04-20 | Y
0616 | S | Capacity Conversion Mechanism for Interconnection Points | National Grid NTS | 2017-04-06 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2017-11-10 | National Grid Gas Distribution | n/a | National Grid NTS | n/a | Panel Requested Text 17/08/17 | 2017-09-08 | 2017-09-07 | Y
0615 | S | Representation on DSC Committees – amendment to include mid-year appointments | E.ON UK | 2017-03-31 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-09-11 | National Grid Gas Distribution | n/a | Cadent | 6 | Panel Requested Text 15/06/2017 | 2017-07-06 | 2017-06-21 | Y
0614 |  | Introducing IHD (In-Home Display) Installed Status of Failed | EDF Energy | 2017-03-08 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-06-14 | National Grid Gas Distribution | n/a | n/a | n/a | No Text req'd - enabling Mod
0613 | S | Revised UK Link Manual CDSP Data Services Document | Cadent | 2017-03-07 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-10-13 | Scotia Gas Networks | n/a | Cadent | n/a | Panel Requested Text 20/07/17 | 2017-08-10 | 2017-08-09 | Y
0612 | R | Project Management and Assurance provisions for gas industry changes | Scotia Gas Networks | 2017-02-06 | Closed | Request | None | Withdrawn | End of process | 2017-03-21 |  |  | Scotia Gas Networks | n/a | No Text req'd - Request |  |  |  | n/a
0611 | S | Amendments to the firm capacity payable price at Interconnection Points | National Grid NTS | 2017-02-03 | Closed | Modification | Transmission | Implemented | Effective date | 2017-08-11 |  |  | National Grid NTS | n/a | Panel Requested Text 18/05/17 | 2017-06-09 | 2017-05-26 | Y | n/a
0610 | S | Project Nexus - Miscellaneous Requirements | Cadent | 2017-01-11 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-06-07 |  |  | Cadent | n/a | Panel Requested Text 16/02/17 | 2017-03-09 | 2017-02-17 | Y | n/a
0609 | A | Transitional arrangements for gas settlement and replacement of Meter Readings, retaining AQ2017 (Project Nexus transitional modification) | British Gas | 2017-02-08 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-03-10 |  |  | Cadent | n/a | Panel Requested Text 16/02/17 | 2017-03-09 | 2017-02-17 | Y
0609 |  | Transitional arrangements for gas settlement and replacement of Meter Readings (Project Nexus transitional modification) | Cadent | 2017-01-09 | Closed | Modification | Distribution | Implemented | Effective date | 2017-05-22 |  |  | Cadent | n/a | Panel Requested Text 19/01/17 | 2017-02-09 | 2017-02-17 | N | n/a
0608 | S | Implementation of 'single service provision' arrangements for iGT connected system exit points (Project Nexus transitional modification) | Cadent | 2017-01-09 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-05-15 |  |  | Cadent | n/a | Panel Requested Text 19/01/17 | 2017-02-09 | 2017-02-01 | Y | n/a
0607 |  | Amendment to Gas Quality NTS Entry Specification at the St Fergus NSMP System Entry Point | BP | 2016-12-07 | Closed | Modification | Transmission | Implemented | Effective date | 2018-02-28 |  |  | National Grid NTS | n/a | No Text req'd - enabling Mod
0606 | S | National Grid Gas plc and National Grid Gas Distribution Limited transitional invoicing arrangement post Project Nexus implementation | Cadent | 2016-12-05 | Closed | Self-Governance | Distribution | Implemented | Effective date | Nexus Imp Date |  |  | Cadent | n/a | Panel Requested Text 19/01/17 | 2017-02-09 | 2017-01-20 | Y | n/a
0605 | S | Amendments to TPD Section K - Additional Methods to Procure and Dispose of Operating Margins Gas | National Grid NTS | 2016-12-02 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2017-08-11 |  |  | National Grid NTS | n/a | Panel Requested Text 19/01/17 | 2017-02-09 | 2017-01-19 | Y | n/a
0604 | S | Central Data Services Provider – Arrangements following implementation of Project Nexus | Cadent | 2016-11-30 | Closed | Self-Governance | Other | Implemented | Effective date | Nexus Imp Date |  |  | Cadent | n/a | Panel Requested Text 16/02/17 | 2017-03-09 | 2017-02-16 | Y | n/a
0603 | S | Removal of liability for members of Performance Assurance Committee | Wales & West Utilities | 2016-11-08 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-01-11 |  |  | Wales & West Utilities | n/a | Text provided with mod | 2016-12-15 | 2016-12-15 | Y | n/a
0602 | A | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation, maintaining a minimum of two Supply Point Business Days (Project Nexus transitional modification) | RWE Npower | 2016-12-23 | Closed | Modification | Distribution | Implemented | Effective date | 2017-02-20 |  |  | Cadent | n/a | Panel Requested Text 19/01/17 | 2017-01-19 | 2017-01-19 | Y | n/a
0602 |  | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation (Project Nexus transitional modification) | Cadent | 2016-11-07 | Closed | Modification | Distribution | Rejected | End of process | 2017-02-17 |  |  | Cadent | n/a | Panel Requested Text 15/12/16 | 2017-01-10 | 2017-01-12 | N | n/a
0601 | FT | Revision of National Grid Gas plc’s Individual Network Code to reflect the correct company name | National Grid NTS | 2016-11-01 | Closed | Fast Track | Transmission | Implemented | Effective date | 2016-12-09 | National Grid NTS | n/a | National Grid NTS | n/a | FT - text provided with mod | 2016-11-17 | 2016-11-17 | Y | n/a
0600 | S | Amend obligation for the acceptance of EPDQD revisions made after D+5 | National Grid NTS | 2016-10-10 | Closed | Modification | Transmission | Implemented | Effective date | 2017-04-07 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 20/10/16 | 2016-11-10 | 2016-11-10 | Y | n/a
0599 |  | Amendments to Capacity Allocations Mechanisms (Interruptible) to comply with EU Capacity Regulations | National Grid NTS | 2016-10-10 | Closed | Modification | European | Withdrawn | End of process | 2016-11-16 | National Grid NTS | n/a | National Grid NTS | n/a | Mod withdrawn |  |  |  | n/a
0598 | S | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | National Grid NTS | 2016-10-10 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2017-04-06 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 15/12/16 | 2017-01-10 | 2016-12-16 | Y | n/a
0597 |  | Rules for the release of incremental capacity at Interconnection Points | National Grid NTS | 2016-10-10 | Closed | Modification | Transmission | Implemented | Effective date | 2017-04-06 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 15/12/16 | 2017-01-10 | 2016-12-23 | Y | n/a
0596 |  | Implementing CGR3 decisions on Significant Code Reviews and self-governance | Wales & West Utilities | 2016-10-07 | Closed | Modification | Governance | Implemented | Effective date | 2017-02-17 | National Grid NTS | n/a | Wales & West Utilities | n/a | Panel Requested Text 20/10/16 | 2016-11-10 | 2016-10-20 | Y | n/a
0595 | S | Amendment to the Arrangements between National Grid NTS and GNI at the Moffat IP to Provide for Interruption of Virtual Reverse Flow | National Grid NTS | 2016-09-02 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2016-12-09 | National Grid NTS | n/a | n/a | n/a | No Text req'd - enabling Mod |  |  |  | n/a
0594 | R | Meter Reading Submission for Advanced & Smart Metering | Gazprom | 2016-09-02 | Closed | Request | Distribution | Request Closed | End of process | 2017-12-21 | National Grid NTS | n/a | n/a | n/a | No Text req'd - Request |  |  |  | n/a
0593 | V | Provision of access to Domestic Consumer data for Price Comparison Websites and Third Party Intermediaries | Northern Gas Networks | 2017-07-20 | Closed | Modification | Distribution | Implemented | Effective date | 2017-12-15 | National Grid NTS | n/a | Northern Gas Networks | n/a | Panel Requested Text 15/09/2016 | 2016-10-06 | 2016-10-07 | N | n/a
0593 |  | Provision of access to Domestic Consumer data for Price Comparison Websites and Third Party Intermediaries | Northern Gas Networks | 2016-08-08 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-07-20 | National Grid NTS | n/a | Northern Gas Networks | n/a | Panel Requested Text 15/09/2016 | 2016-10-06 | 2016-10-07 | N | n/a
0592 | S | Separation of National Grid Transmission and Distribution owned networks - Transitional invoicing arrangements | Cadent | 2016-07-13 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2016-09-30 | National Grid NTS | n/a | Cadent | n/a | Panel Requested Text 21/07/2016 | 2016-08-11 | 2016-08-05 | Y | n/a
0591 | S | DSR - Removal of 7 day rolling profile functionality | National Grid NTS | 2016-07-13 | Closed | Self-Governance | Demand Side Response | Implemented | Effective date | 2016-09-12 | National Grid NTS | n/a | National Grid NTS | n/a | Text provided with mod | 2016-07-21 | 2016-07-21 | Y | n/a
0590 | R | Review the options to remove the use of Fax machines within the UNC | E.ON UK | 2016-06-27 | Closed | Request | Distribution | Withdrawn | End of process | 2016-08-16 | National Grid NTS | n/a | n/a | n/a | No Text req'd - Request
0589 | S | Inclusion of CSEP Supply Meter Points within NDM Sampling Arrangements | E.ON UK | 2016-06-27 | Closed | Self-Governance | Distribution | Implemented | Effective date | Nexus Imp Date | National Grid NTS | n/a | Scotia Gas Networks | 5 | Panel Requested Text 21/07/2016 | 2016-08-11 | 2016-08-08 | Y | n/a
0588 | R | Review UNC arrangements relating to the connection to and operation of gas fired generation on DN networks | Wales & West Utilities | 2016-06-06 | Closed | Request | Transmission | Withdrawn | End of process | 2016-08-05 | National Grid NTS | n/a | n/a | n/a | No Text req'd - Request
0587 |  | Seasonal Energy Balancing Credit Cover | Opus Energy | 2016-06-06 | Closed | Modification | Transmission | Implemented | Effective date | 2017-05-01 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 18/08/2016 | 2016-09-09 | 2016-09-09 | Y | Yes
0586 | FT | Resolution of minor legal text drafting conflicts arising from UNC Modification 0432 | Cadent | 2016-06-06 | Closed | Fast Track | Distribution | Implemented | Effective date | Nexus Imp Date | National Grid NTS | n/a | Cadent | n/a | Text provided with mod | 2016-06-16 | 2016-06-16 | Y | n/a
0585 |  | Separation of NTS and National Grid owned networks – Calculation of Code Credit Limit and Value at Risk | Cadent | 2016-06-06 | Closed | Modification | Distribution | Withdrawn | End of process | 2016-08-03 | National Grid NTS | n/a | Cadent | n/a | Panel Requested Text 16/06/2016 | 2016-07-07 | 2016-06-30 | Y | n/a
0584 | S | Energy Theft Tip-Off Service (ETTOS) – Release of Supplier identity | Northern Gas Networks | 2016-06-01 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2016-08-12 | National Grid NTS | n/a | Northern Gas Networks | n/a | Text provided with mod | 2016-06-16 | 2016-06-16 | Y | n/a
0583 | S | Requiring an Opening Meter Reading at same User Confirmation | Cadent | 2016-05-10 | Closed | Self-Governance | Distribution | Implemented | Effective date | Nexus Imp Date | National Grid NTS | n/a | Cadent | n/a | Panel Requested Text 19/05/2016 | 2016-06-10 | 2016-06-10 | Y | n/a
0582 | S | Amendments to reflect separation in legal ownership of NTS and National Grid owned LDZs to facilitate the sale of National Grid's Gas Distribution Business | Cadent | 2016-05-09 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2016-09-12 | National Grid NTS | n/a | Cadent | n/a | Panel Requested Text 19/05/2016 | 2016-05-19 | 2016-05-19 | Y | n/a
0581 | S | Amending the Oxygen content limit specified in the Network Entry Agreement at Grain LNG | British Gas Trading | 2016-04-08 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2016-08-12 | National Grid NTS | n/a | n/a | n/a | No Text req'd - enabling Mod |  |  |  | n/a
0580 | VS | Implementation of Non Effective Days to enable Annual AQ Review (independent of Nexus transition) | Scotia Gas Networks | 2016-07-21 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2016-08-12 | National Grid NTS | n/a | Scotia Gas Networks | n/a | Text provided with mod | 2016-05-19 | 2016-05-19 | Y
0580 | S | Implementation of Non Effective Days to enable Annual AQ Review (independent of Nexus transition) | Scotia Gas Networks | 2016-04-07 | Closed | Self-Governance | Distribution | Withdrawn | End of process | 2016-07-21 | National Grid NTS | n/a | Scotia Gas Networks | n/a | Text provided with mod | 2016-05-19 | 2016-05-19 | Y
0579 | FT | Updating code to reflect the correct ‘Designated Person’ | British Gas | 2016-04-04 | Closed | Fast Track | Governance | Implemented | Effective date | 2016-05-16 | National Grid NTS | n/a | Cadent | 4 | FT - Text provided with mod | 2016-04-21 | 2016-04-21 | Y | n/a
0578 |  | Implementation of Retrospective Invoice Adjustment arrangements (Project Nexus transitional modification) | Cadent | 2016-03-09 | Closed | Modification | Nexus | Implemented | Effective date | 2016-08-18 | National Grid NTS | n/a | Cadent | n/a | Panel Requested Text 21/04/2016 | 2016-05-13 | 2016-05-13 | Y
0577 | S | Aligning UNC to the indirect clearing model operated by ICE Endex | National Grid NTS | 2016-03-09 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2016-05-16 | National Grid NTS | n/a | National Grid NTS | n/a | Text provided with mod | 2016-03-17 | 2016-03-17 | Y
0576 |  | Generation of an estimated Meter Reading at the Code Cut Off Date in the absence of an actual Meter Reading | Cadent | 2016-03-09 | Closed | Modification | Nexus | Implemented | Effective date | Nexus Imp Date | National Grid NTS | n/a | Cadent | n/a | Panel Requested Text 21/04/2016 | 2016-05-13 | 2016-05-13 | Y
0575 | R | Consider the Performance Assurance Reporting Requirements for Transporters | Scottish Power | 2016-03-03 | Closed | Request | Offtake | Request Closed | End of process | 2016-08-18 |  |  | n/a | n/a | No Text req'd - Request
0574 |  | Creating the permission to release supply point data to the Theft Risk Assessment Service (TRAS) | RWE Npower | 2016-02-08 | Closed | Modification | Distribution | Implemented | Effective date | 2016-12-09 | National Grid NTS | n/a | Northern Gas Networks | 3 | Panel Requested Text 16/06/2016 | 2016-07-07 | 2016-07-13 | N
0573 |  | Project Nexus – deferral of implementation of elements of Retrospective Adjustment arrangements | Cadent | 2016-02-08 | Closed | Urgent | Distribution | Implemented | Effective date | Nexus Imp Date | National Grid NTS | n/a | Cadent | n/a | Urgent - text provided with mod
0572 |  | Amendment to the definition of AUG Year within UNC TPD Section E | British Gas | 2016-01-08 | Closed | Modification | Distribution | Implemented | Effective date | Nexus Imp Date | National Grid Distribution | 6 | Scotia Gas Networks | 1 | Panel Requested Text 18/02/16 | 2016-03-10 | 2016-03-04 | Y
0571 | A | Application of Ratchet Charges to Class 1 Supply Points and Class 2 with an AQ above 73,200kWhs | E.ON UK | 2016-05-05 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-05-11 | National Grid Distribution | 6 | Cadent | n/a | Panel Requested Text 16/06/2016 | 2016-07-07 | 2016-06-22 | Y
0571 |  | Application of Ratchets Charges to Class 1 Supply Points Only | Gazprom | 2015-12-24 | Closed | Modification | Distribution | Withdrawn | End of process | 2017-05-10 | National Grid Distribution | 6 | Cadent | 8 | Panel Requested Text 16/06/2016 | 2016-07-07 | 2016-06-22 | Y
0570 |  | Obligation on Shippers to provide at least one valid meter reading per meter point into settlement once per annum | Scottish Power | 2015-12-03 | Closed | Modification | Distribution | Implemented | Effective date | tbc | National Grid NTS | n/a | Cadent | 6 | Panel Requested Text 15/06/2017 | 2017-07-06 | 2017-05-23 | Y
0569 | S | Removal of the minimum security requirement from the Energy Balancing Credit Rules | Locus Energy | 2015-12-03 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2016-03-11 |  |  | National Grid NTS | n/a | Panel Requested Text 21/01/16 | 2016-02-11 | 2016-01-21 | Y | n/a
0568 |  | Security Requirements and Invoice Payment Settlement Cycle for the Trading System Clearer | ICE Endex | 2015-11-06 | Closed | Modification | Transmission | Implemented | Effective date | 2016-08-01 |  |  | National Grid NTS | n/a | Panel Requested Text 21/01/16 | 2016-02-11 | 2016-01-29 | Y
0567 | S | Amendment to reference temperature conditions within the National Grid NTS – IUK Interconnection Agreement | National Grid NTS | 2015-11-06 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2016-02-12 |  |  | n/a | n/a | No Text req'd - enabling Mod
0566 | S | UNC modification stakeholder engagement and Guidelines | Scotia Gas Networks | 2015-11-06 | Closed | Self-Governance | Governance | Implemented | Effective date | 2016-02-12 |  |  | Scotia Gas Networks | n/a | Panel Requested Text 17/12/15 | 2016-01-12 | 2015-12-17 | Y
0565 | B | Central Data Service Provider: General framework and obligations | Scotia Gas Networks | 2016-10-26 | Closed | Modification | Other | Rejected | End of process | 2017-01-19 |  |  | National Grid Distribution | n/a | Pane Requested Text 28/10/16 | 2016-11-18 | 2016-11-02 | Y | n/a
0565 | A | Central Data Service Provider: General framework and obligations | E.ON UK | 2016-10-10 | Closed | Modification | Other | Implemented | Effective date | 2017-04-01 |  |  | National Grid Distribution | n/a | Panel Requested Text 20/10/16 | 2016-11-10 | 2016-11-02 | Y | n/a
0565 |  | Central Data Service Provider: General framework and obligations | National Grid Distribution | 2015-11-05 | Closed | Modification | Other | Rejected | End of process | 2017-01-19 |  |  | National Grid Distribution | n/a | Panel Requested Text 20/10/16 | 2016-11-10 | 2016-11-02 | Y | n/a
0564 | R | Review of Annual Read Meter Reading requirements | National Grid Distribution | 2015-10-14 | Closed | Request | Distribution | Request Closed | End of process | 2016-06-16 |  |  | n/a | n/a | No Text req'd - Request
0563 | S | Moving the NTS Optional Commodity Charge Formula into the UNC | SSE | 2015-10-12 | Closed | Self-Governance | NTS CMF | Implemented | Effective date | 2016-02-12 |  |  | National Grid NTS | n/a | Panel Requested Text 17/12/15 | 2016-01-12 | 2015-12-17 | Y
0562 | FT | Amendment to the Effective Date of Modification 0519 ‘Harmonisation of Reference Conditions at Interconnection Points’ | National Grid NTS | 2015-10-02 | Closed | Fast Track | None | Implemented | Effective date | 2015-11-06 |  |  | National Grid NTS | n/a | FT - text provided with mod | 2015-10-15 | 2015-10-15 | Y | n/a
0561 | S | Amendment to the oxygen limit within the BBL / NTS Interconnection Agreement | National Grid NTS | 2015-10-02 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2015-12-11 | National Grid NTS | n/a | n/a | n/a | No Text req'd - enabling Mod |  |  |  | n/a
0560 |  | Addressing under-allocation of flows from BBL arising from misalignment of reference conditions | GasTerra | 2015-09-30 | Closed | Urgent | Transmission | Implemented | Effective date | 2015-12-08 |  |  | National Grid NTS | n/a | Urgent Mod | 2015-11-10 | 2015-11-09 | Y | n/a
0559 | FT | Correction of a minor legal text reference related to Information Provision changes | National Grid NTS | 2015-09-28 | Closed | Fast Track | None | Implemented | Effective date | 2015-11-06 |  |  | National Grid NTS | n/a | FT - text provided with mod | 2015-10-15 | 2015-10-15 | Y | n/a
0558 |  | Standardisation of Industry Payment Terms | RWE Npower | 2015-09-04 | Closed | Modification | Distribution | Withdrawn | End of process | 2015-11-05 |  |  | Scotia Gas Networks | 5 | Mod withdrawn |  |  |  | n/a
0557 |  | Notice Period for Changes to Transportation Charges resulting from Uncertain costs allowed expenditure - financial adjustments | E.ON UK | 2015-09-04 | Closed | Modification | DN CMF | Withdrawn | End of process | 2015-11-13 |  |  | National Grid Distribution | 4 | Mod withdrawn |  |  |  | n/a
0556 | FT | Amendment to the Legal Text provided for “Modification 0548 Project Nexus – deferral of Implementation Date” | National Grid Distribution | 2015-09-04 | Closed | Fast Track | None | Implemented | Effective date | 2015-10-09 |  |  | National Grid Distribution | n/a | FT - text provided with mod | 2015-09-17 | 2015-09-17 | Y | n/a
0555 | R | Review of the Market Operator (OCM) Provisions | National Grid NTS | 2015-09-04 | Closed | Request | Market Operator | Request Closed | End of process | 2016-03-17 |  |  | n/a | n/a | No Text req'd - Request |  |  |  | n/a
0554 | FT | Gender-neutral terms within the UNC | Scotia Gas Networks | 2015-08-26 | Closed | Fast Track | None | Implemented | Effective date | 2015-10-09 |  |  | Scotia Gas Networks | n/a | FT - text provided with mod | 2015-09-17 | 2015-09-17 | Y | n/a
0553 | S | Removal of National Grid LNG Storage UNC TPD Section Z obligations and associated cross-references | National Grid LNG Storage | 2015-08-07 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2015-12-11 |  |  | National Grid NTS | n/a | Panel Requested Text 17/09/2015 | 2015-10-08 | 2015-09-30 | Y | n/a
0552 | S | UNC Section Y Housekeeping | National Grid NTS | 2015-08-07 | Closed | Self-Governance | None | Implemented | Effective date | 2015-10-09 |  |  | National Grid NTS | n/a | Panel Requested Text 20/08/2015 | 2015-09-10 | 2015-08-07 | Y | n/a
0551 |  | Protecting consumers who are disaggregated under Modification 0428 from Ratchet charges for Winter 2015 | Gazprom | 2015-08-06 | Closed | Modification | Distribution | Rejected | End of process | 2016-03-21 |  |  | Northern Gas Networks | 3 | Panel Requested Text 17/09/2015 | 2015-10-08 | 2015-10-05 | Y | n/a
0550 |  | Project Nexus: Incentivising Central Project Delivery | RWE Npower | 2015-08-04 | Closed | Modification | Governance | Rejected | End of process | 2016-05-27 |  |  | National Grid Distribution | 2 | Panel Requested Text 21/01/16 | 2016-02-11 | 2016-01-29 | Y | n/a
0549 |  | Improving Arrangements for Managing Major Industry Changes | Gazprom | 2015-07-14 | Closed | Modification | Governance | Withdrawn | End of process | 22-0ct-15 |  |  | Scotia Gas Networks | 1 | Mod withdrawn |  |  |  | n/a
0548 |  | Project Nexus – deferral of Implementation Date | National Grid Distribution | 2015-07-14 | Closed | Urgent | Nexus | Implemented | Effective date | 2015-08-14 |  |  | National Grid Distribution | n/a | Urgent - text provided with mod |  |  |  | n/a
0547 | S | Corrections to the EID arising from implementation of Modifications 0493/0500 | National Grid NTS | 2015-07-03 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2015-10-09 |  |  | National Grid NTS | n/a | Panel Requested Text 16/07/2015 | 2015-08-06 | 2015-08-06 | Y | n/a
0546 | S | Reduction of the Minimum Eligible Quantity (100,000kWh) for European IP capacity | National Grid NTS | 2015-07-03 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2015-10-09 |  |  | National Grid NTS | n/a | Panel Requested Text 16/07/2015 | 2015-08-06 | 2015-08-05 | Y | n/a
0545 | S | Changes to GDN MOD186 Publication dates | Northern Gas Networks | 2015-07-02 | Closed | Self-Governance | DN CMF | Implemented | Effective date | 2015-11-06 |  |  | Northern Gas Networks | n/a | Panel Requested Text 20/08/2015 | 2015-09-10 | 2015-08-18 | Y | n/a
0544 |  | Amendment to charging under Modification 0428 - Single Meter Supply Points | Gazprom | 2015-06-30 | Closed | Urgent | Distribution | Withdrawn | End of process | 2015-07-02 |  |  | National Grid Distribution | 8 | Mod withdrawn |  |  |  | n/a | NOTE: Rotation 6 & 7 missed due to previous text allocations
0543 |  | Ex-post removal of uncontrollable UNC charges at ASEPs which include sub-terminals operating on a 06.00 to 06.00 Gas Day | Gazprom | 2015-06-23 | Closed | Modification | Transmission | Renumbered | End of process | 2015-07-16 |  |  | National Grid NTS | n/a | Mod withdrawn |  |  |  | n/a
0542 |  | Ex-ante removal of uncontrollable UNC charges at ASEPs which include sub-terminals operating on a 06.00 to 06.00 Gas Day | BP | 2015-06-23 | Closed | Modification | Transmission | Renumbered | End of process | 2015-07-16 |  |  | National Grid NTS | n/a | Mod withdrawn |  |  |  | n/a
0541 | B | Ex-post removal of uncontrollable UNC charges at ASEPs which include sub-terminals operating on a 06.00 to 06.00 Gas Day | Gazprom | 2015-07-16 | Closed | Modification | Transmission | Rejected | End of process | 2016-05-26 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 21/01/16 | 2016-02-11 | 2016-02-11 | Y | n/a
0541 | A | Ex-ante removal of uncontrollable UNC charges at ASEPs which include sub-terminals operating on a 06.00 to 06.00 Gas Day | BP | 2015-07-16 | Closed | Modification | Transmission | Rejected | End of process | 2016-05-26 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 21/01/16 | 2016-02-11 | 2016-02-11 | Y | n/a
0541 |  | Removal of uncontrollable UNC charges at ASEPs which include sub-terminals operating on a 06.00 to 06.00 Gas Day via an ex-ante, quantity adjustment | EDF Trading | 2015-06-23 | Closed | Modification | Transmission | Withdrawn | End of process | 2015-12-15 |  |  | National Grid NTS | n/a | Mod withdrawn |  |  |  | n/a
0540 | FT | Amendment to TPD Section G2.15 | Scotia Gas Networks | 2015-06-10 | Closed | Fast Track | Distribution | Implemented | Effective date | 2015-08-07 |  |  | Scotia Gas Networks | n/a | FT - text provided with mod | 2015-07-16 | 2015-07-16 | Y | n/a
0539 |  | Removal of NTS Exit Commodity Charges for Distributed Gas | Barrow Shipping Ltd | 2015-06-05 | Closed | Modification | DN CMF | Rejected | End of process | 2015-11-19 |  |  | Scotia Gas Networks | 5 | Deemed Text Request 17/09/15 | 2015-09-17 | 2015-09-17 | Y | n/a
0538 | FT | Correcting legal text errors – gas Security of Supply Significant Code Review | National Grid NTS | 2015-06-04 | Closed | Fast Track | Transmission | Implemented | Effective date | 2015-10-01 |  |  | National Grid NTS | n/a | FT - text provided with mod | 2015-06-18 | 2015-06-18 | Y | n/a
0537 |  | Change of Project Nexus Implementation Date to 1st April 2016 | Total Gas and Power | 2015-04-27 | Closed | Modification | Nexus | Withdrawn | End of process | 2015-06-18 |  |  | National Grid Distribution | n/a | Mod withdrawn |  |  |  | n/a
0536 |  | Project Nexus – deferral of implementation of elements of Retrospective Adjustment arrangements | National Grid Distribution | 2015-04-24 | Closed | Modification | Nexus | Withdrawn | End of process | 2015-07-24 |  |  | National Grid Distribution | n/a | Mod withdrawn |  |  |  | n/a
0535 |  | Implementation of Non-Effective Days to enable Annual AQ Review (independent of Nexus transition) | Scotia Gas Networks | 2015-03-06 | Closed | Modification | Nexus | Implemented | Effective date | 2015-07-24 |  |  | Scotia Gas Networks | n/a | Panel Requested Text 16/04/2015 | 2015-05-07 | 2015-05-07 | Y | TBC
0534 |  | Maintaining the Efficacy of the NTS Optional Commodity ('shorthaul') Tariff at Bacton Entry Points | Gazprom | 2015-03-06 | Closed | Modification | Transmission | Implemented | Effective date | 2016-08-01 |  |  | National Grid NTS | n/a | Panel Requested Text 16/07/2015 | 2015-08-06 | 2015-07-23 | Y | TBC
0533 | S | Corrections to Network Entry Provisions in the National Grid NTS-BBL Interconnection Agreement | National Grid NTS | 2015-03-06 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2015-06-15 |  |  | National Grid NTS | n/a | No Text req'd - enabling Mod |  |  |  | n/a
0532 |  | Implementation of Non-Effective Days (Project Nexus transitional modification) | National Grid Distribution | 2015-03-06 | Closed | Modification | Nexus | Rejected | End of process | 2016-06-30 |  |  | National Grid Distribution | n/a | Panel Requested Text 19/11/2015 | 2015-12-10 | 2015-12-03 | Y | n/a
0531 |  | Provision of an Industry User Test System | SSE | 2015-02-09 | Closed | Modification | Nexus | Rejected | End of process | 2016-10-20 |  |  | National Grid Distribution | 4 | Panel Requested Text 21/04/2016 | 2016-05-13 | 2016-05-06 | Y | n/a
0530 |  | Use of Supply Point Register data for Project Nexus 'Market Trials' Testing Phase | National Grid Distribution | 2015-02-06 | Closed | Modification | Nexus | Withdrawn | End of process | 2015-02-18 |  |  | National Grid Distribution | n/a | Mod withdrawn |  |  |  | n/a
0529 |  | Implementation of Retrospective Adjustment arrangements (Project Nexus transitional modification) | National Grid Distribution | 2015-02-06 | Closed | Modification | Nexus | Rejected | End of process | 2016-02-10 |  |  | National Grid Distribution | n/a | Panel Requested Text 21/05/15 | 2015-06-11 | 2015-05-21 | Y | n/a
0528 | V | Implementation of Supply Point Administration, gas allocation and settlement arrangements (Project Nexus transitional modification) | National Grid Distribution | 2015-08-20 | Closed | Modification | Nexus | Implemented | Effective date | 2016-02-11 |  |  | National Grid Distribution | n/a | Panel Requested Text 16/04/2015 | 2015-05-07 | 2015-04-16 | Y | n/a
0528 |  | Implementation of Supply Point Administration, gas allocation and settlement arrangements (Project Nexus transitional modification) | National Grid Distribution | 2015-02-06 | Closed | Modification | Nexus | Withdrawn | End of process | 2015-08-20 |  |  | National Grid Distribution | n/a | Panel Requested Text 16/04/2015 | 2015-05-07 | 2015-04-16 | Y | n/a
0527 |  | Implementation of Annual Quantity arrangements (Project Nexus transitional modification) | National Grid Distribution | 2015-02-06 | Closed | Modification | Nexus | Implemented | Effective date | 2016-02-11 |  |  | National Grid Distribution | n/a | Panel Requested Text 16/04/2015 | 2015-05-07 | 2015-04-16 | Y | n/a
0526 | S | Identification of Supply Meter Point pressure tier | E.ON UK | 2015-02-06 | Closed | Self-Governance | Distribution | Rejected | End of process | 2016-06-16 |  |  | Northern Gas Networks | 3 | Panel Requested Text 21/04/2016 | 2016-05-13 | 2016-05-13 | Y | n/a
0525 |  | Enabling EU Compliant Interconnection Agreements | National Grid NTS | 2015-02-04 | Closed | Modification | European | Implemented | Effective date | 2015-10-01 |  |  | National Grid NTS | n/a | Panel Requested Text 21/05/15 | 12/06/15 | 2015-06-04 | Y | n/a
0524 |  | Enabling the Use of Pre Nexus Meter Reads for the purposes of Post Nexus Rolling AQ Calculation | Gazprom | 2015-01-23 | Closed | Modification | Nexus | Withdrawn | End of process | 2015-02-11 |  |  | National Grid Distribution | n/a | Mod withdrawn |  |  |  | n/a
0523 | S | Supply Point Registration – Facilitation of ‘faster switching’ for Shared Supply Meter Points | National Grid Distribution | 2015-01-07 | Closed | Self-Governance | Distribution | Implemented | Effective date | Nexus Imp Date |  |  | National Grid Distribution | n/a | Panel Requested Text 21/05/15 | 2015-06-12 | 2015-05-21 | Y | n/a
0522 | S | Governance of the use of email as a valid UNC communication | E.ON UK | 2014-08-08 | Closed | Self-Governance | Distribution | Rejected | End of process | 2015-12-17 |  |  | Northern Gas Networks | n/a | Panel Requested Text 19/11/15 | 2015-12-10 | 2015-11-18 | Y | n/a
0521 |  | Revision of User Admission Criteria to include Transporter verification of its ability to transact with the Applicant User | National Grid NTS | 2014-12-10 | Closed | Modification | NTS CMF | Rejected | End of process | 2015-05-11 |  |  | National Grid NTS | n/a | Panel requested text 18/12/14 | 2015-01-14 | 2014-12-18 | Y | n/a
0520 | A | Performance Assurance Reporting | E.ON UK | 2015-10-02 | Closed | Modification | Distribution | Implemented | Effective date | 2017-01-01 |  |  | Wales & West Utilities | n/a | Panel Requested Text 19/11/2015 | 2015-12-10 | 2015-12-08 | Y | TBC
0520 |  | Performance Assurance Reporting | British Gas | 2014-11-25 | Closed | Modification | Distribution | Rejected | End of process | 2016-04-25 |  |  | Wales & West Utilities | n/a | Panel requested Text 20/08/15 | 2015-09-10 | 2015-09-04 | Y | TBC
0519 |  | Harmonisation of Reference Conditions at Interconnection Points | National Grid NTS | 2014-11-07 | Closed | Modification | European | Implemented | Effective date | 2015-10-01 |  |  | National Grid NTS | n/a | Panel Requested Text 15/01/15 | 2015-02-05 | 2015-01-16 | Y | n/a
0518 | S | Shipper Verification of meter and address details following system meter removals. | Scotia Gas Networks | 2014-10-31 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2017-09-01 |  |  | Scotia Gas Networks | n/a | Panel Requested Text 21/05/15 | 2015-06-12 | 2015-05-21 | Y | n/a
0517 | B | Review of the Supply Matching Merit Order in Setting Capacity Charges, Rolling Average to Reduce Volatility in Annual Charges | SSE | 2014-12-16 | Closed | Modification | NTS CMF | Rejected | End of process | 2015-09-25 |  |  | National Grid NTS | n/a | Deemed Text Request 18/06/15 | 2015-07-09 | 2015-06-18 | Y | n/a
0517 | A | Review of the Supply Matching Merit Order in Setting Capacity Charges and Timing of Resultant Price Changes | Wales & West Utilities | 2014-12-11 | Closed | Modification | NTS CMF | Rejected | End of process | 2015-09-25 |  |  | National Grid NTS | n/a | Panel requested text 18/12/14 | 2015-01-14 | 2015-01-06 | Y | n/a
0517 |  | Review of the Supply Matching Merit Order in Setting Capacity Charges | National Grid NTS | 2014-10-03 | Closed | Modification | NTS CMF | Rejected | End of process | 2015-09-25 |  |  | National Grid NTS | n/a | Panel requested text 18/12/14 | 2015-01-14 | 2015-01-06 | Y | n/a
0516 | S | Information provision by large Customers to aid understanding of site characteristics | Wingas | 2014-09-16 | Closed | Self-Governance | Distribution | Implemented | Effective date | Nexus Imp Date |  |  | Scotia Gas Networks | n/a | Panel requested text 19/02/15 | 2015-03-12 | 2015-02-19 | Y | n/a
0515 | S | Resolution timescales for SRVs and USRVs following Project Nexus Implementation | National Grid Distribution | 2014-08-27 | Closed | Self-Governance | Nexus | Implemented | Effective date | 2015-03-13 |  |  | National Grid Distribution | n/a | Panel Requested Text 20/11/14 | 2014-12-11 | 2014-12-04 | Y | n/a
0514 |  | Extending the Daily Metered ‘voluntary’ service to Project Nexus Implementation Date plus six months | National Grid Distribution | 2014-08-27 | Closed | Modification | Nexus | Implemented | Effective date | Nexus Imp Date |  |  | National Grid Distribution | n/a | Panel Requested Text 20/11/14 | 2014-11-20 | 2014-11-20 | Y | n/a
0513 |  | UK Link Programme (Project Nexus) - independent project assurance for Users | National Grid Distribution | 2014-08-20 | Closed | Urgent | Nexus | Implemented | Effective date | 2015-10-27 |  |  | National Grid Distribution | n/a | None Required |  |  |  | Yes
0512 | S | Amendment to Section M to be consistent with Faster Switching proposals | British Gas | 2014-08-20 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2015-03-13 |  |  | National Grid Distribution | 2 | Panel requested text 18/12/14 | 2015-01-14 | 2014-12-18 | Y | n/a
0511 |  | Introduction of an Enduring Solution for managing Advanced Meters in central systems post Nexus | Gazprom | 2014-08-18 | Closed | Modification | Nexus | Withdrawn | End of process | 2015-01-23 |  |  | Northern Gas Networks | n/a | Mod withdrawn |  |  |  | n/a
0510 | V | Reform of Gas Allocation Regime at GB Interconnection Points | National Grid NTS | 2015-07-16 | Closed | Modification | European | Implemented | Effective date | 2015-10-01 | National Grid NTS | n/a | National Grid NTS | n/a | Panel Requested Text 16/07/15 | 2015-08-06 | 2015-07-16 | Y | n/a
0510 |  | Reform of Gas Allocation Regime at GB Interconnection Points | National Grid NTS | 2014-08-08 | Closed | Modification | European | Withdrawn | End of process | 2015-07-16 |  |  | National Grid NTS | n/a | Panel Requested Text 15/01/15 | 2015-02-05 | 2015-01-19 | Y | n/a
0509 |  | Permission to release Protected Information to an Authorised Third Party for Performance Assurance settlement risk analysis | E.ON UK | 2014-08-08 | Closed | Modification | Governance | Withdrawn | End of process | 2015-06-24 |  |  | Scotia Gas Networks | 1 | Mod withdrawn |  |  |  | n/a
0508 |  | Revised Distributed Gas Charging Arrangements | National Grid Distribution | 2014-07-04 | Closed | Modification | DN Charging Methodology Forum | Withdrawn | End of process | 2014-10-24 |  |  | National Grid Distribution | n/a | Mod withdrawn |  |  |  | n/a
0507 |  | Changing The Effective Date of 0451AV | Winchester Gas | 2014-07-01 | Closed | Modification | Distribution | Implemented | Effective date | 2014-11-01 |  |  | National Grid Distribution | 8 | Panel Requested Text 21/08/13 | 2014-09-11 | 2014-08-21 | Y | n/a
0506 | AV | Gas Performance Assurance Framework and Governance Arrangements | SSE | 2015-11-19 | Closed | Modification | Performance Assurance | Rejected | End of process | 2015-12-17 |  |  | Wales & West Utilities | n/a | Panel Requested Text 19/11/15 | 2015-12-10 | 2015-11-19 | Y | n/a
0506 | A | Gas Performance Assurance Framework and Governance Arrangements | SSE | 2015-01-02 | Closed | Modification | Performance Assurance | Withdrawn | End of process | 2015-11-19 |  |  | Wales & West Utilities | n/a | Panel Requested Text 18/06/15 | 2015-07-09 | 2015-06-30 | Y | n/a
0506 | V | Gas Performance Assurance Framework and Governance Arrangements | Scottish Power | 2015-11-19 | Closed | Modification | Performance Assurance | Implemented | Effective date | 2016-01-29 |  |  | Wales & West Utilities | 7 | Panel Requested Text 19/11/15 | 2015-12-10 | 2015-11-19 | Y | n/a
0506 |  | Gas Performance Assurance Framework and Governance Arrangements | Scottish Power | 2014-06-12 | Closed | Modification | Performance Assurance | Withdrawn | End of process | 2015-11-19 |  |  | Wales & West Utilities | 7 | Panel Requested Text 18/06/15 | 2015-07-09 | 2015-06-30 | Y | n/a
0505 | S | Update to UNC TPD Section G & M to correct anomalies arising from the implementation of UNC Modification 0463S | Scotia Gas Networks | 2014-06-06 | Closed | Self-Governance | Distribution | Withdrawn | End of process | 2014-10-22 |  |  | Scotia Gas Networks | n/a | Mod withdrawn | 2014-07-10 | 2014-06-30 |  | n/a
0504 |  | Demand Side Response (DSR) Methodology Implementation | National Grid NTS | 2014-06-04 | Closed | Modification | Demand Side Response | Implemented | Effective date | 2016-03-01 |  |  | National Grid NTS | n/a | Panel Requested Text 19/11/15 | 2015-12-10 | 2015-11-19 | Y | n/a
0503 | FT | Update of Transporter Procedure Document references within Network Code | E.ON UK | 2014-06-02 | Closed | Fast Track | Distribution | Implemented | Effective date | 2014-08-08 |  |  | (Proposed as FT - Text included) | n/a | FT Mod - Text provided with the Mod | 2014-07-18 | 2014-07-18 | Y | n/a
0502 |  | Amendment to Gas Quality NTS Entry Specification at the px Teesside System Entry Point | Energy24 Limited | 2014-05-01 | Closed | Modification | Transmission | Implemented | Effective date | 2015-09-28 |  |  | National Grid NTS | n/a | No Text req'd - enabling Mod |  |  |  | n/a
0501 | CV | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations, including a capped capacity return option and an aggregate overrun regime. | Eni | 2015-05-01 | Closed | Modification | European | Rejected | End of process | 2015-07-20 |  |  | National Grid NTS | n/a | Panel requested text 18/12/14 | 2015-01-14 | 2015-01-14 | Y | n/a
0501 | C | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations, including a capped capacity return option and an aggregate overrun regime. | Eni | 2014-11-07 | Closed | Modification | European | Withdrawn | End of process | 2015-05-01 |  |  | National Grid NTS | n/a | Panel Requested Text 16/10/14 | 2014-11-06 | 2014-10-17 | Y | Yes
0501 | BV | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations, including a restricted capacity return option. | Centrica Storage | 2015-05-01 | Closed | Modification | European | Rejected | End of process | 2015-07-20 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-10-02 | Y | n/a
0501 | B | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations, including a restricted capacity return option. | Centrica Storage | 2014-10-10 | Closed | Modification | European | Withdrawn | End of process | 2015-05-01 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-10-02 | Y | n/a
0501 | AV | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations, including capacity return option. | Centrica Energy | 2015-05-01 | Closed | Modification | European | Rejected | End of process | 2015-07-20 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-10-02 | Y | n/a
0501 | A | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations, including capacity return option. | Centrica Energy | 2014-07-23 | Closed | Modification | European | Withdrawn | End of process | 2015-05-01 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-10-02 | Y | n/a
0501 | V | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations | National Grid NTS | 2015-05-01 | Closed | Modification | European | Implemented | Effective date | 2015-07-21 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-10-02 | Y | n/a
0501 |  | Treatment of Existing Entry Capacity Rights at the Bacton ASEP to comply with EU Capacity Regulations | National Grid NTS | 2014-05-01 | Closed | Modification | European | Withdrawn | End of process | 2015-05-01 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-10-02 | Y | n/a
0500 |  | EU Capacity Regulations – Capacity Allocation Mechanisms with Congestion Management Procedures | National Grid NTS | 2014-05-01 | Closed | Modification | European | Implemented | Effective date | 2015-06-19 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-10-02 | Y | n/a
0499 | FT | Amendment to TPD Section G1.6.13(e)(iv) | National Grid Distribution | 2014-04-10 | Closed | Fast Track | Distribution | Implemented | Effective date | 2014-10-01 |  |  | National Grid Distribution | n/a | FT - text provided with mod | 2014-09-18 | 2014-09-18 | Y | n/a
0498 |  | Amendment to Gas Quality NTS Entry Specification at BP Teesside System Entry Point | BP Gas Marketing | 2014-04-04 | Closed | Modification | Transmission | Implemented | Effective date | 2015-09-28 |  |  | National Grid NTS | n/a | No Text req'd - enabling Mod |  |  |  | n/a
0497 |  | Removal of the CSEP NExA table held within Annex A part 8 | RWE Npower | 2014-04-04 | Closed | Modification | Distribution | Implemented | Effective date | 2015-02-27 |  |  | National Grid Distribution | 6 | Panel Requested Text 21/08/13 | 2014-09-11 | 2014-08-21 | Y | n/a
0496 | FT | Reinstatement of Calendar Days as a measure in Section G2.5.8(b) | Scotia Gas Networks | 2014-04-04 | Closed | Fast Track | Governance | Implemented | Effective date | 2014-05-14 |  |  | Scotia Gas Networks | n/a | FT - text provided with mod | 2014-04-17 | 2014-04-17 | Y | n/a
0495 |  | Introduction of a Change Board for the UNC | E.ON UK | 2014-04-04 | Closed | Modification | Governance | Withdrawn | End of process | 2014-11-04 |  |  | Scotia Gas Networks | 5 | Mod withdrawn |  |  |  | n/a
0494 |  | Imbalance Charge amendments required to align the UNC with the Network Code on Gas Balancing of Transmission Networks | National Grid NTS | 2014-04-04 | Closed | Modification | European | Implemented | Effective date | 2015-10-01 |  |  | National Grid NTS | n/a | Panel requested Text 19/06/14 | 2014-07-10 | 2014-06-19 | Y | n/a
0493 |  | EU Gas Balancing Code - Daily Nominations at Interconnection Points (IP) | National Grid NTS | 2014-04-04 | Closed | Modification | European | Implemented | Effective date | 2015-06-19 |  |  | National Grid NTS | n/a | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-09-19 | Y | n/a
0492 | FT | Governance change - update to Mod Rules following Consumers' Representative's name change | National Grid NTS | 2014-04-04 | Closed | Fast Track | Governance | Implemented | Effective date | 2014-06-09 |  |  | National Grid NTS | n/a | FT - text provided with mod | 2014-06-09 | 2014-05-15 | Y | n/a
0491 |  | Change Implementation Date of Project Nexus to 1st April 2016 | National Grid NTS | 2014-03-10 | Closed | Modification | Distribution | Rejected | End of process | 2014-05-16 |  |  | National Grid NTS | n/a | Sugg Text was confirmed as formal Text at Panel 11/03/14 | 2014-04-01 | 2014-03-11 | Y | n/a
0490 | S | Updates to UNC TPD Section B to correct anomalies arising from the implementation of UNC Modification 0376S “Increased Choice when Applying for NTS Exit Capacity | National Grid NTS | 2014-03-07 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2014-05-14 |  |  | National Grid NTS | n/a | FT - text provided with mod | 2014-05-15 | 2014-05-15 | Y | n/a
0489 |  | EU Gas Balancing Code - Information Provision changes required to align the UNC with the EU Code | National Grid NTS | 2014-03-07 | Closed | Modification | European | Implemented | Effective date | 2015-10-01 |  |  | National Grid NTS | n/a | Panel requested Text 19/06/14 | 2014-07-10 | 2014-06-19 | Y | n/a
0488 | S | Additional Changes to the Mod 81 Reports | Scottish Power | 2014-03-07 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2014-07-01 |  |  | National Grid Distribution | 4 | Panel requested text 15/05/14 | 2014-06-09 | 2014-05-15 | Y | n/a
0487 | V | Introduction of an Advanced Meter Reader (AMR) Service Provider (ASP) Identifier (ASP ID) and Advanced Meter Indicator | Gazprom | 2014-10-16 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2015-04-01 |  |  | Northern Gas Networks | 3 | Panel requested text 17/07/14, NGN 'stop' note 12/08/14 | 2014-09-05 | 2014-09-05 | Y | Yes
0487 | S | Introduction of Advanced Meter Indicator and Advanced Meter Reader (AMR) Service Provider Identifier in advance of Project Nexus Go Live | Gazprom | 2014-03-05 | Closed | Self-Governance | Distribution | Withdrawn | End of process | 2014-10-16 |  |  | Northern Gas Networks | 3 | Panel requested text 17/07/14, NGN 'stop' note 12/08/14 | 2014-09-05 | 2014-09-05 | Y | n/a
0486 |  | Use of the Pre-Payment Profile For IGTs | Winchester Gas | 2014-02-25 | Closed | Modification | Distribution | Withdrawn | End of process | 2014-07-04 |  |  | National Grid Distribution | 2 | Withdrawn |  |  |  | n/a
0485 |  | Introduction of the Long-term use-it-or-lose-it mechanism to facilitate compliance with the EU Congestion Management Procedures | National Grid NTS | 2014-02-07 | Closed | Modification | European | Implemented | Effective date | 2014-09-30 |  |  | National Grid NTS | n/a | Panel requested text 15/05/14 | 2014-06-05 | 2014-05-30 | Y | n/a
0484 | S | Guidance for the production of legal text | Gazprom | 2014-02-07 | Closed | Self-Governance | Governance | Implemented | Effective date | 2014-07-11 |  |  | Scotia Gas Networks | 1 | Panel requested text 20/02/14 | 2014-03-14 | 2014-03-14 | Y | n/a
0483 |  | Performance Assurance Framework Incentive Regime | British Gas | 2014-02-07 | Closed | Modification | Performance Assurance | Withdrawn | End of process | 2015-03-06 |  |  | National Grid Distribution transferred to WWU | 8 | Mod withdrawn |  |  |  | n/a
0482 | S | Proposed Changes to Mod 81 Reports to be effective from 01/7/14 | Scottish Power | 2014-02-06 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2014-07-01 |  |  | Wales & West Utilities | 7 | Panel requested text 20/02/14 | 2014-03-13 | 2014-04-30 | N | n/a
0481 |  | Amendment to AQ Values Present Within Annex A of the CSEP NExA AQ Table Following the 2013 AQ Review | SSE | 2014-02-03 | Closed | Modification | Distribution | Implemented | Effective date | 2014-10-01 |  |  | National Grid Distribution |  | 04/02/14 CW confirmed none required for UNC |  |  |  | n/a
0480 | FT | Minor update to UNC General Terms Section B | Northern Gas Networks | 2014-01-27 | Closed | Fast Track | Distribution | Implemented | Effective date | 2014-03-14 |  |  | Northern Gas Networks |  | FT - text provided with mod | 2014-03-14 | 2014-03-14 | Y | n/a
0479 | S | Inclusion of email as a valid UNC communication’ | Northern Gas Networks | 2014-01-27 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2015-03-13 |  |  | Northern Gas Networks |  | Panel Requested Text 20/11/14 | 2014-12-11 | 2014-12-02 | Y | n/a
0478 |  | Filling the gap for SOQ reductions below BSSOQ until Project Nexus | Northern Gas Networks | 2014-01-27 | Closed | Modification | Distribution | Implemented | Effective date | 2014-10-01 |  |  | Northern Gas Networks |  | Sugg Text was confirmed as formal Text at Panel 20/02/14 |  |  |  | n/a
0477 |  | Supply Point Registration - Facilitation of Faster Switching | British Gas | 2014-01-03 | Closed | Modification | Distribution | Implemented | Effective date | 2014-11-07 |  |  | Scotia Gas Networks |  | Panel requested text 20/02/14 |  |  |  | Yes
0476 | S | Alignment of DN Charging Methodology with RIIO-GD1 Arrangements | National Grid Distribution | 2013-12-30 | Closed | Self-Governance | DN Charging Methodolgy Forum | Implemented | Effective date | 2014-04-01 |  |  | National Grid Distribution |  | Sugg Text was confirmed as formal Text at Panel 16/01/13 |  |  |  | n/a
0475 | S | Update to Section G, Annex G3 (Prospective Erroneous Large AQ Calculation Proforma) | Scottish Power | 2013-12-23 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2014-07-11 |  |  | National Grid Distribution |  | Panel requested text 15/05/14 | 2014-06-09 | 2014-04-08 | Y | n/a
0474 | S | Inclusion of the guidelines relating to the "Customer Settlement Error Claims Process" within UNC governance and introduction of the User Pays charges associated with such claims | National Grid Distribution | 2013-12-10 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2014-06-09 |  |  | National Grid Distribution |  | Panel requested text 19/12/13 |  |  |  | Yes
0473 | A | Project Nexus – Allocation of Unidentified Gas | British Gas | 2014-05-01 | Closed | Modification | Nexus | Rejected | End of process | 2014-11-20 |  |  | Northern Gas Networks |  | Panel requested text 16/10/14 | 2014-11-06 | 2014-11-12 | N | Yes
0473 |  | Project Nexus – Allocation of Unidentified Gas | Gazprom | 2013-11-18 | Closed | Modification | Nexus | Implemented | Effective date | Nexus Imp Date |  |  | Northern Gas Networks |  | Panel requested text 17/04/14 | 2014-05-13 | 2014-05-14 | N | Yes
0472 | S | Reporting the number of registration attempts by a Gas Shipper | RWE Npower | 2013-11-11 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2014-09-15 |  |  | National Grid Distribution |  | Panel requested text 19/06/2014 | 2014-07-10 | 2014-07-08 | Y | n/a
0471 | S | Amending the start time that a Day-ahead Market Offer can be accepted | EDF Energy | 2013-11-08 | Closed | Self-Governance | Transmission | Implemented | Effective date | 2014-04-29 |  |  | National Grid NTS |  | Panel requested text 21/11/13 |  |  |  | Yes
0470 |  | Notification of Minimal Safety operating gas needs of large customers | Wingas | 2013-10-04 | Closed | Modification | Distribution | Withdrawn | End of process | 2014-09-16 |  |  | Scotia Gas Networks |  | Withdrawn 16/09/14 |  |  |  | n/a
0469 | S | Transporter Gas Safety Visit Reporting | British Gas | 2013-10-04 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2015-01-14 |  |  | National Grid Distribution |  | Panel requested text 16/10/14 | 2014-11-06 | 2014-10-22 | Y | n/a
0468 |  | Unique Property Reference Number (UPRN) Population by Gas Transporters | E.ON UK | 2013-10-01 | Closed | Modification | Distribution | Withdrawn | End of process | 2015-12-21 |  |  | National Grid Distribution |  | Withdrawn 21/12/15 |  |  |  | n/a
0467 |  | Project Nexus - iGT Single Service Provision; data preparation | National Grid Distribution | 2013-10-01 | Closed | Modification | Nexus | Implemented | Effective date | 2015-01-16 |  |  | National Grid Distribution |  | Panel requested text 17/10/13 | 2013-11-07 | 2014-02-04 | N | n/a
0466 | AV | Daily Meter Reading Simplification with improved within day data provision | Wingas | 2014-06-23 | Closed | Modification | Distribution | Implemented | Effective date | 2016-04-01 |  |  | National Grid Distribution |  | (Panel Requested Text for 0466A 18/09/14 - Mod withdrawn/replaced by 0466AV) | 2014-10-09 | 2014-08-26 | Y | n/a
0466 | A | Daily Meter Reading Simplification with improved within day data provision | Wingas | 2014-06-23 | Closed | Modification | Distribution | Withdrawn | End of process | 2015-02-19 |  |  | National Grid Distribution |  | Panel Requested Text 18/09/14 | 2014-10-09 | 2014-08-26 | Y | Yes
0466 |  | Daily Meter Reading Simplification | National Grid Distribution | 2013-10-01 | Closed | Modification | Distribution | Rejected | End of process | 2015-03-26 |  |  | National Grid Distribution |  | Panel requested text 15/05/14 | 2014-06-05 | 2014-05-19 | Y | n/a
0465 | V | Introduction of the Planning and Advanced Reservation of Capacity Agreement (PARCA), Weighted Average PARCA Security | SSE | 2013-09-27 | Closed | Modification | Transmission | Implemented | Effective date | 2015-02-02 |  |  | National Grid NTS |  | Sugg Text was confirmed as formal Text at Panel 17/10/13 |  |  |  | n/a | Legal Text Delivery not actively tracked prior to this date
0464 |  | Alternative LNG supply to the Scottish Independent Networks (SINs) | Scotia Gas Networks | 2013-09-06 | Closed | Urgent | Distribution | Implemented | Effective date | 2013-10-31 |  |  | Scotia Gas Networks |  | Text was confirmed as formal Text at Panel 17/10/13 |  |  |  | n/a
0463 | S | Recognition of the ‘2nd January’ Scottish Bank Holiday as a Business Day for Supply Point related transactions | SSE | 2013-08-02 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2014-03-14 |  |  | Scotia Gas Networks |  | Panel requested text 21/11/13 |  |  |  | n/a
0462 |  | Introducing Fast Track Self Governance into the Uniform Network Code | Scotia Gas Networks | 2013-08-01 | Closed | Modification | Governance | Implemented | Effective date | 2013-12-31 |  |  | Scotia Gas Networks |  | Panel requested text 21/11/13 |  |  |  | n/a
0461 |  | Changing the UNC Gas Day to Align with the Gas Day in EU Network Codes | National Grid NTS | 2013-06-07 | Closed | Modification | Transmission | Implemented | Effective date | 2015-10-01 |  |  | National Grid NTS |  | Panel requested text 21/11/13 |  |  |  | n/a
0460 | S | Alignment of capacity and revenue treatment within the NTS Charging Methodology with RIIO-T1 arrangements | National Grid NTS | 2013-06-07 | Closed | Self-Governance | NTS Charging Methodology Forum | Implemented | Effective date | 2013-10-11 |  |  | National Grid NTS |  | 2013-06-20 |  |  |  | n/a
0459 | S | Amendments to the 'K' revenue adjustment factor based on RIIO-T1 | National Grid NTS | 2013-06-07 | Closed | Self-Governance | NTS Charging Methodology Forum | Implemented | Effective date | 2013-09-09 |  |  | National Grid NTS |  | 2013-06-20 |  |  |  | n/a
0458 |  | Seasonal LDZ System Capacity Rights. | Scotia Gas Networks | 2013-06-07 | Closed | Modification | Distribution | Implemented | Effective date | 2015-02-28 |  |  | Scotia Gas Networks |  | Panel requested text 21/11/13 |  |  |  | n/a
0457 | S | Extending the use of the UK Link Network (Information Exchange (IX)) to Meter Asset Provider (MAP) organisations | National Grid Distribution | 2013-06-04 | Closed | Self-Governance | Distribution | Implemented | Effective date | 2013-12-13 |  |  | National Grid Distribution |  | 2013-09-19 |  |  |  | n/a
0456 |  | Revision to the treatment of Allocation of Unidentified Gas for the 2013/14 AUG Year | British Gas | 2013-05-24 | Closed | Urgent | Distribution | Rejected | End of process | 2013-06-28 |  |  | National Grid Distribution |  | 03/06/13 (Ofgem) |  |  |  | n/a
0455 |  | Updating of Meter Information by the Transporter | National Grid Distribution | 2013-05-21 | Closed | Modification | Distribution | Implemented | Effective date | 2014-05-27 |  |  | National Grid Distribution |  | Panel requested text 21/11/13 |  |  |  | Yes
0454 |  | Introduction of a Long Term Non Firm Capacity Product | National Grid NTS | 2013-05-02 | Closed | Modification | Transmission | Rejected | End of process | 2014-06-20 |  |  | National Grid NTS |  | 2013-09-19 |  |  |  | Yes
0453 |  | Project Nexus - Demand Estimation | National Grid Distribution | 2013-04-23 | Closed | Modification | Nexus | Withdrawn | End of process | 2013-10-18 |  |  | National Grid Distribution |  | 19/09/2013 (mod withdrawn 18/10/13) |  |  |  | n/a
0452 | V | Introduction of the Planning and Advanced Reservation of Capacity Agreement (PARCA) | National Grid NTS | 2013-04-05 | Closed | Modification | Transmission | Rejected | End of process | 2014-12-05 |  |  | National Grid NTS |  | Sugg Text was confirmed as formal Text at Panel 17/10/13 |  |  |  | n/a
0451 | AV | Individual Settlements For Pre-Payment & Smart Meters | E.ON UK | 2013-07-04 | Closed | Modification | Distribution | Implemented | Effective date | 2014-02-01 |  |  | Northern Gas Networks |  | 18/07/2013 (0451A); 0451AV provided 22/12/13 |  |  |  | n/a
0451 | V | Individual Settlements For Pre-Payment & Smart Meters | Winchester Gas | 2013-03-27 | Closed | Urgent | Distribution | Rejected | End of process | 2014-01-31 |  |  | Northern Gas Networks |  | 20/06/2013(0451); revised text for 0451V 10/01/14 |  |  |  | Yes

## Lookups
Automated Status Path (must be alphabetical do not edit)
Current Status | Next Stage | Live/Closed | Proposing Organisation List | Category List | Workgroup
Allocated to Workgroup | Report to Panel | Live | Barrow Shipping Ltd | Modification | Distribution
Consultation Closed | Final Mod Report | Live | BG | Request | European
Final Mod Report | Panel Consideration | Live | BP | Review | Governance
Final Mod Report Sent Back by Ofgem | Panel Consideration | Live | British Gas | Self-Governance | Offtake
Implemented | Effective date | Closed | British Gas Trading | Significant Code Review | Performance Assurance
New Proposal | Panel Consideration | Live | Cadent | Suspended SCR | Nexus
|  |  | Centrica | Urgent | Transmission
Panel did not recommend implementation | Ofgem decision | Live | Centrica Storage Ltd | Timetable Directed | NTS CMF
Panel recommended implementation | Ofgem decision | Live | ConocoPhillips | Fast Track | DN CMF
Rejected | End of process | Closed | Corona Energy |  | Demand Side Response
Renumbered | End of process | Closed | E.ON UK |  | Market Operator
Representations invited | Consultation end | Live | EDF Energy |  | None
Request Closed | End of process | Closed | EDF Trading |  | Other
Sent to Ofgem | Ofgem decision | Live | Electricity Supply Board |  | UIG
Withdrawn | End of process | Closed | Energy 24
energywatch
Exxon Mobil
first:utility
GasTerra
SUGGESTED STATUS PATH |  |  | Gaz de France
Reference Purpsoses ONLY |  |  | Gazprom
Current Status | Next Stage | Live/Closed | ICE Endex
New Proposal | Panel Consideration | Live | Locus Energy
Allocated to Workgroup | Report to Panel | Live | Macquarie Bank
Legal Text being prepared? | Report to Panel | Live | National Grid Gas Distribution
Representations invited | Consultation end | Live | National Grid NTS
Consultation Closed | Final Mod Report | Live | National Grid LNG Storage
Final Mod Report | Panel Consideration | Live | Northern Gas Networks
Panel did not recommend implementation | Ofgem decision (date in red) | Live | Opus Energy
Panel recommended implementation | Ofgem decision (date in red) | Live | RWE Npower
Implemented | Effective date | Closed | RWE Trading GmbH
Final Mod Report Sent Back by Ofgem | Panel Consideration | Live | SGN
Renumbered | End of process | Closed | Scottish Power
Withdrawn | End of process | Closed | Scottish&Southern Energy
Lapsed? | End of process | Closed | Shell
Rejected | End of process | Closed | Spark Energy
Sent to Ofgem | Ofgem decision | Live | SSE
Urgent Status Requested? | Ofgem decision or Panel Consideration | Live | Statoil UK
? Denotes no longer used |  |  | Total Gas and Power
Vermilion Energy Ireland Ltd
Wales & West Utilities
Winchester Gas
Wingas
Suggested Validation Look Ups Lists (pre automation)
Current Status | Next Stage | Live/Closed
New Proposal | Panel Consideration | Live
Rejected | Report to Panel | Closed
Allocated to Workgroup | Consultation end
Representations invited | Final Mod Report
Consultation Closed | Panel recommendation
Final Mod Report | Ofgem decision
Panel recommended implementation | Ofgem decision on urgency
Panel did not recommend implementation | None
Implemented | Effective date
Final Mod Report Sent Back by Ofgem | End of process
Renumbered | Renumbered
Withdrawn
Sent to Ofgem

## Legal Text Rotation
UNC Text Allocation Register
| Rotation | Transporter
| 1 | Scotia Gas Networks
| 2 | Cadent | Chris Warner
| 3 | Northern Gas Networks
| 4 | Cadent | Chris Warner
| 5 | Scotia Gas Networks
| 6 | Cadent | Chris Warner
| 7 | Wales & West Utilities | Richard Pomroy
| 8 | Cadent | Chris Warner

This register identifies the text provider, in column G, for each modification. Column F 'Rotation' shows who is next using the numerical order in the Transporter list at the top of this sheet.
Transporter raised modifications are not subject to this rota and are shown 'n/a., as are certain other modifications not requiring text (eg Fast Track mods with shipper-supplied text).
Columns P-S track the delivery of the text.